SELECTION OF CONSULTANTS

Request for Proposals

Consulting Services

Procurement of:

Development and delivery of managerial training

RFP No: GD-PCU - GRENADA-381458-CS-QCBS

Consulting Services for: Development and delivery of managerial training

Client: Ministry of ICT

Country: Grenada

Issued on: August 29th, 2024

TABLE OF CONTENT

PART I	3

Section 1. Request for Proposal Letter	3

Section 2. Instructions to Consultants and Data Sheet	6

Section 3.  Technical Proposal – Standard Forms	37

Section 4.  Financial Proposal - Standard Forms	66

Section 5.  Eligible Countries	77

Section 6.  Fraud and Corruption	79

Section 7.  Terms of Reference	81

PART II	87

Section 8. Conditions of Contract and Contract Forms	87

PART III	194

Section 9. Notification of Intention to Award and Beneficial Ownership Forms	194

PART I

Section 1. Request for Proposal Letter

Request for Proposal Letter

Consulting Services

Name of Assignment: Development and delivery of Managerial Training

RFP Reference No.: GD-PCU - GRENADA-381458-CS-QCBS

Credit No.: IDA-66790

Country: Grenada

Date: August 29th, 2024

- The Ministry of ICT (hereinafter called “Borrower”) has received financing from the International Development Association (IDA) (the “Bank”) in the form of a “credit” (hereinafter called “credit” toward the cost of Caribbean Digital Transformation Project. The Ministry of ICT, an implementing agency of the Client, intends to apply a portion of the proceeds of this credit to eligible payments under the contract for which this Request for Proposals is issued. Payments by the Bank will be made only at the request of the Ministry of ICT and upon approval by the Bank, and will be subject, in all respects, to the terms and conditions of the financing agreement. The financing agreement prohibits a withdrawal from the credit account for the purpose of any payment to persons or entities, or for any import of goods, if such payment or import, to the knowledge of the Bank, is prohibited by a decision of the United Nations Security council taken under Chapter VII of the Charter of the United Nations. No party other than the Ministry of ICT shall derive any rights from the financing agreement or have any claims to the proceeds of the credit.

- The Client now invites proposals to provide the following consulting services (hereinafter called “Services”): Development and delivery of Managerial Training. More details on the Services are provided in the Terms of Reference (Section 7).

- This Request for Proposals (RFP) has been addressed to the following shortlisted Consultants:

- 1.	Coherent							Grenada

- 2.	eLearning Kings						Grenada

- 3.	HelpUsTrade 							United Kingdom

- 4 	Kimron Corion Digital Media Expert and Strategist	 	Grenada

- 5.    ITC Consulting						Grenada

- 6.    Aninver Development Partners				Spain

- It is not permissible to transfer this RFP to any other firm.

- A firm will be selected under Quality And Cost-Based Selection procedures and in a Full Technical Proposal (FTP) format as described in this RFP, in accordance with the Bank’s “Procurement Regulations for IPF Borrowers” July 2016, November 2017, July 2018, November 2020, September 2023  (“Procurement Regulations”), which can be found at the following website: www.worldbank.org

The RFP includes the following documents:

Section 1 – Request for Proposals Letter

Section 2 - Instructions to Consultants and Data Sheet

Section 3 - Technical Proposal FTP - Standard Forms

Section 4 - Financial Proposal - Standard Forms

Section 5 – Eligible Countries

Section 6 – Fraud and Corruption

Section 7 - Terms of Reference

Section 8 - Standard Forms of Contract (Lump Sum)

- Please inform us by September 4th, 2024, in writing at by E-mail spo@procurement.gov.gd :

(a)	that you have received this Request for Proposals; and

(b)	whether you intend to submit a proposal alone or intend to enhance your experience by requesting permission to associate with other firm(s) (if permissible under Section 2, Instructions to Consultants (ITC), Data Sheet 14.1.1).

- Attention is drawn to the Procurement Regulations requiring the Borrower to disclose information on the successful Consultant’s beneficial ownership, as part of the Contract Award Notice, using the Beneficial Ownership Disclosure Form as included in the Request for Proposals.

- Details on the proposal’s submission date, time and address are provided in ITC 17.7 and ITC 17.9.

Yours sincerely,

Jenny Alexander-Lalgie

Chief Procurement Officer (Ag.)

Financial Complex

The Carenage

St. George’s, Grenada

Section 2. Instructions to Consultants and Data Sheet

TABLE OF CONTENT

A.  General Provisions	8

1.	Definitions	8

2.	Introduction	10

3.	Conflict of Interest	11

4.	Unfair Competitive Advantage	12

5.	Fraud and Corruption	12

6.	Eligibility	12

B.  Preparation of Proposals	14

7.	General Considerations	14

8.	Cost of Preparation of Proposal	14

9.	Language	14

10.	Documents Comprising the Proposal	14

11.	Only One Proposal	15

12.	Proposal Validity	15

13.	Clarification and Amendment of RFP	16

14.	Preparation of Proposals Specific Considerations	17

15.	Technical Proposal Format and Content	18

16.	Financial Proposal	18

C.  Submission, Opening and Evaluation	19

17.	Submission, Sealing, and Marking of Proposals	19

18.	Confidentiality	20

19.	Opening of Technical Proposals	21

20.	Proposals Evaluation	21

21.	Evaluation of Technical Proposals	21

22.	Notification of Results of Technical Evaluation, Opening of /Invitation to Submit Financial Proposals for QBS	21

23.	Public Opening of Financial Proposals (for QCBS, FBS, and LCS methods)	22

24.	Correction of Errors	24

25.	Taxes	24

26.	Conversion to Single Currency	25

27.	Combined Quality and Cost Evaluation	25

D.  Negotiations and Award	25

28.	Negotiations	25

29.	Conclusion of Negotiations	26

30.	Standstill Period	27

31.	Notification of Intention to Award	27

32.	Notification of Award	28

33.	Debriefing by the Client	29

34.	Signing of Contract	29

35.	Procurement Related Complaint	29

E.  Data Sheet	30

[Notes to the Client: this part of Section 2, Instructions to Consultants, shall not be modified. Any necessary changes, acceptable to the Bank, to address specific country and project issues, to supplement, but not over-write, the provisions of the Instructions to Consultants (ITC), shall be introduced through the Data Sheet only. “Notes to the Client” should be deleted from the final RFP issued to the shortlisted Consultants].

Instructions to Consultants

A.  General Provisions

| Definitions |  | - “Affiliate(s)” means an individual or an entity that directly or indirectly controls, is controlled by, or is under common control with the Consultant. - “Applicable Law” means the laws and any other instruments having the force of law in the Client’s country, or in such other country as may be specified in the Data Sheet, as they may be issued and in force from time to time. - “Bank” means the International Bank for Reconstruction and Development (IBRD) or the International Development Association (IDA). - “Borrower” means the Government, Government agency or other entity that signs the financing agreement with the Bank. - “Client” means the implementing agency that signs the Contract for the Services with the selected Consultant. - Client’s Personnel” is as defined in Clause GCC 1.1 (e). - “Consultant” means a legally-established professional consulting firm or an entity that may provide or provides the Services to the Client under the Contract. - “Contract” means a legally binding written agreement signed between the Client and the Consultant and includes all the attached documents listed in its Clause 1 (the General Conditions of Contract (GCC), the Special Conditions of Contract (SCC), and the Appendices). - “Data Sheet” means an integral part of the Instructions to Consultants (ITC) Section 2 that is used to reflect specific country and assignment conditions to supplement, but not to over-write, the provisions of the ITC. - “Day” means a calendar day, unless otherwise specified as “Business Day”. A Business Day is any day that is an official working day of the Borrower. It excludes the Borrower’s official public holidays. - “Experts” means, collectively, Key Experts, Non-Key Experts, or any other personnel of the Consultant, Sub-consultant or Joint Venture member(s). - “Government” means the government of the Client’s country. - “in writing” means communicated in written form (e.g. by mail, e-mail, fax, including, if specified in the Data Sheet, distributed or received through the electronic-procurement system used by the Client) with proof of receipt; - “Joint Venture (JV)” means an association with or without a legal personality distinct from that of its members, of more than one Consultant where one member has the authority to conduct all business for and on behalf of any and all the members of the JV, and where the members of the JV are jointly and severally liable to the Client for the performance of the Contract. - “Key Expert(s)” means an individual professional whose skills, qualifications, knowledge and experience are critical to the performance of the Services under the Contract and whose CV is taken into account in the technical evaluation of the Consultant’s proposal. - “ITC” (this Section 2 of the RFP) means the Instructions to Consultants that provides the shortlisted Consultants with all information needed to prepare their Proposals. - “Non-Key Expert(s)” means an individual professional provided by the Consultant or its Sub-consultant and who is assigned to perform the Services or any part thereof under the Contract and whose CVs are not evaluated individually. - “Proposal” means the Technical Proposal and the Financial Proposal of the Consultant. - “RFP” means the Request for Proposals to be prepared by the Client for the selection of Consultants, based on the SPD - RFP. - “Services” means the work to be performed by the Consultant pursuant to the Contract. - “Sexual Exploitation and Abuse” “(SEA)” means the following: Sexual Exploitation is defined as any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another. Sexual Abuse is defined as the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions. - “Sexual Harassment” “(SH)” is defined as unwelcome sexual advances, requests for sexual favors, and other verbal or physical conduct of a sexual nature by the Experts with other Experts or Client’s Personnel. - “SPD - RFP” means the Standard Procurement Document - Request for Proposals, which must be used by the Client as the basis for the preparation of the RFP. - “Sub-consultant” means an entity to whom the Consultant intends to subcontract any part of the Services while the Consultant remains responsible to the Client during the whole performance of the Contract. - “Terms of Reference (TORs)” (this Section 7 of the RFP) means the Terms of Reference that explains the objectives, scope of work, activities, and tasks to be performed, respective responsibilities of the Client and the Consultant, and expected results and deliverables of the assignment. |  |
| --- | --- | --- | --- |
| Introduction |  | - The Client named in the Data Sheet intends to select a Consultant from those listed in the Request for Proposals (RFP), in accordance with the method of selection specified in the Data Sheet. - The shortlisted Consultants are invited to submit a Technical Proposal and a Financial Proposal, or a Technical Proposal only, as specified in the Data Sheet, for consulting services required for the assignment named in the Data Sheet. The Proposal will be the basis for negotiating and ultimately signing the Contract with the selected Consultant. - The Consultants should familiarize themselves with the local conditions and take them into account in preparing their Proposals, including attending a pre-proposal conference if one is specified in the Data Sheet. Attending any such pre-proposal conference is optional and is at the Consultants’ expense. - The Client will timely provide, at no cost to the Consultants, the inputs, relevant project data, and reports required for the preparation of the Consultant’s Proposal as specified in the Data Sheet. |  |
| Conflict of Interest |  | - The Consultant is required to provide professional, objective, and impartial advice, at all times holding the Client’s interests paramount, strictly avoiding conflicts with other assignments or its own corporate interests, and acting without any consideration for future work. - The Consultant has an obligation to disclose to the Client any situation of actual or potential conflict that impacts its capacity to serve the best interest of its Client. Failure to disclose such situations may lead to the disqualification of the Consultant or the termination of its Contract and/or sanctions by the Bank. - Without limitation on the generality of the foregoing, the Consultant shall not be hired under the circumstances set forth below: |  |
| a. Conflicting Activities |  | (i) Conflict between consulting activities and procurement of goods, works or non-consulting services: a firm that has been engaged by the Client to provide goods, works, or non-consulting services for a project, or any of its Affiliates, shall be disqualified from providing consulting services resulting from or directly related to those goods, works, or non-consulting services. Conversely, a firm hired to provide consulting services for the preparation or implementation of a project, or any of its Affiliates, shall be disqualified from subsequently providing goods or works or non-consulting services resulting from or directly related to the consulting services for such preparation or implementation. |  |
| b. Conflicting Assignments |  | (ii) Conflict among consulting assignments: a Consultant (including its Experts and Sub-consultants) or any of its Affiliates shall not be hired for any assignment that, by its nature, may be in conflict with another assignment of the Consultant for the same or for another Client. |  |
| c. Conflicting Relationships |  | (iii) Relationship with the Client’s staff: a Consultant (including its Experts and Sub-consultants) that has a close business or family relationship with a professional staff of the Borrower (or of the Client, or of implementing agency, or of a recipient of a part of the Bank’s financing) who are directly or indirectly involved in any part of (i) the preparation of the Terms of Reference for the assignment, (ii) the selection process for the Contract, or (iii) the supervision of the Contract, may not be awarded a Contract, unless the conflict stemming from this relationship has been resolved in a manner acceptable to the Bank throughout the selection process and the execution of the Contract. |  |
| Unfair Competitive Advantage |  | - Fairness and transparency in the selection process require that the Consultants or their Affiliates competing for a specific assignment do not derive a competitive advantage from having provided consulting services related to the assignment in question. To that end, the Client shall indicate in the Data Sheet and make available to all shortlisted Consultants together with this RFP all information that would in that respect give such Consultant any unfair competitive advantage over competing Consultants. |  |
| Fraud and Corruption |  | - The Bank requires compliance with the Bank’s Anti-Corruption Guidelines and its prevailing sanctions policies and procedures as set forth in the WBG’s Sanctions Framework, as set forth in Section 6. - In further pursuance of this policy, Consultants shall permit and shall cause their agents (where declared or not), subcontractors, subconsultants, service providers, suppliers, and personnel, to permit the Bank to inspect all accounts, records and other documents relating to any shortlisting process, Proposal submission, and contract performance (in the case of award), and to have them audited by auditors appointed by the Bank. |  |
| Eligibility |  | - The Bank permits consultants (individuals and firms, including Joint Ventures and their individual members) from all countries to offer consulting services for Bank-financed projects. - Furthermore, it is the Consultant’s responsibility to ensure that its Experts, joint venture members, Sub-consultants, agents (declared or not), sub-contractors, service providers, suppliers and/or their employees meet the eligibility requirements as established by the Bank in the applicable Procurement Regulations. - As an exception to the foregoing ITC 6.1 and ITC 6.2 above: |  |
| a. Sanctions |  | - A Consultant that has been sanctioned by the Bank, pursuant to the Bank’s Anti-Corruption Guidelines and in accordance with its prevailing sanctions policies and procedures as set forth in the WBG’s Sanctions Framework as described in Section VI, Fraud and Corruption, paragraph 2.2 d., shall be ineligible to be shortlisted for, submit proposals for, or be awarded a Bank-financed contract or benefit from a Bank-financed contract, financially or otherwise, during such period of time as the Bank shall have determined. The list of debarred firms and individuals is available at the electronic address specified in the PDS. |  |
| b. Prohibitions |  | - Firms and individuals of a country or goods manufactured in a country may be ineligible if so indicated in Section 5 (Eligible Countries) and: (a) as a matter of law or official regulations, the Borrower’s country prohibits commercial relations with that country, provided that the Bank is satisfied that such exclusion does not preclude effective competition for the provision of Services required; or (b) by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s Country prohibits any import of goods from that country or any payments to any country, person, or entity in that country. |  |
| c. Restrictions for State-Owned Enterprises |  | - State-owned enterprises or institutions in the Borrower’s country may be eligible to compete and be awarded a contract only if they can establish, in a manner acceptable to the Bank, that they: (i) are legally and financially autonomous, (ii) operate under commercial law, and (iii) are not under supervision of the Client. |  |
| d. Restrictions for Public Employees |  | - Government officials and civil servants of the Borrower’s country are not eligible to be included as Experts, individuals, or members of a team of Experts in the Consultant’s Proposal unless: (i) the services of the government official or civil servant are of a unique and exceptional nature, or their participation is critical to project implementation; and (ii) their hiring would not create a conflict of interest, including any conflict with employment or other laws, regulations, or policies of the Borrower. |  |
| e. Borrower Debarment |  | - A firm that is under a sanction of debarment by the Borrower from being awarded a contract is eligible to participate in this procurement, unless the Bank, at the Borrower’s request, is satisfied that the debarment; (a) relates to fraud or corruption, and (b) followed a judicial or administrative proceeding that afforded the firm adequate due process. |  |
| B. Preparation of Proposals |  |  |  |
| General Considerations |  | - In preparing the Proposal, the Consultant is expected to examine the RFP in detail. Material deficiencies in providing the information requested in the RFP may result in rejection of the Proposal. |  |
| Cost of Preparation of Proposal |  | - The Consultant shall bear all costs associated with the preparation and submission of its Proposal, and the Client shall not be responsible or liable for those costs, regardless of the conduct or outcome of the selection process. The Client is not bound to accept any proposal, and reserves the right to annul the selection process at any time prior to Contract award, without thereby incurring any liability to the Consultant. |  |
| Language |  | - The Proposal, as well as all correspondence and documents relating to the Proposal exchanged between the Consultant and the Client, shall be written in the language(s) specified in the Data Sheet. |  |
| Documents Comprising the Proposal |  | - The Proposal shall comprise the documents and forms listed in the Data Sheet. - If specified in the Data Sheet, the Consultant shall include a statement of an undertaking of the Consultant to observe, in competing for and executing a contract, the Client country’s laws against fraud and corruption (including bribery). - The Consultant shall furnish information on commissions, gratuities, and fees, if any, paid or to be paid to agents or any other party relating to this Proposal and, if awarded, Contract execution, as requested in the Financial Proposal submission form (Section 4). |  |
| Only One Proposal |  | - The Consultant (including the individual members of any Joint Venture) shall submit only one Proposal, either in its own name or as part of a Joint Venture in another Proposal. If a Consultant, including any Joint Venture member, submits or participates in more than one proposal, all such proposals shall be disqualified and rejected. This does not, however, preclude a Sub-consultant, or the Consultant’s staff from participating as Key Experts and Non-Key Experts in more than one Proposal when circumstances justify and if stated in the Data Sheet. |  |
| Proposal Validity |  | - Proposals shall remain valid until the date specified in the Data Sheet or any extended date if amended by the Client in accordance with ITC 13.1.1. - During this period, the Consultant shall maintain its original Proposal without any change, including the availability of the Key Experts, the proposed rates and the total price. - If it is established that any Key Expert nominated in the Consultant’s Proposal was not available at the time of Proposal submission or was included in the Proposal without his/her confirmation, such Proposal shall be disqualified and rejected for further evaluation, and may be subject to sanctions in accordance with ITC 5. |  |
| a. Extension of Proposal Validity |  | - The Client will make its best effort to complete the negotiations and award the contract prior to the date of expiry of the Proposal validity. However, should the need arise, the Client may request, in writing, all Consultants who submitted Proposals prior to the submission deadline to extend the Proposals’ validity. - If the Consultant agrees to extend the validity of its Proposal, it shall be done without any change in the original Proposal and with the confirmation of the availability of the Key Experts, except as provided in ITC 12.7. - The Consultant has the right to refuse to extend the validity of its Proposal in which case such Proposal will not be further evaluated. |  |
| b. Substitution of Key Experts at Validity Extension |  | - If any of the Key Experts become unavailable for the extended validity period, the Consultant shall seek to substitute another Key Expert. The Consultant shall provide a written adequate justification and evidence satisfactory to the Client together with the substitution request. In such case, a substitute Key Expert shall have equal or better qualifications and experience than those of the originally proposed Key Expert. The technical evaluation score, however, will remain to be based on the evaluation of the CV of the original Key Expert. - If the Consultant fails to provide a substitute Key Expert with equal or better qualifications, or if the provided reasons for the replacement or justification are unacceptable to the Client, such Proposal will be rejected. |  |
| c. Sub-Contracting |  | - The Consultant shall not subcontract the whole of the Services. |  |
| Clarification and Amendment of RFP |  | - The Consultant may request a clarification of any part of the RFP during the period indicated in the Data Sheet before the Proposals’ submission deadline. Any request for clarification must be sent in writing, or by standard electronic means, to the Client’s address indicated in the Data Sheet. The Client will respond in writing, or by standard electronic means, and will send written copies of the response (including an explanation of the query but without identifying its source) to all shortlisted Consultants. Should the Client deem it necessary to amend the RFP as a result of a clarification, it shall do so following the procedure described below: - At any time before the proposal submission deadline, the Client may amend the RFP by issuing an amendment in writing or by standard electronic means. The amendment shall be sent to all shortlisted Consultants and will be binding on them. The shortlisted Consultants shall acknowledge receipt of all amendments in writing. - If the amendment is substantial, the Client may extend the proposal submission deadline to give the shortlisted Consultants reasonable time to take an amendment into account in their Proposals. - The Consultant may submit a modified Proposal or a modification to any part of it at any time prior to the proposal submission deadline. No modifications to the Technical or Financial Proposal shall be accepted after the deadline. |  |
| Preparation of Proposals Specific Considerations |  | - While preparing the Proposal, the Consultant must give particular attention to the following: - If a shortlisted Consultant considers that it may enhance its expertise for the assignment by associating with other consultants in the form of a Joint Venture or as Sub-consultants, it may do so with either (a) non-shortlisted Consultant(s), or (b) shortlisted Consultants if permitted in the Data Sheet. In all such cases a shortlisted Consultant must obtain the written approval of the Client prior to the submission of the Proposal. When associating with non-shortlisted firms in the form of a joint venture or a sub-consultancy, the shortlisted Consultant shall be a lead member. If shortlisted Consultants associate with each other, any of them can be a lead member. - The Client may indicate in the Data Sheet the estimated Key Experts’ time input (expressed in person-month) or the Client’s estimated total cost of the assignment, but not both. This estimate is indicative and the Proposal shall be based on the Consultant’s own estimates for the same. - If stated in the Data Sheet, the Consultant shall include in its Proposal at least the same time input (in the same unit as indicated in the Data Sheet) of Key Experts, failing which the Financial Proposal will be adjusted for the purpose of comparison of proposals and decision for award in accordance with the procedure in the Data Sheet. - For assignments under the Fixed-Budget selection method, the estimated Key Experts’ time input is not disclosed. Total available budget, with an indication whether it is inclusive or exclusive of taxes, is given in the Data Sheet, and the Financial Proposal shall not exceed this budget. |  |
| Technical Proposal Format and Content |  | - The Technical Proposal shall be prepared using the Standard Forms provided in Section 3 of the RFP and shall comprise the documents listed in the Data Sheet. The Technical Proposal shall not include any financial information. A Technical Proposal containing material financial information shall be declared non-responsive. 15.1.1 Consultant shall not propose alternative Key Experts. Only one CV shall be submitted for each Key Expert position. Failure to comply with this requirement will make the Proposal non-responsive. - Depending on the nature of the assignment, the Consultant is required to submit a Full Technical Proposal (FTP), or a Simplified Technical Proposal (STP) as indicated in the Data Sheet and using the Standard Forms provided in Section 3 of the RFP. |
| Financial Proposal |  | - The Financial Proposal shall be prepared using the Standard Forms provided in Section 4 of the RFP. It shall list all costs associated with the assignment, including (a) remuneration for Key Experts and Non-Key Experts, (b) reimbursable expenses indicated in the Data Sheet. |  |
| a. Price Adjustment |  | - For assignments with a duration exceeding 18 months, a price adjustment provision for foreign and/or local inflation for remuneration rates applies if so stated in the Data Sheet. |  |
| b. Taxes |  | - The Consultant and its Sub-consultants and Experts are responsible for meeting all tax liabilities arising out of the Contract unless stated otherwise in the Data Sheet. Information on taxes in the Client’s country is provided in the Data Sheet. |  |
| c. Currency of Proposal |  | - The Consultant may express the price for its Services in the currency or currencies as stated in the Data Sheet. If indicated in the Data Sheet, the portion of the price representing local cost shall be stated in the national currency. |  |
| d. Currency of Payment |  | - Payment under the Contract shall be made in the currency or currencies in which the payment is requested in the Proposal. |  |
| C. Submission, Opening and Evaluation |  |  |  |
| Submission, Sealing, and Marking of Proposals | - The Consultant shall submit a signed and complete Proposal comprising the documents and forms in accordance with ITC 10 (Documents Comprising Proposal). Consultants shall mark as “CONFIDENTIAL” information in their Proposals which is confidential to their business. This may include proprietary information, trade secrets or commercial or financially sensitive information. The submission can be done by mail or by hand. If specified in the Data Sheet, the Consultant has the option of submitting its Proposals electronically. - An authorized representative of the Consultant shall sign the original submission letters in the required format for both the Technical Proposal and, if applicable, the Financial Proposal and shall initial all pages of both. The authorization shall be in the form of a written power of attorney attached to the Technical Proposal. - A Proposal submitted by a Joint Venture shall be signed by all members so as to be legally binding on all members, or by an authorized representative who has a written power of attorney signed by each member’s authorized representative. - Any modifications, revisions, interlineations, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the Proposal. - The signed Proposal shall be marked “Original”, and its copies marked “Copy” as appropriate. The number of copies is indicated in the Data Sheet. All copies shall be made from the signed original. If there are discrepancies between the original and the copies, the original shall prevail. - The original and all the copies of the Technical Proposal shall be placed inside a sealed envelope clearly marked “Technical Proposal”, “[Name of the Assignment]“, [reference number], [name and address of the Consultant], and with a warning “Do Not Open until [insert the date and the time of the Technical Proposal submission deadline].” - Similarly, the original Financial Proposal (if required for the applicable selection method) and its copies shall be placed inside of a separate sealed envelope clearly marked “Financial Proposal” “[Name of the Assignment], [reference number], [name and address of the Consultant]”, and with a warning “Do Not Open With The Technical Proposal.” - The sealed envelopes containing the Technical and Financial Proposals shall be placed into one outer envelope and sealed. This outer envelope shall be addressed to the Client and bear the submission address, RFP reference number, the name of the assignment, the Consultant’s name and the address, and shall be clearly marked “Do Not Open Before [insert the time and date of the submission deadline indicated in the Data Sheet]”. - If the envelopes and packages with the Proposal are not sealed and marked as required, the Client will assume no responsibility for the misplacement, loss, or premature opening of the Proposal. - The Proposal or its modifications must be sent to the address indicated in the Data Sheet and received by the Client no later than the deadline indicated in the Data Sheet, or any extension to this deadline. Any Proposal or its modification received by the Client after the deadline shall be declared late and rejected, and promptly returned unopened. |  |  |
| Confidentiality | - From the time the Proposals are opened to the time the Contract is awarded, the Consultant should not contact the Client on any matter related to its Technical and/or Financial Proposal. Information relating to the evaluation of Proposals and award recommendations shall not be disclosed to the Consultants who submitted the Proposals or to any other party not officially concerned with the process, until the Notification of Intention to Award the Contract. Exceptions to this ITC are where the Client notifies Consultants of the results of the evaluation of the Technical Proposals. - Any attempt by shortlisted Consultants or anyone on behalf of the Consultant to influence improperly the Client in the evaluation of the Proposals or Contract award decisions may result in the rejection of its Proposal, and may be subject to the application of prevailing Bank’s sanctions procedures. - Notwithstanding the above provisions, from the time of the Proposals’ opening to the time of Contract award publication, if a Consultant wishes to contact the Client or the Bank on any matter related to the selection process, it shall do so only in writing. |  |  |
| Opening of Technical Proposals | - The Client’s evaluation committee shall conduct the opening of the Technical Proposals in the presence of the shortlisted Consultants’ authorized representatives who choose to attend (in person, or online if this option is offered in the Data Sheet). The opening date, time and the address are stated in the Data Sheet. The envelopes with the Financial Proposal shall remain sealed and shall be securely stored with a reputable public auditor or independent authority until they are opened in accordance with ITC 23. - At the opening of the Technical Proposals the following shall be read out: (i) the name and the country of the Consultant or, in case of a Joint Venture, the name of the Joint Venture, the name of the lead member and the names and the countries of all members; (ii) the presence or absence of a duly sealed envelope with the Financial Proposal; (iii) any modifications to the Proposal submitted prior to proposal submission deadline; and (iv) any other information deemed appropriate or as indicated in the Data Sheet. |  |  |
| Proposals Evaluation | - Subject to provision of ITC 15.1, the evaluators of the Technical Proposals shall have no access to the Financial Proposals until the Financial Proposals are opened. - The Consultant is not permitted to alter or modify its Proposal in any way after the proposal submission deadline except as permitted under ITC 12.7. While evaluating the Proposals, the Client will conduct the evaluation solely on the basis of the submitted Technical and Financial Proposals. |  |  |
| Evaluation of Technical Proposals | - The Client’s evaluation committee shall evaluate the Technical Proposals on the basis of their responsiveness to the Terms of Reference and the RFP, applying the evaluation criteria, sub-criteria, and point system specified in the Data Sheet. Each responsive Proposal will be given a technical score. A Proposal shall be rejected at this stage if it does not respond to important aspects of the RFP or if it fails to achieve the minimum technical score indicated in the Data Sheet. |  |  |
| Notification of Results of Technical Evaluation, Opening of /Invitation to Submit Financial Proposals for QBS | - Following ranking of the Technical Proposals and determination of the proposal that has achieved the highest technical score, the Client shall notify in writing the highest ranking Consultant of its technical score and that its Technical Proposal has been evaluated as the highest ranking. - The Client shall simultaneously notify in writing the other Consultants: (i) on their overall technical score, as well as scores obtained for each criterion and sub-criterion, and that their technical proposals have not been evaluated as the highest ranked; and (ii) that their Financial Proposals will be returned unopened after completing the selection process and Contract signing. - If Financial Proposals were invited together with the Technical Proposals, the Client shall notify all of the Consultants that submitted proposals of the date, time and location of the public opening of the Financial Proposals of the highest ranking Consultant. If Financial Proposals were not invited to be submitted along with the Technical Proposals, opening of Financial Proposals does not apply, and the highest ranking Consultant shall be invited to submit its Financial Proposals for negotiations. - The opening date of the Financial Proposal or invitation of the highest ranking Consultant to submit its Financial Proposal, as applicable, shall not be earlier than ten (10) Business Days from the date of notification of the results of the technical evaluation, described in ITC 22.1 and 22.2. However, if the Client receives a complaint on the results of the technical evaluation within the ten (10) Business Days, the opening date or the date to invite submission of Financial Proposal, as applicable, shall be subject to ITC 35.1. |  |  |
| Public Opening of Financial Proposals (for QCBS, FBS, and LCS methods) | - After the technical evaluation is completed, the Client shall notify in writing those Consultants whose Proposals were considered non-responsive to the RFP and TOR or did not meet the minimum qualifying technical score, advising them the following: - their Proposal was not responsive to the RFP and TOR or did not meet the minimum qualifying technical score; - provide information relating to the Consultant’s overall technical score, as well as scores obtained for each criterion and sub-criterion; - their Financial Proposals will be returned unopened after completing the selection process and Contract signing; and - notify them of the date, time and location of the public opening of the Financial Proposals. - The Client shall simultaneously notify in writing those Consultants whose Proposals were considered responsive to the RFP and TOR, and that have achieved the minimum qualifying technical score, advising them the following: - their Proposal was responsive to the RFP and TOR and met the minimum qualifying technical score; - provide information relating to the Consultant’s overall technical score, as well as scores obtained for each criterion and sub-criterion; - their Financial Proposal will be opened at the public opening of Financial Proposals; and - notify them of the date, time and location of the public opening and invite them for the opening of the Financial Proposals. - The opening date shall not be earlier than ten (10) Business Days from the date of notification of the results of the technical evaluation, described in ITC 23.1 and 23.2. However, if the Client receives a complaint on the results of the technical evaluation within the ten (10) Business Days, the opening date shall be subject to ITC 35.1. - The Consultant’s attendance at the opening of the Financial Proposals (in person, or online if such option is indicated in the Data Sheet) is optional and is at the Consultant’s choice. - The Financial Proposals shall be opened publicly by the Client’s evaluation committee in the presence of the representatives of the Consultants and anyone else who chooses to attend. Any interested party who wishes to attend this public opening should contact the client as indicated in the Data Sheet. Alternatively, a notice of the public opening of Financial Proposals may be published on the Client’s website, if available. At the opening, the names of the Consultants, and the overall technical scores, including the break-down by criterion, shall be read aloud. The Financial Proposals will then be inspected to confirm that they have remained sealed and unopened. These Financial Proposals shall be then opened, and the total prices read aloud and recorded. Copies of the record shall be sent to all Consultants who submitted Proposals and to the Bank. |  |  |
| Correction of Errors | - Activities and items described in the Technical Proposal but not priced in the Financial Proposal, shall be assumed to be included in the prices of other activities or items, and no corrections are made to the Financial Proposal. |  |  |
| a. Time-Based Contracts | 24.1.1 If a Time-Based contract form is included in the RFP, the Client’s evaluation committee will (a) correct any computational or arithmetical errors, and (b) adjust the prices if they fail to reflect all inputs included for the respective activities or items included in the Technical Proposal. In case of discrepancy between (i) a partial amount (sub-total) and the total amount, or (ii) between the amount derived by multiplication of unit price with quantity and the total price, or (iii) between words and figures, the former will prevail. In case of discrepancy between the Technical and Financial Proposals in indicating quantities of input, the Technical Proposal prevails and the Client’s evaluation committee shall correct the quantification indicated in the Financial Proposal so as to make it consistent with that indicated in the Technical Proposal, apply the relevant unit price included in the Financial Proposal to the corrected quantity, and correct the total Proposal cost. |  |  |
| b. Lump-Sum Contracts | 24.1.2 If a Lump-Sum contract form is included in the RFP, the Consultant is deemed to have included all prices in the Financial Proposal, so neither arithmetical corrections nor price adjustments shall be made. The total price, net of taxes understood as per ITC 25, specified in the Financial Proposal (Form FIN-1) shall be considered as the offered price. Where there is a discrepancy between the amount in words and the amount figures, the amount in words shall prevail. |  |  |
| Taxes | - The Client’s evaluation of the Consultant’s Financial Proposal shall exclude taxes and duties in the Client’s country in accordance with the instructions in the Data Sheet. |  |  |
| Conversion to Single Currency | - For the evaluation purposes, prices shall be converted to a single currency using the selling rates of exchange, source and date indicated in the Data Sheet. |  |  |
| Combined Quality and Cost Evaluation |  |  |  |
| - Quality and Cost-Based Selection (QCBS) | - In the case of QCBS, the total score is calculated by weighting the technical and financial scores and adding them as per the formula and instructions in the Data Sheet. The Consultant with the Most Advantageous Proposal, which is the Proposal that achieves the highest combined technical and financial scores, will be invited for negotiations. |  |  |
| b. Fixed-Budget Selection (FBS) | - In the case of FBS, those Proposals that exceed the budget indicated in ITC 14.1.4 of the Data Sheet shall be rejected. - The Client will select the Consultant with the Most Advantageous Proposal, which is the highest-ranked Technical Proposal that does not exceed the budget indicated in the RFP, and invite such Consultant to negotiate the Contract. |  |  |
| c. Least-Cost Selection | - In the case of Least-Cost Selection (LCS), the Client will select the Consultant with the Most Advantageous Proposal, which is the Proposal with the lowest evaluated total price among those Proposals that achieved the minimum qualifying technical score, and invite such a Consultant to negotiate the Contract. |  |  |
| D. Negotiations and Award |  |  |  |
| Negotiations | - The negotiations will be held at the date and address indicated in the Data Sheet with the Consultant’s representative(s) who must have written power of attorney to negotiate and sign a Contract on behalf of the Consultant. - The Client shall prepare minutes of negotiations that are signed by the Client and the Consultant’s authorized representative. |  |  |
| a. Availability of Key Experts | - The invited Consultant shall confirm the availability of all Key Experts included in the Proposal as a pre-requisite to the negotiations, or, if applicable, a replacement in accordance with ITC 12. Failure to confirm the Key Experts’ availability may result in the rejection of the Consultant’s Proposal and the Client proceeding to negotiate the Contract with the next-ranked Consultant. - Notwithstanding the above, the substitution of Key Experts at the negotiations may be considered if due solely to circumstances outside the reasonable control of and not foreseeable by the Consultant, including but not limited to death or medical incapacity. In such case, the Consultant shall offer a substitute Key Expert within the period of time specified in the letter of invitation to negotiate the Contract, who shall have equivalent or better qualifications and experience than the original candidate. |  |  |
| b. Technical Negotiations | - The negotiations include discussions of the Terms of Reference (TORs), the proposed methodology, the Client’s inputs, the special conditions of the Contract, and finalizing the “Description of Services” part of the Contract. These discussions shall not substantially alter the original scope of services under the TOR or the terms of the contract, lest the quality of the final product, its price, or the relevance of the initial evaluation be affected. |  |  |
| c. Financial Negotiations | - The negotiations include the clarification of the Consultant’s tax liability in the Client’s country and how it should be reflected in the Contract. - If the selection method included cost as a factor in the evaluation, the total price stated in the Financial Proposal for a Lump-Sum contract shall not be negotiated. - In the case of a Time-Based contract, unit rates negotiations shall not take place, except when the offered Key Experts and Non-Key Experts’ remuneration rates are much higher than the typically charged rates by consultants in similar contracts. In such case, the Client may ask for clarifications and, if the fees are very high, ask to change the rates after consultation with the Bank. The format for (i) providing information on remuneration rates in the case of Quality Based Selection; and (ii) clarifying remuneration rates’ structure under this Clause, is provided in Appendix A to the Financial Form FIN-3: Financial Negotiations – Breakdown of Remuneration Rates. |  |  |
| Conclusion of Negotiations | - The negotiations are concluded with a review of the finalized draft Contract, which then shall be initialed by the Client and the Consultant’s authorized representative. - If the negotiations fail, the Client shall inform the Consultant in writing of all pending issues and disagreements and provide a final opportunity to the Consultant to respond. If disagreement persists, the Client shall terminate the negotiations informing the Consultant of the reasons for doing so. The Client will then invite the next-ranked Consultant to negotiate a Contract. Once the Client commences negotiations with the next-ranked Consultant, the Client shall not reopen the earlier negotiations. |  |  |
| Standstill Period | - The Contract shall not be awarded earlier than the expiry of the Standstill Period. The Standstill Period shall be ten (10) Business Days unless extended in accordance with ITC 33. The Standstill Period commences the day after the date the Client has transmitted to each Consultant (that has not already been notified that it has been unsuccessful) the Notification of Intention to Award the Contract. Where only one Proposal is submitted, or if this contract is in response to an emergency situation recognized by the Bank, the Standstill Period shall not apply. |  |  |
| Notification of Intention to Award | - The Client shall send to each Consultant (that has not already been notified that it has been unsuccessful) the Notification of Intention to Award the Contract to the successful Consultant. The Notification of Intention to Award shall contain, at a minimum, the following information: - the name and address of the Consultant with whom the client successfully negotiated a contract; - the contract price of the successful Proposal; - the names of all Consultants included in the short list, indicating those that submitted Proposals; - where the selection method requires, the price offered by each Consultant as read out and as evaluated; - the overall technical scores and scores assigned for each criterion and sub-criterion to each Consultant; - the final combined scores and the final ranking of the Consultants; - a statement of the reason(s) why the recipient’s Proposal was unsuccessful, unless the combined score in (f) above already reveals the reason; - the expiry date of the Standstill Period; and - instructions on how to request a debriefing and/or submit a complaint during the Standstill Period. |  |  |
| Notification of Award | - Upon expiry of the Standstill Period, specified in ITC 30.1 or any extension thereof, and upon satisfactorily addressing any complaint that has been filed within the Standstill Period, and upon verifying that the Consultant (including each member of a JV) is not disqualified by the Bank due to noncompliance with contractual SEA/SH prevention and response obligations, the Client shall, send a notification of award to the successful Consultant, confirming the Client’s intention to award the Contract to the successful Consultant and requesting the successful Consultant to sign and return the draft negotiated Contract within eight (8) Business Days from the date of receipt of such notification. The Client will require the Consultant to replace any subconsultant that is disqualified by the Bank due to noncompliance with contractual SEA/SH prevention and response obligations. The client shall simultaneously request the successful Consultant to submit, within eight (8) Business Days, the Beneficial Ownership Disclosure Form. Contract Award Notice Within ten (10) Business Days from the date of notification of award such request, the Client shall publish the Contract Award Notice which shall contain, at a minimum, the following information: - name and address of the Client; - name and reference number of the contract being awarded, and the selection method used; - names of the consultants that submitted proposals, and their proposal prices as read out at financial proposal opening, and as evaluated; - names of all Consultants whose Proposals were rejected or were not evaluated, with the reasons therefor; - the name of the successful consultant, the final total contract price, the contract duration and a summary of its scope; and - successful Consultant’s Beneficial Ownership Disclosure Form. - The Contract Award Notice shall be published on the Client’s website with free access if available, or in at least one newspaper of national circulation in the Client’s Country, or in the official gazette. The Client shall also publish the contract award notice in UNDB online. |  |  |
| Debriefing by the Client | - On receipt of the Client’s Notification of Intention to Award referred to in ITC 31.1, an unsuccessful Consultant has three (3) Business Days to make a written request to the Client for a debriefing. The Client shall provide a debriefing to all unsuccessful Consultants whose request is received within this deadline. - Where a request for debriefing is received within the deadline, the Client shall provide a debriefing within five (5) Business Days, unless the Client decides, for justifiable reasons, to provide the debriefing outside this timeframe. In that case, the standstill period shall automatically be extended until five (5) Business Days after such debriefing is provided. If more than one debriefing is so delayed, the standstill period shall not end earlier than five (5) Business Days after the last debriefing takes place. The Client shall promptly inform, by the quickest means available, all Consultants of the extended standstill period. - Where a request for debriefing is received by the Client later than the three (3)-Business Day deadline, the Client should provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of Public Notice of Award of contract. Requests for debriefing received outside the three (3)-day deadline shall not lead to extension of the standstill period. - Debriefings of unsuccessful Consultants may be done in writing or verbally. The Consultants shall bear their own costs of attending such a debriefing meeting. |  |  |
| Signing of Contract | - The Contract shall be signed prior to the expiry date of the Proposal validity and promptly after expiry of the Standstill Period, specified in ITC 30.1 or any extension thereof, and upon satisfactorily addressing any complaint that has been filed within the Standstill Period. - The Consultant is expected to commence the assignment on the date and at the location specified in the Data Sheet. |  |  |
| Procurement Related Complaint | - The procedures for making a Procurement-related Complaint are as specified in the Data Sheet. |  |  |

Section 2. Instructions to Consultants

E.  Data Sheet

| ITC Reference | A. General |  |
| --- | --- | --- |
| 1 (b) | Grenada |  |
| 1 (o) | Electronic –Procurement System The Client shall use the following electronic-procurement system to manage this Request for Proposal (RFP) process: https://in-tendhost.co.uk/GND/aspx/Home The electronic-procurement system shall be used to manage the following part of the RFP process: The electronic-procurement system shall be used to manage the following aspects of the Proposal process: issuance of the procurement documents, clarifications and addenda to the procurement documents, submission and opening of proposals. |  |
| 2.1 | Name of the Client: Ministry of ICT Method of selection: Quality and Cost-Based Selection as per the Procurement Regulations (available on www.worldbank.org) |  |
| 2.2 | Financial Proposal to be submitted together with Technical Proposal: Yes No _ The name of the assignment is: Development and delivery of Managerial Training |  |
| 2.3 | A pre-proposal conference will be held: Yes or No [If “Yes”, fill in the following:] Date of pre-proposal conference:____________________________ Time: _________________________________________________ Address: Telephone: Facsimile: E-mail: Contact person/conference coordinator:[insert name and title] _____________________________ |  |
| 2.4 | The Client will provide the following inputs, project data, reports, etc. to facilitate the preparation of the Proposals: N/A |  |
| 6.3.1 | A list of debarred firms and individuals is available at the Bank’s external website: www.worldbank.org/debarr |  |
| B. Preparation of Proposals |  |  |
| 9.1 | This RFP has been issued in the English language. Proposals shall be submitted in English language. All correspondence exchange shall be in English language. |  |
| 10.1 | For SIMPLIFIED TECHNICAL PROPOSAL (STP): 1st Inner Envelope with the Technical Proposal: - Power of Attorney to sign the Proposal - TECH-1 - TECH-2 - TECH-4 - TECH-5 - TECH-6 - TECH-7 Code of Conduct: The Consultant shall submit its Code of Conduct that will apply to the Experts. The Consultant shall use for this purpose the Code of Conduct form in Section 3. No substantial modifications shall be made to this form, except that the Consultant may introduce additional requirements, including as necessary to take into account specific Contract issues/risks. AND 2nd Inner Envelope with the Financial Proposal (if applicable): (1) FIN-1 (2) FIN-2 (3) FIN-3 (4) FIN-4 - (5) Statement of Undertaking (if required under Data Sheet 10.2 below) |  |
| 10.2 | Statement of Undertaking is required Yes_, or No |  |
| 11.1 | Participation of Sub-consultants, Key Experts and Non-Key Experts in more than one Proposal is permissible Yes _or No |  |
| 12.1 | Proposals shall be valid until January 23rd, 2025 |  |
| 13.1 | Clarifications may be requested no later than 15 days prior to the submission deadline. The contact information for requesting clarifications is: Procurement Officer, Central Procurement Unit, Ministry of Finance, The Carenage, St. George’s, Grenada E-mail: axel.joseph@procurement.gov.gd, cc: Carlanoel@carcip.gov.gd |  |
| 14.1.1 | Shortlisted Consultants may associate with (a) non-shortlisted consultant(s): Yes or No _ Or (b) other shortlisted Consultants: Yes _ or No |  |
| 14.1.3 for time-based contracts only | [If not used, state “Not applicable”. If used, insert the following: The Consultant’s Proposal must include the minimum Key Experts’ time-input of __6__ person-months. For the evaluation and comparison of Proposals only: if a Proposal includes less than the required minimum time-input, the missing time-input (expressed in person-month) is calculated as follows: The missing time-input is multiplied by the highest remuneration rate for a Key Expert in the Consultant’s Proposal and added to the total remuneration amount. Proposals that quoted higher than the required minimum of time-input will not be adjusted. |  |
| 15.2 | The format of the Technical Proposal to be submitted is: FTP__ or STP |  |
| 16.2 | A price adjustment provision applies to remuneration rates: Yes _ or No |
| 16.3 | Information on the Consultant’s tax obligations in the Client’s country can be found www.ird.gd |
| 16.4 | The Financial Proposal shall be stated in the following currencies: Consultant may express the price for their Services in any fully convertible currency, singly or in combination of up to three foreign currencies. The Financial Proposal should state local costs in the Client’s country currency (local currency): Yes or No_. |
| C. Submission, Opening and Evaluation |  |
| 17.1 | The Consultants shall have the option of submitting their Proposals electronically. All Technical and Financial proposals should be submitted in PDF and password protected to the following email: cpu@gov.gd. On receipt of the documents, a confirmation email would be sent acknowledging the names of the files received. All files submitted should be clearly labelled whether it is Technical or Financial proposal or supplemental information. The name of the firm should also be clearly stated. All firms should submit their passwords for technical proposals to the email address stated within 1 hour after the proposal submission deadline. The password for the financial proposals should be withheld until the technical evaluation has been completed and a date and time is set for the opening of the financials. At this point proposers are expected and will be asked (via email) to provide their password for their financial proposals. Please note a Proposer shall use different passwords for the technical and financial. A Zoom ID for the opening of the proposals will be scheduled and vendors would have the opportunity to view the opening through this medium. |
| 17.4 | The Consultant must submit: (a) Technical Proposal: one (1) original (b) Financial Proposal: one (1) original. |
| 17.7 and 17.9 | The Proposals must be submitted no later than: Date: September 30th, 2024 Time: 2:00 P.M Local Time |
| 19.1 | An online option of the opening of the Technical Proposals is offered: Yes or No__ |
| 19.2 | In addition, the following information will be read aloud at the opening of the Technical Proposals : N/A |
| 21.1 [for STP] | Criteria, sub-criteria, and point system for the evaluation of the Simplified Technical Proposals are: Points (i) Adequacy and quality of the proposed methodology, and work plan in responding to the Terms of Reference: Total points for criterion (i): [40] (ii) Key Experts’ qualifications and competence for the Assignment: {Notes to Consultant: each position number corresponds to the same for Key Experts in Form TECH-6 to be prepared by the Consultant} a) Position K-1: Information & data literacy [15] b) Position K-2: Communication & Collaboration [15] c) Position K-3: Small business operations [15] d) Position K-4: Safety [15] Total points for criterion (ii): [60] Total points for the two criteria: 100 The minimum technical score (St) required to pass is: 80 |
|  | Public Opening of Financial Proposals |
| 23.4 | An online option of the opening of the Financial Proposals is offered: Yes or No__. The online opening procedure shall be: Upon completion of the Technical Evaluation a notice of intent will be sent to the consultants for the opening of the financial proposals with the MS Teams link for the online opening. |
| 25.1 | For the purpose of the evaluation, the Client will exclude: (a) all local identifiable indirect taxes such as sales tax, excise tax, VAT, or similar taxes levied on the contract’s invoices; and (b) all additional local indirect tax on the remuneration of services rendered by non-resident experts in the Client’s country. If a Contract is awarded, at Contract negotiations, all such taxes will be discussed, finalized (using the itemized list as a guidance but not limiting to it) and added to the Contract amount as a separate line, also indicating which taxes shall be paid by the Consultant and which taxes are withheld and paid by the Client on behalf of the Consultant. |
| 26.1 | The single currency for the conversion of all prices expressed in various currencies into a single one is: Eastern Caribbean Dollar The official source of the selling (exchange) rate is: Eastern Caribbean Central Bank The date of the exchange rate is: September 23rd, 2024 |
|  | D. Negotiations and Award |
| 28.1 | Expected date and address for contract negotiations: Date: December 27th, 2024 Address: Ministry of ICT |
| 34.2 | Expected date for the commencement of the Services: Date: January 2025 at: TBD |
| 35.1 | The procedures for making a Procurement-related Complaint are detailed in the “Procurement Regulations for IPF Borrowers (Annex III).” If a Consultant wishes to make a Procurement-related Complaint, the Consultant shall submit its complaint following these procedures, In Writing (by the quickest means available, such as by email or fax), to: For the attention: Jenny Alexander-Lalgie Title/position: Chief Procurement Officer (Ag.) Client: Ministry of Finance Email address: spo@procurement.gov.gd In summary, a Procurement-related Complaint may challenge any of the following: - the terms of this Request for Proposal; - the Client’s decision to exclude a Consultant from the procurement process prior to the award of contract; and - the Client’s decision to award the contract. |

Section 3.  Technical Proposal – Standard Forms

{Notes to Consultant shown in brackets {  } throughout Section 3 provide guidance to the Consultant to prepare the Technical Proposal; they should not appear on the Proposals to be submitted.}

###### Checklist of Required Forms

| Required for FTP or STP |  | FORM | DESCRIPTION | Page Limit |
| --- | --- | --- | --- | --- |
| FTP | STP |  |  |  |
|  |  | TECH-1 | Technical Proposal Submission Form. |  |
| If applicable |  | TECH-1 Attachment | If the Proposal is submitted by a joint venture, attach a letter of intent or a copy of an existing agreement. |  |
| If applicable |  | Power of Attorney | No pre-set format/form. In the case of a Joint Venture, several are required: a power of attorney for the authorized representative of each JV member, and a power of attorney for the representative of the lead member to represent all JV members |  |
|  |  | TECH-2 | Consultant’s Organization and Experience. |  |
|  |  | TECH-2A | A. Consultant’s Organization |  |
|  |  | TECH-2B | B. Consultant’s Experience |  |
|  |  | TECH-3 | Comments or Suggestions on the Terms of Reference and on Counterpart Staff and Facilities to be provided by the Client. |  |
|  |  | TECH-3A | A. On the Terms of Reference |  |
|  |  | TECH-3B | B. On the Counterpart Staff and Facilities |  |
|  |  | TECH-4 | Description of the Approach, Methodology, and Work Plan for Performing the Assignment |  |
|  |  | TECH-5 | Work Schedule and Planning for Deliverables |  |
|  |  | TECH-6 | Team Composition, Key Experts Inputs, and attached Curriculum Vitae (CV) |  |
|  |  | TECH-7 | Code of Conduct |  |
|  |  | TECH-8 | Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Performance Declaration |  |

All pages of the original Technical and Financial Proposal shall be initialed by the same authorized representative of the Consultant who signs the Proposal.

###### Form TECH-1

Technical Proposal Submission Form

Seamoons, St. Andrew’s, Grenada W.I.

To: 	Ministry of ICT

Botanical Gardens

Ministerial Complex

Tanteen, St. George’s

Grenada

Dear Sirs:

We, the undersigned, offer to provide the consulting services for Development and delivery of Managerial Training in accordance with your Request for Proposals (RFP) dated 20th September 2024 and our Proposal.  We are hereby submitting our Proposal, which includes this Technical Proposal and a Financial Proposal sealed in a separate envelope.

If the Consultant’s Proposal includes Sub-consultants, insert the following: We are NOT submitting our Proposal with Sub-consultants.

We hereby declare that:

a) 	All the information and statements made in this Proposal are true and we accept that any misinterpretation or misrepresentation contained in this Proposal may lead to our disqualification by the Client and/or may be sanctioned by the Bank.

(b) 	Our Proposal shall be valid and remain binding upon us until 20th Feb 2025.

(c) 	We have no conflict of interest in accordance with ITC 3.

(d) 	We meet the eligibility requirements as stated in ITC 6, and we confirm our understanding of our obligation to abide by the Bank’s policy in regard to Fraud and Corruption as per ITC 5.

(e)    We, along with any of our sub-consultants, subcontractors, suppliers, or service providers for any part of the contract, are not subject to, and not controlled by any entity or individual that is subject to, a temporary suspension or a debarment imposed by the World Bank Group or a debarment imposed by the World Bank Group in accordance with the Agreement for Mutual Enforcement of Debarment Decisions between the World Bank and other development banks. Further, we are not ineligible under the Client’s country laws or official regulations or pursuant to a decision of the United Nations Security Council;

(f) 	Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH):     [select the appropriate option from (i) to (iii) below and delete the others].

We e-LearningKings

- have not been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations.]

- [are subject to disqualification by the Bank for non-compliance with SEA/ SH obligations.]

- [had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations. An arbitral award on the disqualification case has been made in our favor.]

(g)    In competing for (and, if the award is made to us, in executing) the Contract, we undertake to observe the laws against fraud and corruption, including bribery, in force in the country of the Client.

(h) 	Except as stated in the Data Sheet, ITC 12.7, we undertake to negotiate a Contract on the basis of the proposed Key Experts. We accept that the substitution of Key Experts for reasons other than those stated in ITC 12 and ITC 28.4 may lead to the termination of Contract negotiations.

(i) 	Our Proposal is binding upon us and subject to any modifications resulting from the Contract negotiations.

We undertake, if our Proposal is accepted and the Contract is signed, to initiate the Services related to the assignment no later than the date indicated in ITC 34.2 of the Data Sheet.

We understand that the Client is not bound to accept any Proposal that the Client receives.

We remain,

Sign here

Yours sincerely,

Kendell Daniel,

President

_________________________________________________________________

Signature (of Consultant’s authorized representative) {In full and initials}:

Full name:	{insert full name of authorized representative}

Title: 	{insert title/position of authorized representative}

Name of Consultant (company’s name or JV’s name):

Capacity: 	{insert the person’s capacity to sign for the Consultant}

Address:  	{insert the authorized representative’s address}

Phone/fax:	{insert the authorized representative’s phone and fax number, if applicable}

Email:  	{insert the authorized representative’s email address}

{For a joint venture, either all members shall sign or only the lead member, in which case the power of attorney to sign on behalf of all members shall be attached}

Form TECH-2 (for Full and simplified Technical Proposals)

Consultant’s Organization and Experience

Form TECH-2: a brief description of the Consultant’s organization and an outline of the recent experience of the Consultant that is most relevant to the assignment. In the case of a joint venture, information on similar assignments shall be provided for each partner. For each assignment, the outline should indicate the names of the Consultant’s Key Experts and Sub-consultants who participated, the duration of the assignment, the contract amount (total and, if it was done in a form of a joint venture or a sub-consultancy, the amount paid to the Consultant), and the Consultant’s role/involvement.

A - Consultant’s Organization

1. Provide here a brief description of the background and organization of your company of each member for this assignment.

e-Learning Kings:

- Business Documents:

- IRD Good standing certificate:

e-Learning Kings Team:

- Project Team and Key Experts

In alignment with ITB 21.1, the project team comprises the required Key Experts and supporting infrastructure staff to effectively execute the project and provide ongoing support to small businesses, both during the training and after completion through our mentorship program.

1.1 Core Project Teams Leads:

Project Management

- Zarah Chase (Team Leader): Certified Project Manager with over 10 years of experience in IT, digital transformation, social media marketing, website development, and WordPress and ASP.NET/C# web application development. He is skilled in Project Management Frameworks, Change Management Frameworks, and is a Certified Trainer and Coach. Kendell will lead the overall project execution and digital transformation initiatives.

Technology Coordinator:

- Kendell Daniel (Technology Coordinator and digital transformation e-learning management specialist): Certified Project Manager with over 10 years of experience in IT, digital transformation, social media marketing, website development, and WordPress and ASP.NET/C# web application development. He is skilled in Project Management Frameworks, Change Management Frameworks, and is a Certified Trainer and Coach. Kendell will lead the overall project execution and digital transformation initiatives.

## 1.2 Key Experts for Our for Development and Delivery of the related topical areas as outline in the TOR:

A. Position K-1: Information & Data Literacy

- Expert: Hainsley Edwards, MSc in Computer and Information Systems

- Role: Mr. Edwards leads the development and delivery of cutting-edge training modules tailored for small to medium businesses, focusing on information management, data literacy, and data-driven decision-making tools. His approach ensures participants gain comprehensive knowledge of digital transformation tools and technologies, vital for thriving in an online business environment. The curriculum begins with foundational technology theory and progresses to advanced business operations systems, emphasizing the integration of these systems to enhance data transmission efficiency. His training will instill a forward-thinking mindset, encouraging participants to plan and adapt to future changes while optimizing current operations with AI-driven analytics and insights.

B. Position K-2: Communication & Collaboration

- Expert: Zarah Chase, MSc in Communication and Media Literacy / Project Coordinator

- Role: Ms. Chase oversees the development and implementation of training focused on communication tools and collaboration platforms. Her role extends to managing project coordination and ensuring that messages are specifically crafted for varied business sectors, such as retail and services. Each training module is customized to relate directly to the participants' business types, enhancing relatability and effectiveness. Key areas include mastering platforms for internal and external communication, adopting cost-effective digital strategies, and utilizing AI to elevate communication quality and business record management.

C. Position K-3: Small Business Operations

- Expert: Joseph Gill, MSc in Computer Systems

- Role: With over 20 years as a software developer, Mr. Gill specializes in digital platforms that enhance small business operations, focusing on e-services and e-payments. His training materials are designed to encourage the adoption of sustainable and suitable digital platforms tailored for the Caribbean market. He addresses common barriers to digital commerce, such as online payment transactions, and offers localized solutions that enhance business visibility, operations, and integration with essential services like tax registration and internal records management. His expertise also extends to leveraging AI to improve business outcomes.

D. Position K-4: Safety (Platform and Digital Safety)

- Expert: Dave George, Small Business ICT Adoption Specialist

- Role: With 25 years of experience, Mr. George focuses on cybersecurity and platform safety, essential for businesses transitioning online. He brings a wealth of practical experience from both the US and Caribbean markets, providing case studies and real-world applications to safeguard mission-critical data and financial transactions. His training emphasizes the strategic use of AI systems to manage complex security tasks effectively.

Further Details: Comprehensive CVs and additional information about each expert's contributions to the project are detailed in TECH-6 (Workplans).

2.0 Back Office Support Units

The project team will be supported by two additional units:

2.1 Administrative Back-Office Staff:

  - Responsible for managing project documentation, scheduling, communication, and logistical coordination. Two staff member will be dedicated to this back end function. One for the focus on the field and mentorship support, the other for the project administrative activites inclusive of project documentation, reporting, and managing the project related data.

2.2 Mentorship Support Field Team Members:

  - Providing hands-on support and mentorship to small businesses, ensuring the successful adoption of digital tools and technologies. This team will engage in field visits and offer personalized guidance to small business owner or managers to drive the changes that are placed within the context of digital training and ultimate digital adoption.  The team will be focused on services delivery using the methods and principles of the ADKAR framework ensuring that the small business owner/managers are well supported in an environment of change that can be new and sometime a bit frustrating.

The full details regarding the roles of the support units are included in the proposal.

e-Learning Kings: Digital Transformation Framework for Micro, Small, and Medium Enterprises (MSMEs)

Overview

e-Learning Kings has designed and successfully implemented a comprehensive digital transformation framework tailored for micro, small, and medium enterprises (MSMEs) with 10 to 15 employees. Over the past four years, this framework has been deployed across Grenada, contributing significantly to the digital evolution of several sectors.

Our framework, ATIAF (Assess, Test, Implement, Assessment & Measurement, and Focused Training), is specifically created for small island states, where financial resources, intelligence, and human capacity in small businesses face tremendous challenges. Often, these businesses are managed by a single owner or a small team who struggle to break out of a cycle of repeated, non-transformative practices. This situation can be overwhelming, stifling innovation and growth.

At e-Learning Kings, we believe in the power of visionary thinking and an envisioning process. We guide businesses to focus on future possibilities, constantly pushing for progressive elaboration and development. By offering a clear, actionable path forward, we help business owners escape these cycles and achieve transformative change.

The ATIAF Methodology

Our ATIAF methodology is designed to address the specific challenges of small businesses in resource-constrained environments:

- Assess: We begin with a comprehensive evaluation of the business’s current processes, identifying bottlenecks and areas for potential digital transformation.

- Test: After assessment, we conduct testing to validate the viability of new solutions within the business environment. This ensures that the proposed changes are suitable and will lead to effective outcomes.

- Implement: Based on the results of the tests, we implement the most appropriate digital solutions, ensuring minimal disruption to the business operations.

- Assessment & Measurement: Post-implementation, we conduct ongoing assessments to measure the effectiveness of the digital solutions and ensure they align with the business goals.

- Focused Training: Finally, we offer focused training to the business owner and staff, equipping them with the skills and knowledge to fully adopt and maintain the new systems. This step is crucial to long-term success, as it ensures that the transformation is sustainable and can evolve with the business.

Framework Implementation Across Sectors

Our digital transformation framework has been applied across various industries, including:

- Public Sector Agencies and State-Owned Enterprises: Supporting small-scale projects aimed at boosting digital engagement.

- Micro-Businesses (1-2 Family Members): Offering transformative tools to improve the operations of registered and unregistered businesses.

- Agro-processing and Farming Businesses: Assisting in the adoption of modern technologies to enhance productivity and market reach.

- IT Consulting and Service-Based Businesses: Helping with the integration of digital services to streamline business functions.

- Medical, Legal, and Real Estate Agencies: Enabling the use of digital solutions to enhance client service and operational efficiency.

Our Approach

We employ a three-step pathway to guide businesses through their digital transformation:

- Assessment: We conduct a comprehensive evaluation of each business to identify its unique needs and potential for digital integration.

- Digital Transformation Action Plan: We create a detailed, customized action plan for management, outlining clear steps for digital adoption.

- Training: We offer focused training to business owners and staff, empowering them to implement and adopt their new digital solutions effectively.

Proven Results

Our experience has shown that many businesses struggle to break free from outdated processes. By introducing digital tools and frameworks, we help these businesses overcome mental and operational roadblocks, embracing a more effective and streamlined future.

# Key Projects in recent times that we have supported directly that aligns with the requirement of the proposed

- Simple Pure Agro-Processing: Digital Transformation Project

Client: Simple Pure Agro-Processing

Contact: info@simplepureagroprocessing.com

Design Phase Outputs:

We collaborated with Simple Pure Agro-Processing (SPA) to enhance their logistics and operational efficiency through a comprehensive digital assessment. This process helped identify key areas for improvement and resulted in the development of a Digital Implementation Plan and Roadmap specifically tailored to their soursop production operations.

- Key Output: A Digital Transformation Plan comprising several mini-projects aligned with SPA's strategic goals and objectives, ensuring a structured path toward achieving sustainable growth and operational optimization.

Implementation Phase:

- Website Development with Enhanced Cybersecurity: We supported the creation and launch of SPA's public-facing website, which serves as an informational hub for association members and the public. The website provides details about the soursop industry, best farming practices, and the latest industry news. A key area of focus was cybersecurity, particularly for mobile and web-based application platforms. Given the rise in phishing attacks and website impersonation—where malicious actors create fake websites to deceive users and steal information—we implemented advanced security measures, including:

  - Two-factor authentication (2FA) for user accounts.

  - SSL encryption to secure data transmission.

  - Education on recognizing website impersonation and phishing emails, helping SPA staff and users identify fake links, domains, and deceptive tactics often used by cybercriminals to breach small businesses.

- AI Integration for Data Management and Decision-Making: Leveraging our web platform and data management tools, we integrated Artificial Intelligence (AI) to enhance SPA's decision-making processes. AI tools help analyze farming data, monitor production, and predict outcomes. By employing predictive analytics, SPA can better forecast crop yields, optimize farming practices, and improve operational efficiency.

- Exploration of Local Online Payment Options: As part of the digital transformation strategy, we explored local online payment methods, including the 4Cs payment system and other regional platforms, to identify viable solutions for small businesses in Grenada. These payment systems offer opportunities for businesses to easily accept payments for goods and services, expanding their digital reach and improving their e-commerce capabilities. While implementation is not within the current project scope, these options provide a foundation for future digital payment integration, ensuring businesses can meet the needs of local and international customers.

- Digitization of Land Plots Using Drone and GIS Technologies: To address the impact of climate change on their crops, we assisted in the digitization of land plots using drone technologies and GIS mapping. This initiative, enhanced with AI-powered insights, allowed SPA to visualize and monitor farming practices, detecting potential risks to crop health early on.

- Data Management – Data Analytics, using advance AI technologies to help delivery GIS output that are normally impossible without the use of trained experts in the GIS field. SPA staff members were trained to use GIS imagery to capture the coordinates of their plans and plan their irrigation system for drought management.

- Plant Research: Adoption of AI to support the research work related to the main crop (sour sop) the adoption of technologies such as GPT4.0 research base subsystem to find associative cause of issue related to the fungal crop issues such a fruit rot (anthracnose)

- Training and Cybersecurity Awareness: Throughout the project, SPA management and staff were trained in managing their digital systems effectively. We conducted several face-to-face and online training sessions, focusing not only on digital tools but also on cybersecurity best practices. Specific areas of awareness included:

  - Website Impersonation: Teaching participants how to recognize fake websites designed to mimic legitimate platforms and steal sensitive information.

  - Phishing Attacks: Providing insights on how to identify suspicious emails, links, and communications that aim to trick users into revealing passwords or personal data.

  - Password Management: Educating users on creating strong passwords, utilizing password managers, and avoiding common mistakes like reusing passwords across multiple accounts.

  - Data Backup and Recovery: Instructing participants on the importance of regular data backups and how to recover data in the event of a cyber incident.

  - Secure Payment Systems: Ensuring that businesses understand how to use secure e-payment platforms that protect customer information and business financial data.

These training sessions provided SPA with the tools needed to operate securely in the digital world, helping them minimize risks as they implement their digital transformation strategies.

- Art10Tic Print (Grenada District)

Client: Art10Tic Print (Grenada District)

Contact: info@grenadadistrict.com

Design Phase Outputs:

We collaborated with Simple Pure Agro-Processing (SPA) to enhance their logistics and operational efficiency through a comprehensive digital assessment. This process helped identify key areas for improvement and resulted in the development of a Digital Implementation Plan and Roadmap specifically tailored to their soursop production operations.

- Key Output: A Digital Transformation Plan comprising several mini-projects aligned with SPA's strategic goals and objectives, ensuring a structured path toward achieving sustainable growth and operational optimization.

Implementation Phase:

- Website Development with Enhanced Cybersecurity: We supported the creation and launch of SPA's public-facing website, which serves as an informational hub for association members and the public. The website provides details about the soursop industry, best farming practices, and the latest industry news. A key area of focus was cybersecurity, particularly for mobile and web-based application platforms. Given the rise in phishing attacks and website impersonation—where malicious actors create fake websites to deceive users and steal information—we implemented advanced security measures, including:

  - Two-factor authentication (2FA) for user accounts.

  - SSL encryption to secure data transmission.

  - Education on recognizing website impersonation and phishing emails, helping SPA staff and users identify fake links, domains, and deceptive tactics often used by cybercriminals to breach small businesses.

- AI Integration for Data Management and Decision-Making: Leveraging our web platform and data management tools, we integrated Artificial Intelligence (AI) to enhance SPA's decision-making processes. AI tools help analyze farming data, monitor production, and predict outcomes. By employing predictive analytics, SPA can better forecast crop yields, optimize farming practices, and improve operational efficiency.

- Exploration of Local Online Payment Options: As part of the digital transformation strategy, we explored local online payment methods, including the 4Cs payment system and other regional platforms, to identify viable solutions for small businesses in Grenada. These payment systems offer opportunities for businesses to easily accept payments for goods and services, expanding their digital reach and improving their e-commerce capabilities. While implementation is not within the current project scope, these options provide a foundation for future digital payment integration, ensuring businesses can meet the needs of local and international customers.

- Digitization of Land Plots Using Drone and GIS Technologies: To address the impact of climate change on their crops, we assisted in the digitization of land plots using drone technologies and GIS mapping. This initiative, enhanced with AI-powered insights, allowed SPA to visualize and monitor farming practices, detecting potential risks to crop health early on.

- Data Management – Data Analytics, using advance AI technologies to help delivery GIS output that are normally impossible without the use of trained experts in the GIS field. SPA staff members were trained to use GIS imagery to capture the coordinates of their plans and plan their irrigation system for drought management.

- Plant Research: Adoption of AI to support the research work related to the main crop (sour sop) the adoption of technologies such as GPT4.0 research base subsystem to find associative cause of issue related to the fungal crop issues such a fruit rot (anthracnose)

- Training and Cybersecurity Awareness: Throughout the project, SPA management and staff were trained in managing their digital systems effectively. We conducted several face-to-face and online training sessions, focusing not only on digital tools but also on cybersecurity best practices. Specific areas of awareness included:

  - Website Impersonation: Teaching participants how to recognize fake websites designed to mimic legitimate platforms and steal sensitive information.

  - Phishing Attacks: Providing insights on how to identify suspicious emails, links, and communications that aim to trick users into revealing passwords or personal data.

  - Password Management: Educating users on creating strong passwords, utilizing password managers, and avoiding common mistakes like reusing passwords across multiple accounts.

  - Data Backup and Recovery: Instructing participants on the importance of regular data backups and how to recover data in the event of a cyber incident.

  - Secure Payment Systems: Ensuring that businesses understand how to use secure e-payment platforms that protect customer information and business financial data.

These training sessions provided SPA with the tools needed to operate securely in the digital world, helping them minimize risks as they implement their digital transformation strategies.

- Art10Tic Print: Our work with this small family-owned design studio focused on integrating AI technologies to enhance design processes. This led to the creation of more modern and attractive designs for the tourism market, opening new business opportunities.

Contact: info@simplepureagroprocessing.com

- SpiceMobile: We supported this medium-sized business in improving their online visibility and developing a digital payment acceptance system, expanding their customer base.

Contact: info@simplepureagroprocessing.com

- Land Surveyor (Belfone): By adopting AI and drone-based surveying technologies, we helped this surveying firm modernize their practices. Utilizing RTK (Real-Time Kinematic) technology for mapping and grid-point precision, they are now better equipped for future projects.

Contact: info@simplepureagroprocessing.com

- Egg Farming: In collaboration with local egg farmers, we developed a digital product cycle and investment profile, helping them realize the potential benefits of egg production for human food security. Our solution provided insights into egg production's high amino acid content and nutritional benefits, empowering farmers with a clearer vision for expanding their operations.

Contact: info@simplepureagroprocessing.com

- Alignment with Local and National Goals

Our framework aligns with the Grenadian government's objectives of fostering digital transformation among 125 small businesses. We firmly believe that our methodology is ideally suited to the current landscape and will drive significant growth in productivity and business opportunities across the nation.

Our ultimate goal is to cultivate a growth mindset within businesses, fostering an openness to new technologies and processes, thereby creating lasting opportunities for innovation and success.

2. Include organizational chart, a list of Board of Directors, and beneficial ownership. The successful Consultant shall also provide additional information on beneficial ownership, using the Beneficial Ownership Disclosure Form.

B - Consultant’s Experience

1. 	List only previous similar assignments successfully completed in the last 5 years.

e-Learning King must list all experience of what we have done, whether free or paid to support digital transformation of small business, churches etc.

2. 	List only those assignments for which the Consultant was legally contracted by the Client as a company or was one of the joint venture members. Assignments completed by the Consultant’s individual experts working privately or through other consulting firms cannot be claimed as the relevant experience of the Consultant, or that of the Consultant’s partners or sub-consultants, but can be claimed by the Experts themselves in their CVs. The Consultant should be prepared to substantiate the claimed experience by presenting copies of relevant documents and references if so requested by the Client. We need to get SPA website and operational guideline and a digital transformation strategic action plan done and handed over to Marlon St. Louis, we also need to do this for Dave Geroge in Aislecom to assist with the experience and qualification, both must have focus on the aspects of training of the top leaders to created the environment for digital adoption.

| Duration | Assignment name/& brief description of main deliverables/outputs | Name of Client & Country of Assignment | Approx. Contract value (in US$ equivalent)/ Amount paid to your firm | Role on the Assignment |
| --- | --- | --- | --- | --- |
| {e.g., Jan.2009– Apr.2010} | {e.g., “Improvement quality of...............”: designed master plan for rationalization of ........; } | {e.g., Ministry of ......, country} | {e.g., US$1 mill/US$0.5 mill} | {e.g., Lead partner in a JV A&B&C} |
| {e.g., Jan-May 2008} | {e.g., “Support to sub-national government.....” : drafted secondary level regulations on..............} | {e.g., municipality of........., country} | {e.g., US$0.2 mil/US$0.2 mil} | {e.g., sole Consultant} |

Form TECH-4 (for Simplified Technical Proposal Only)

Description of Approach, Methodology, and Work Plan for Performing the Assignment

Form TECH-4: a description of the approach, methodology, and work plan for performing the assignment, including a detailed description of the proposed methodology and staffing for training, if the Terms of Reference specify training as a specific component of the assignment.

Overview of the technical approch to the project:

Approach to the Project:

In response to RFP No: GD-PCU - GRENADA-381458-CS-QCBS: “Development and Delivery of Managerial Training” for a targeted one hundred and twenty-five (125) or more micro, small, and medium enterprises (MSMEs) in Grenada, e-Learning Kings is pleased to submit this proposal. The aim is to support these businesses in adopting digital technology to enhance their operations, a process known as digital transformation.

e-Learning Kings, a leader in Digital Transformation Business, specializes in organizational change management through the strategic adoption of aligned digital technologies. Our approach places a strong emphasis on human capital development, leveraging self-paced, interactive learning to ensure sustainable and impactful transformation.

For this project, e-Learning Kings proposes a comprehensive solution for the businesses of Grenada, under the leadership of the Ministry of ICT and the CARDTP Project, which includes the development and delivery of five to six core courses aimed at supporting the digital transformation of small businesses. These courses will be delivered and supported through a combination of:

- E-learning platform: Offering flexible, self-paced learning.

- Face-to-face training sessions: Providing hands-on, instructor-led guidance.

- Direct in-office support: Offering practical, personalized assistance to help businesses apply the learned concepts directly within their operations, via mentorship pathway.

Our approach follows the ADKAR methodology, a well-established framework for change management that focuses on Awareness, Desire, Knowledge, Ability, and Reinforcement. By utilizing this methodology, we aim to ensure that business owners and managers are not only introduced to the digital tools necessary for transformation but are also empowered to successfully adopt and integrate these changes into their daily operations.

Given that the project, as outlined in the referenced TOR, is scheduled to start in April 2024 and is intended to be executed over a two-year period, we propose an adaptive approach to ensure that the project's goals are met effectively despite potential delays. Recognizing the importance of this initiative, we will implement strategies to accelerate key activities and optimize resource allocation, allowing us to achieve the intended outcomes within 12 to 18 months. This approach ensures that the project remains on track and delivers meaningful results in a shorter timeframe without compromising quality.

Approach to the Execution phase of the project (doing the work):

The e-Learning Kings Team proposes the most fitting solution in alignment with the designed TOR, wherein 125 small business members will be grouped into cohorts of 25 members per group. This structure will result in the formation of five cohorts, each comprising at least one representative from micro, small, or medium-sized businesses. The number of representatives from any small business will not be limited to one individual, rather we will encourage participation from all employees where applicable.

Our team will operate the project through a framework of three parallel swimlanes, each focused on distinct aspects of the project to ensure effective implementation and delivery.

Swimlane 1: Core Administrative and Project Management Tasks

This swimlane will focus on the core administrative and project management responsibilities typical of a publicly funded project. Our Project Implementation Team will include a e-learning Kings Project Coordinator supported by back-office administrative staff. Their tasks will include:

- Managing all aspects of the project’s outputs and deliverables.

- Ensuring effective communication within the project, including scheduling and coordination of training sessions.

- Handling document management and ensuring compliance with data protection laws and other relevant legislation.

- Scheduling and following up with the in-house action learning activities for the mentorship (field teams members)

This team will ensure smooth execution of all administrative functions, managing both the internal workings of the project and communication with external stakeholders.

Swimlane 2: Technical and Technological Delivery

This swimlane will focus on the development and delivery of course content, ensuring that participants receive comprehensive training both in-person and virtually. The key experts will form this team, ensuring that:

- Course content is delivered consistently, with a common thread tying together the presentations of various experts in to a coherent window of e-learning materials that is contextualize and localized to the Grenadian market.

- All participants follow the same use case, which will be addressed from multiple perspectives, providing a 360-degree view of how digital technology can solve different challenges.

- Deliver on demand support solution via the mentorship (field Officers) who will create learning and supporting materials that is very specific or unique to a particular small business issue, software, etc. While unique, the course will be delivered via the established modalities and platform to ensure effective communication.

Cohort-Based Learning Approach for Small Business Digital Transformation

The e-Learning Kings approach emphasizes a structured and supportive learning environment to ensure that small businesses not only adopt but successfully integrate digital tools into their operations. Each expert will present their particular topic from a unified use case, allowing participants to understand how technology integrates different parts of their business into a cohesive and functional solution.

By 2027, our goal is for 125 small businesses to have implemented cloud-based software and digital solutions. However, we anticipate that challenges may arise as many managers may experience frustration with IT-related issues. These could include difficulties in using the software solutions, performing necessary IT tasks, or troubleshooting complications. Recognizing these challenges, e-Learning Kings has developed an adaptive handholding support system using the ADKAR change management model, ensuring that businesses receive the guidance they need to overcome obstacles.

Why Change Fails and How We Address It

“Organizational change often fails because, while employees know a change is happening, they don’t understand why it’s occurring. This can be due to a lack of trust, poor change management strategies, or the absence of proper training and support.”

We at e-Learning Kings believe that for successful change, it’s not enough to transfer knowledge. Ability must be demonstrated, and support must be provided to ensure that participants can apply what they learn. This is where our approach excels, offering reinforcement and continuous support to make the change permanent.

Cohort Structure and Design

To achieve this, we propose that the 125 small businesses be grouped into five cohorts, each cohort comprising 25 business units. Each cohort is designed to be flexible, allowing for a varying number of participants from each business, as one business may register 1 to 3 members.

Cohort Design:

- Five Cohorts: Each cohort will contain 25 business units (businesses), with no limitations on the number of participants from each business.

- Participant Structure: Each business can have between 1 to 3 representatives participating in the program.

- Learning Flexibility: Participants will have access to on-demand training through our e-Learning platform, allowing them to progress at their own pace.

- Support and Mentorship: Each cohort will receive continuous support, including IT assistance and mentorship, to address any challenges they face during the implementation of digital solutions.

Schematic of the Cohort Approach

Below is a visual representation of how the cohorts will be structured and the key components of the learning experience:

Each cohort will consist of a maximum of 25 business units, and each business can have multiple participants. This approach allows for flexible learning experiences and real-time support for the adoption of digital transformation.

Learning Delivery and Support

- Flexible Learning: Participants can access the e-Learning platform on demand, ensuring that they can progress at their own pace. This accommodates varying levels of availability and digital literacy among businesses.

- Expert-Led Courses: Each course will be led by subject matter experts, covering various aspects of digital transformation, including cloud-based solutions, data analytics, cybersecurity, and AI integration.

- Unified Use Case: All experts will present their content based on a shared use case, allowing participants to see how different technologies come together to form a cohesive solution for their business.

- On-Site Mentorship and IT Support: e-Learning Kings will provide in-office support to ensure that businesses are not left struggling with IT issues or frustrations related to the implementation of their digital tools. This hands-on assistance is key to maintaining momentum and ensuring that participants can successfully adopt the solutions they have learned.

The ADKAR Model for Sustainable Change

The ADKAR model (Awareness, Desire, Knowledge, Ability, Reinforcement) will guide our change management strategy, ensuring that each participant not only learns but applies the knowledge and skills they acquire.

- Awareness: Ensuring participants understand why digital transformation is essential for their business.

- Desire: Creating a desire among participants to engage with and adopt new technologies.

- Knowledge: Providing the necessary training and resources to equip participants with the skills to implement change.

- Ability: Demonstrating their ability to apply these skills in real-world scenarios.

- Reinforcement: Providing continuous mentorship and support to ensure that the changes stick and are sustained over time.

By structuring the businesses into cohorts and providing continuous, on-demand learning and mentorship, e-Learning Kings will ensure that these 125 businesses in Grenada can successfully adopt and implement digital technologies by 2027, overcoming the typical challenges associated with change and technology integration.

Swimlane 3: Delivery and Mentorship

The third swimlane focuses on the mentorship and support of small businesses. This will include:

- On-site visits to provide hands-on guidance, ensuring that skills taught during training are effectively applied in practice.

- A live help desk, operational throughout the two-year project duration, offering participants ongoing support not only for course-related queries but also for IT technical assistance as they implement the concepts and strategies introduced during training.

This swimlane is designed to offer continuous mentorship and motivation, helping businesses overcome challenges as they adopt and integrate new digital technologies into their operations.

By utilizing these three parallel swimlanes, the e-Learning Kings Team ensures a well-rounded and cohesive approach to project execution. This structure promotes not only the theoretical learning of digital technologies but also the practical, real-world application of these concepts within each business.

a) 	Technical Approach, Methodology, and Organization of the Consultant’s team.

Understanding of the Objectives

The Caribbean Digital Transformation Project (CARDTP) aims to drive digital adoption among non-ICT small and medium enterprises (SMEs) in Grenada by empowering 125 business owners/managers with the necessary digital skills and tools. The project, in collaboration with the World Bank Group, focuses on creating a sustainable, digitally driven economy by providing managerial training that enhances productivity, digital literacy, operational efficiency, and the use of digital technologies for transformation. The training will focus on equipping businesses to utilize modern digital tools and strategies to enhance their operations, marketing, and overall competitiveness.

Key topics will include:

- Data Analytics: Leveraging data for business insights and decision-making.

- Cloud Computing: Migrating operations to scalable, secure cloud platforms.

- Cybersecurity: Protecting digital assets and sensitive data.

- Artificial Intelligence (AI): Implementing AI tools for automation and customer engagement.

- E-Commerce and Digital Marketing: Expanding market reach through digital channels.

- Social media and Online Presence: Strengthening brand visibility and engagement with customers.

Our goal is to equip participants with practical digital tools that align with their specific business goals and objectives, fostering economic growth, innovation, and job creation.

Technical Approach

Our approach is designed to provide targeted, impactful training that addresses the specific needs of business owners and managers in Grenada. The technical framework consists of the following core components:

- Needs Assessment:

  - Conduct a comprehensive needs analysis to identify the specific challenges, digital gaps, and opportunities faced by managers in various sectors. This will ensure that the training is relevant and aligned with their operational needs. (e-Learning Kings has developed and implemented the ATIAF framework – see attached in annex 1)

  - Gather data on the current skill levels of participants through surveys, interviews, and focus groups. This will help tailor the content to varying levels of digital literacy. (e-Learning Kings has attached our general assessment questionnaire, which complements physical processes to assessment of the client/small business environment from three perspective – People, Organizational Structures and Technologies)

- Content Customization:

  - Customized Content Development: Based on the needs assessment, the training content will be customized to address the key areas where digital adoption can have the most significant impact. We will focus on core areas such as digital platforms, process automation, and cybersecurity, ensuring that all business types—whether in retail, hospitality, services, agriculture or manufacturing—are catered to. (Our content delivery platform allows e-learning Kings to create and deliver content based on an adaptive modality. Thus, end user and business owner will be provided with content based on their needs, allow them to address their specific business goals and requirements)

  - Real-World Application: Content will include practical exercises, case studies, and real-world scenarios. This ensures that business owners/managers not only understand the theory behind digital tools but can also apply them in their daily operations. (Given our implementation of our practice and framework for existing small businesses in Grenada, our example and cases studies with lessons learnt, can be well adopted by several small business, seeking to have digital transformation projects)

- Cohort and Individualized Training:

  - Cohort Training: Managers and owners with common needs will participate in group training sessions focused on core topics such as cloud computing, data management, and social media engagement. This will encourage peer learning and discussion of shared challenges. The TOR outlines execution of 3 to 4 cohorts of training. This can be executed to allow for groups of 25 small business owners/manager to participate notable using both (in person and online methods). It is critical to have some level of face-to-face interaction as the uptake of online training can be challenging in the operational environment for many small businesses. Events can be organed to ensure that these business owners can be taught in real time with mentors and hand holding support to overcome the feat and challenges of using IT and digital platforms.

  - Individualized Sessions: Businesses with unique needs will receive tailored, one-on-one sessions to address specific challenges or opportunities. For example, if a retail business needs help setting up an e-commerce platform, the training will be designed accordingly. (e-Learning kings ATAIF framework seek to ensure that finding and detail from the first Stage is used an input and feedback to guide the development of digital strategies for the small business owners. This will also be critical to ensure that the need of the business is understood and that as complementary to the broad cohort-based training, additional support for unique specific try of training or software adoption be developed and detail to support these small businesses.)

- Hybrid Training Delivery:

  - The training will be delivered through a hybrid approach, combining in-person and virtual sessions. This flexible delivery ensures wider participation, especially given the geographic dispersion and varying schedules of the participants.

  - 50% of the training will occur on-site at the businesses' workplaces. This allows for personalized training in the actual work environment, ensuring practical applicability and hands-on learning.

- Cybersecurity and SEA/SH Risk Management:

  - Cybersecurity: We will integrate cybersecurity training into the program, focusing on safeguarding business data and managing digital identities. Businesses will be trained on essential cybersecurity practices, including how to protect their digital infrastructure from cyber threats and data breaches.

  - Sexual Exploitation and Abuse (SEA) and Sexual Harassment (SH): We recognize the importance of addressing SEA/SH risks. Our training will include policies and strategies for mitigating SEA/SH risks, with clear reporting mechanisms and guidelines to ensure a safe and respectful learning environment. We will also collaborate with businesses to ensure that workplace policies support these standards. The World Bank Social Safeguard should provide support to this project to ensure that all employees are well aware of these matters.

- Mentorship and Continuous Support:

  - Our team will provide ongoing support throughout the program. Participants will have access to mentors who will guide them through the adoption of digital tools. Regular check-ins and evaluations will ensure that the participants remain on track. The mentorship component will be used to support direct delivery and training to the business – in their own operational environment, allow for our input to determine where IT and other challenges can be adequality address to lead to a successful outcome.

- Monitoring and Evaluation (M&E):

  - We will set up an M&E framework to track progress, participant engagement, and skill acquisition. Feedback will be gathered at each stage to ensure continuous improvement.

  - Regular progress reports will be provided to the CARDTP Unit to ensure transparency and accountability.

Methodology

  - Project Inception and Planning:

    - Within the first week the Detail Work Plan will be delivered to the Project Implementation Unit (PIU)

    - Within the first month, we will submit the Inception Report, which will include the finalized methodology, project charter, scope of work, and timeline. We will engage with the CARDTP Unit to confirm deliverables and adjust plans as needed.

  - Training Delivery Methodology:

    - Blended Learning Approach: The training will use a mix of e-learning modules, virtual classroom sessions, and face-to-face workshops. By incorporating digital learning platforms, we ensure that participants can access the content at their own pace while also benefiting from interactive sessions.

    - Interactive Tools: Training modules will incorporate interactive tools such as simulations, quizzes, and group projects to enhance learning. Each session will include hands-on exercises to ensure participants can apply what they’ve learned.

  - Monitoring Progress:

    - Participants will be assessed through regular evaluations to track progress and skill development.

    - Quarterly progress reports will provide updates on the number of participants trained and the impact of the training on their businesses.

  - Reporting and Recommendations:

    - At the end of the two-year period, we will submit a final report, detailing the outcomes of the training program, lessons learned, and recommendations for future improvements. The report will include a thorough analysis of how participants have implemented digital tools in their businesses and the resultant business outcomes.

  - Organization of the Consultant’s Team

    - To deliver the objectives outlined, our team will be structured as follows:

  - Project Manager Team (Back Office Support):

    - Responsible for overseeing the project’s execution, ensuring deliverables are met on time, and acting as the primary point of contact with the CARDTP Unit. The Project Manager will ensure alignment between the client’s expectations and the project outcomes.

  - Lead Digital Skills Trainers:

    - This expert will develop and lead the training sessions on topics such as general platforms and software for small businesses, data analytics, cloud computing, cybersecurity, and AI tools. They will ensure that the training materials are relevant and that participants are able to apply these skills in their businesses.

(Key Experts in keeping with ITB 21.1 is included)

a) Position K-1: Information & data literacy [15]

b) Position K-2: Communication & Collaboration [15]

c) Position K-3: Small Business Operations [15]

d)  Position K-4: Safety [15]

  - Subject Matter Experts (SMEs):

    - A team of subject matter experts specializing in areas such as data management, digital marketing, cybersecurity, and AI. These experts will deliver both group and one-on-one training based on the unique needs of each business.

  - Mentors:

    - Assigned to provide personalized support to business owners and managers, guiding them through the practical application of the training content. There will be a back-office team that will be dedicated to the support of the 4 cohorts – providing online help desk support, online virtual support and in person/in office support to their assigned small business.

  - Monitoring and Evaluation Officer:

    - Responsible for tracking progress, gathering feedback, and providing data to measure the impact of the training.

  - Cybersecurity Specialist:

    - This expert will ensure that participants are adequately trained on protecting their digital assets and managing cybersecurity risks.

  - Administrative and Logistical Support:

    - Back-office staff will support scheduling, communication, and coordination with participants, ensuring smooth execution of the training sessions.

Conclusion

This approach will ensure that the project meets the objectives of the Caribbean Digital Transformation Project by equipping 125 SMEs with the digital skills necessary for success in a modern economy. The hybrid training model, combined with our tailored methodology and strong emphasis on practical application, cybersecurity, and SEA/SH risk management, ensures a comprehensive and sustainable impact on Grenada's business landscape.

b) 	Work Plan and Staffing. {Please outline the plan for the implementation of the main activities/tasks of the assignment, their content and duration, phasing and interrelations, milestones (including interim approvals by the Client), and tentative delivery dates of the reports. The proposed work plan should be consistent with the technical approach and methodology, showing understanding of the TOR and ability to translate them into a feasible working plan and work schedule showing the assigned tasks for each expert. A list of the final documents (including reports) to be delivered as final output(s) should be included here. The work plan should be consistent with the Work Schedule Form.}

Work Plan and Staffing

The implementation of the Caribbean Digital Transformation Project (CARDTP) for training 125 small and medium enterprises (SMEs) in Grenada will be executed in a phased approach, ensuring structured delivery of activities, consistent monitoring, and achievement of project milestones. The plan adheres to the Terms of Reference (TOR) and is designed to meet the project objectives, ensuring that participants are equipped with the necessary digital skills and tools aligned to their business needs.

Phasing and Interrelations of Activities

The detail workplan is attached, and shall be discussed with Kickoff meeting for refinement and sign off within the first week of the project.

The work plan is divided into three core phases:

- Phase 1: Project Inception and Preparation

  - Duration: 1 month of active engagement over 2 calendar months

  - Objective: Establish a strong foundation for the project, ensuring alignment with the client’s expectations, confirming the methodology, and setting up the project infrastructure.

  - Activities:

    - Submission of Inception Report detailing the final methodology and approach, project charter, scope of work for each business, agreement on deliverables, and project milestones.

    - Establishment of the Monitoring and Evaluation (M&E) framework.

    - Client engagement meetings to confirm understanding of scope and deliverables.

  - Deliverable: Inception Report (finalized), setting the groundwork for the project.

  - Milestone: Client approval of the Inception Report.

- Phase 2: Content Development and Training Preparation (Delivery Phase)

  - Duration: 2-6 months

  - Objective: Develop tailored training materials and digital transformation plans for each of the 125 businesses based on individual needs assessments.

  - Activities:

    - Conduct detailed needs assessments for all businesses to identify their specific challenges, opportunities, and digital readiness.

    - Development of Small Business Digital Transformation Plans, customized for each business, outlining digital tools, strategies, and timelines.

    - Design of training materials addressing common elements for cohort-based sessions and tailored content for individualized training.

  - Deliverables:

    - First batch of  50 Small Business Digital Transformation Plans (Month 3).

    - Second batch of 50 Small Business Digital Transformation Plans (Month 5).

    - Final batch of 25 Small Business Digital Transformation Plans (Month 6).

  - Milestones:

    - Client approval of the first batch of transformation plans.

    - Client approval of the second batch of transformation plans.

    - Client approval of the final batch of transformation plans.

- Phase 3: Training Delivery and Monitoring

  - Duration: 7-12 months

  - Objective: Deliver training to businesses through both cohort-based group sessions and individualized in-office training sessions, followed by continuous monitoring and feedback collection.

  - Activities:

    - Conduct cohort-based training sessions (for common digital needs) in small groups.

    - Deliver customized individual training sessions for each business (50% on-site, 50% online or at external venues).

    - Monitor training progress through the established M&E framework and collect feedback from participants.

  - Deliverables:

    - Training Report after the first batch of 50 businesses (Month 9).

    - Training Report after the second batch of 50 businesses (Month 10).

    - Training Report after the final batch of 25 businesses (Month 11).

  - Milestones:

    - Client sign-off on completion of training for each cohort.

    - Continuous feedback and adjustments based on participant evaluations.

- Phase 4: Evaluation, Final Reporting, and Closeout

  - Duration: 12-18 months

  - Objective: Conduct final evaluations of the training program, assess its impact on business operations, and submit the final report and recommendations.

  - Activities:

    - Conduct post-training evaluations through surveys and business performance assessments.

    - Prepare and submit the Final Project Report, including lessons learned and recommendations for future digital transformation efforts.

    - Submission of Final Business Outcomes Report, assessing the impact of digital tools on business performance.

  - Deliverables:

    - Final Project Report (Month 12).

    - Final Business Outcomes Report (Month 12).

  - Milestone:

    - Final sign-off from the client on project completion.

### Tentative Delivery Schedule for Reports (24 Months)

| Deliverable | Description | Duration (Months) | Delivery Date | Client Approval |
| --- | --- | --- | --- | --- |
| Inception Report | Final methodology, project charter, scope, M&E setup | Month 1-2 | End of Month 2 | Required |
| Small Business Digital Transformation Plans for Training Batch 1 | First batch of 50 plans | Month 3-6 | End of Month 6 | Required |
| Small Business Digital Transformation Plans for Training Batch II | Second batch of 50 plans | Month 7-10 | End of Month 10 | Required |
| Small Business Digital Transformation Plans for Training Batch III | Final batch of 25 plans | Month 11-12 | End of Month 12 | Required |
| Training Report (First Batch) | Completion of training for the first batch of 50 businesses | Month 13-16 | End of Month 16 | Required |
| Training Report (Second Batch) | Completion of training for the second batch of 50 businesses | Month 17-20 | End of Month 20 | Required |
| Training Report (Final Batch) | Completion of training for the final 25 businesses | Month 21-22 | End of Month 22 | Required |
| Final Project Report | Comprehensive final report covering all phases of the project | Month 23 | End of Month 23 | Required |
| Final Business Outcomes Report | Assessment of business impact from digital transformation | Month 23-24 | End of Month 24 | Required |

Details of Each Phase:

Inception Phase (Months 1-2):

- Submission of the Inception Report will occur by the end of Month 2, following client engagement and project setup and finalization of data collection from the full small businesses. This report will include the final methodology, project charter, scope of work, and M&E framework.

Content Development and Training Preparation (Months 3-12):

- Small Business Digital Transformation Plans will be developed in three batches:

  - First Batch (50 plans) by Month 6.

  - Second Batch (50 plans) by Month 10.

  - Final Batch (25 plans) by Month 12.

Training Delivery Phase with mentorship support (Months 4- 22):

- The training for businesses will be conducted in three phases:

  - First Batch of 50 businesses: Training will be completed between Months 13 and 16.

  - Second Batch of 50 businesses: Training will be completed between Months 17 and 20.

  - Final Batch of 25 businesses: Training will be completed by the end of Month 22.

Final Evaluation and Reporting (Months 23-24):

- The Final Project Report will be delivered in Month 23, summarizing the outcomes of the training, lessons learned, and overall impact.

- The Final Business Outcomes Report will be delivered by Month 24, providing detailed analysis on the digital transformation impact on business performance.

Staffing and Task Allocation

The consultant’s team is organized to ensure efficiency and specialization in delivering the project objectives. Each expert has been assigned specific tasks based on their expertise and will be responsible for ensuring the successful execution of the project within the given timelines. Below is the updated list of Subject Matter Experts (SMEs) and other key roles, including mentorship staff, for each key position:

| Position | Assigned Tasks | Expert | Duration |
| --- | --- | --- | --- |
| Position K-1: Information & Data Literacy | Lead training in information literacy, data analytics, data management, and ensuring businesses understand how to leverage data for decision-making. | Hensley Edwards. MSC Computer Systems | Full Time – Dual Role |
| Position K-2: Communication & Collaboration | Provide expertise in enhancing communication through digital tools, collaboration software, and improving business processes with digital technologies like cloud platforms. | Zarah Chase, Msc. Communication, BSC Media Literacy and Communication. | Full duration – Dual Role |
| Position K-3: Small Business Operations | Focus on integrating digital tools into day-to-day business operations, including sales, marketing, customer management, and financial tools. | Joseph Gill | Full duration |
| Position K-4: Safety | Lead the development and training on cybersecurity best practices, data privacy, and ensuring businesses are safe from digital threats. | Dave George | Full duration |
| Project Manager | Overall project management, coordination with the client, milestone tracking, and reporting. | Zarah Chase | Full duration |
| Lead Digital Skills Trainer | Lead in content customization, development of training modules, and delivery of digital skills training. | Cardisha Daniel | Full duration |
| Learning Management System Administrator | Manage the Learning Management System (LMS) for course content, tracking participant progress, and troubleshooting system issues. | Kendell Daniel | Full duration |
| Digital and Social Media team | Responsible for managing the project’s digital presence, including social media, digital marketing, and community engagement. Lead social media campaigns for awareness and engagement. | Kendell Daniel, Elroy Jones (Lead: Zarah Chase) | Full duration -Dual Role |
| Monitoring & Evaluation (M&E) Officer | Responsible for monitoring progress, gathering feedback, and compiling evaluation reports. | Hensley Edwards. MSC Computer Systems | Full Time – Dual Role |
| Mentorship and Training Staff (4 Groups with 2 Mentors Each) | Provide ongoing mentorship and support to business owners/managers throughout the program, ensuring they can apply the digital transformation strategies effectively. | Group 1 Mentors: [Mentor 1, Mentor 2] Group 2 Mentors: [Mentor 3, Mentor 4] Group 3 Mentors: [Mentor 5, Mentor 6] Group 4 Mentors: [Mentor 7, Mentor 8] | Full duration |
| Administrative Staff | Scheduling, communication, document preparation, and logistical coordination. | Kendell Daniel, Ms. Chase | Full duration |

Mentorship Role and Contribution:

- Mentorship Groups: Four mentorship groups, each consisting of two mentors, will be assigned to different cohorts of businesses. These mentors will provide continuous support throughout the project, helping businesses integrate digital tools into their operations effectively.

- Full Duration: The mentorship teams will work throughout the full project duration, offering personalized advice, monitoring progress, and troubleshooting any issues that arise during the implementation of the digital transformation plans.

Details of Additional Roles:

- Learning Management System (LMS) Administrator:

  - Expert: Kendell Daniel.

  - Tasks:

    - Oversee the day-to-day management of the LMS, ensuring that course content is accessible to participants.

    - Track and report on participant progress through the training modules.

    - Provide technical support and troubleshoot issues related to the LMS platform.

- Digital and Social Media Team:

  - Lead: Zarah Chase.

  - Team Members: Kendell Daniel, Elroy Jones.

  - Tasks:

    - Manage and promote the program’s digital presence across various social media platforms.

    - Lead social media campaigns to raise awareness of the project and engage participants.

    - Create digital marketing content, including graphics, blog posts, and updates on program progress.

    - Engage with the community and stakeholders through social media channels, responding to queries and promoting digital transformation initiatives.

Mentorship Staff Details:

The mentorship teams, consisting of four groups, each with two mentors, will provide ongoing support to the business owners and managers throughout the program, ensuring that they can successfully implement digital transformation strategies.

- Mentorship Groups:

  - Group 1 Mentors: [Mentor 1, Mentor 2].

  - Group 2 Mentors: [Mentor 3, Mentor 4].

  - Group 3 Mentors: [Mentor 5, Mentor 6].

  - Group 4 Mentors: [Mentor 7, Mentor 8].

Each mentor will provide guidance in applying digital tools, offering personalized advice, and addressing challenges encountered by the businesses.

c) 	Comments (on the TOR and on counterpart staff and facilities)

Comments on Counterpart Staff and Facilities Provided by the Client:

In order to ensure the smooth execution of this project, certain support from the Client will be essential. Below are the key facilities and resources that will facilitate the successful delivery of the project:

- Project Counterpart Administrative Support:

- Request: We kindly request the Client to provide administrative support in coordinating meetings, managing participant registrations, and ensuring that all necessary documentation is available in a manner agreed by both consultant and project implementation unit (PIU) to ensure that execution, deliverable and financial flows are timely.

- Rationale: This will streamline communications and help manage logistics more efficiently, allowing the project team to focus on training and implementation.

- Office Space and Meeting Rooms:

- Request: Provision of office space and meeting rooms for the project team to use when on-site meeting with the PIU is being planned. Additionally, given the 4 cohorts to be trained with some course that must be done face to face, the use of facilities such as the national stadium training room or other conference rooms must be budgeted for within the project. These rooms, accommodation and refreshments will be used for face-to-face training sessions, consultations, and coordination meetings. These items must be clarified for costing purposed, whether consultant or project shall facilitate these cost and expenses.

- Rationale: On-site office space will facilitate collaboration between the project team and the Client, as well as allow for direct communication and logistical support during in-person training sessions.

- Local Transportation:

- Request: Assistance with local transportation arrangements for the project team, particularly for on-site visits to businesses that will be receiving in-office training.

- Rationale: Reliable local transportation will help the project team to reach multiple business locations across the island, ensuring timely and efficient delivery of training services. Would reimbursement for travel be a direct cost onto the consultant or shall it be part of the reimbursement claims.

- Access to Data and Background Reports:

- Request: Provision of access to existing background reports, studies, and relevant data related to SMEs in Grenada, including any previous assessments of digital readiness.

- Rationale: Having access to existing information will help the project team tailor the training content to the specific needs and conditions of the businesses, thus enhancing the overall effectiveness of the program.

- Technical Equipment:

- Request: If available, provision of technical equipment (e.g., projectors, internet access, and other necessary IT infrastructure) for training sessions, particularly for face-to-face cohort training.

- Rationale: Having access to such equipment will ensure that all training sessions are delivered efficiently, without delays due to technical constraints. While the consultant can provide projector and some other mobile equipment. Internet at the selected and agreed upon facilities must be provided by the project.

Form TECH-5 (for FTP and STP)

Work Schedule and planning for deliverables

The Work Schedule presented here shall be discussed and clarifies at the first meeting to ensure that the deliverables are acceptable from the envisioned details. This work plan is our proposed and can be modified to meet the client needs.

Approach to the delivery of the training is detail above ( concept of using 5 groups or cohorts of 25 small business each) will be focused on the registration into the groups and then the successfully completion of each

| N° | Deliverables 1 (D-..) | Months |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | ..... | 24 | TOTAL |
| D-1 Project Preparation Stage |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D-1A | Inception Reporting: Prepare and submit initial inception report detailing project goals, objectives, and preliminary assessment. Including minutes of meeting such as the kickoff and all interactions over the first month of the project. | XXXX |  |  |  |  |  |  |  |  |  |  |  |
| D-1B | Final Methodology and Approach: Define and finalize the methodology and approach for the project, outlining the business training strategy. | X |  |  |  |  |  |  |  |  |  |  |  |
| D-1C | Project Charter Agreement: Establish a formal agreement on the scope, resources, timelines, and responsibilities for the project. | X |  |  |  |  |  |  |  |  |  |  |  |
| D-1D | Scope of Work for Each Business: Develop and document the specific scope of work for each of the 125 businesses, tailoring it to their industry and needs. | XX |  |  |  |  |  |  |  |  |  |  |  |
| D-1E | Agreement of Core Deliverables: Define the core deliverables for each business, ensuring alignment with client and business expectations. | X |  |  |  |  |  |  |  |  |  |  |  |
| D-1F | Project Milestones Document: Establish key milestones and a timeline for the project, ensuring measurable checkpoints. | XXX |  |  |  |  |  |  |  |  |  |  |  |
| D-1G | Project Systems Setup (M&E): Set up data collection systems for monitoring and evaluation, ensuring comprehensive data collection for tracking project progress. | XXXX |  |  |  |  |  |  |  |  |  |  |  |
| The Inception Report will serve as the core physical document produced in the Inception Reporting Stage and will take 4 weeks to deliver after contract sign off. This report will include all the documents listed under D-1A to D-1G: D-1A: Final Methodology and Approach D-1B: Project Charter Agreement D-1C: Scope of Work for Each of the 125 Businesses D-1D: Agreement of Core Deliverables D-1E: Project Milestones Document D-1F: Project Systems for Data Collection and Monitoring (M&E) D-1G: Inception Reporting requirement as per contractual agreements and WB reporting clause. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Costing for this phase is based on the following costing: Payment milestone amount USD $40,000.00 (10% of the Total Contract Value) – Detail for Costing is attached as Tech5Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D-2 | Execution Stage 1 Data Collection and Analysis of Businesses: ( TOR 3.1 Needs Assessment will be targeted in this stream of work) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Gather relevant data from 125 businesses to assess their current digital and operational capabilities. |  | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX |  |  |  |  |  |
|  | Drafting Initial Assessments: Prepare preliminary assessments based on the data collected, identifying gaps and opportunities for digital transformation. |  |  | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX |  |  |  |  |
|  | Sign off on the Individual Reports for each of the 125 businesses based on the agreed sector specific template: Deliver initial findings and recommendations in an inception report to each of the small businesses. Reports will be the following: |  |  |  | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX |  |  |  |
|  | Small Business Digital Transformation Plan for Business <<Name>> Content. |  |  |  | * |  | * |  | * |  |  |  |  |
|  | Business Profile Template |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Digital Transformation Assessment |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Business Digital Transformation Plan/Guide |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Technology Adoption Roadmap |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Digital Marketing Strategy |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Operational Efficiency Improvement |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Customer Journey Mapping |  |  |  |  |  |  |  |  |  |  |  |  |
|  | KPI Measurement |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Cybersecurity Checklist |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Social Media Engagement Strategy |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Customized Training Plan based on finding and current status of the business operations. (Content development included) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Automation Process (AI Plan) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-Commerce Integration (optional) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Change Management(optional) |  |  |  |  |  |  |  |  |  |  |  |  |
| The D-2 Content Development for Training phase involves the creation of individual Small Business Digital Transformation Plans for each of the 125 selected businesses. The deliverables are spread over a total of 6 months and will be based on segments of 50 approved small business plans (twice) and 25 approved small business plans (final segment). Each plan will be developed, reviewed, and signed off by the small businesses, with a cover report submitted to the PIU (Project Implementation Unit) along with the invoice for payment. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Payment will be associated with the following: Milestone for D2: - 50 Plans Approved and Completed for Small Business (cohort 1) USD$125,000.00 - 50 Plans Approved and Completed for Small Business (cohort 2) USD$125,000.00 - 25 Plans Approved and Completed for Small Business (final cohort) USD$ 62,500.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D-3 Content Delivery Training (delivery phase) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identify and Structure Content: Develop training content for key business areas (sales, operations, marketing, finance) to guide digital transformation. |  |  | All activities are already detailed according to the e-Learning Kings framework and the D-2 assessment phase of the project, as outlined in the table above. This structured approach ensures that both the common and unique business needs are addressed, with the framework guiding the overall project execution and the D-2 phase focusing on developing individualized digital transformation plans for each business. Mandate General Course: (suggested titles): Digital Tools for Growth: Harnessing Platforms to Transform Your Small Business - Focus: Digital adoption technologies and platforms for small businesses. Data-Driven Success: Leveraging Analytics to Make Smarter Business Decisions - Focus: Data Analytics – decision making using available data to drive your business changes and achieve goals. Cloud on a Budget: Powering Your Business Without an IT Team - Focus: Cloud Computing – the low-cost method of getting online without having an IT team. Cyber Safe: How to Plan for and Mitigate Online Risks in Your Business - Focus: Cybersecurity Essentials – The risk of going online can be planned for. AI at Work: Supercharging Your Business with Artificial Intelligence - Focus: Enhancing the better version of your business by adopting Artificial Intelligence as your new employee. Social Media Mastery: Driving Business Growth Through Digital Marketing - Focus: Social media and digital marketing strategies for small businesses to enhance their online presence and drive customer engagement. Clear and Connected: Mastering Online Communication and Technical Writing for Business Success - Focus: Online methods of communication, technical writing, and ensuring clarity when communicating with customers and business partners. |  |  |  |  |  |  |  |  |  |
|  | Develop Training Materials: Create detailed training materials customized for each key area based on the specific needs of the businesses. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review and Refine Content Based on Feedback: Refine and adjust the content based on feedback from the client and initial businesses trained. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Finalize and Deliver the Training Content: Deliver the finalized training content that will be used in the direct training sessions. |  |  | Cohort-Based Group Sessions will allow all participants in 4 or 5 cohorts to participate in the above listed course that is tailored for the Grenadian micro, small and medium context allowing for relevance in the delivery and the adoption of the various ideas and technologies presented to the 125 participating businesses. The detail of these course will be delivered as the core outputs, however, Customized Individual Training. Tailored sessions will be developed for each business to address unique business-specific needs based on their individualized Digital Transformation Plan, these types of activities will be supported via the mentorship streamline of work activities, allowing a business to adopt any of the technologies presented in their operations. |  |  |  |  |  |  |  |  |  |

1	List the deliverables with the breakdown for activities required to produce them and other benchmarks such as the Client’s approvals.  For phased assignments, indicate the activities, delivery of reports, and benchmarks separately for each phase.

2	Duration of activities shall be indicated in a form of a bar chart.

3.     Include a legend, if necessary, to help read the chart.

Ongoing Concurrent Training:

The training program will consist of two parallel tracks:

- Cohort-Based Group Sessions: These sessions will focus on common elements relevant to all businesses, such as digital marketing, e-commerce integration, financial management tools, and customer relationship management (CRM) systems. Group training will allow businesses to learn foundational digital transformation concepts together, facilitating shared experiences and discussions on general challenges and opportunities.

- Customized Individual Training: Tailored sessions will be developed for each business to address unique business-specific needs based on their individualized Digital Transformation Plan. This customized training will dive into specific technologies, operational processes, or strategies that are essential for the unique growth and transformation of each business.

By integrating both cohort training for common elements and individualized training, the program ensures that all participants benefit from broad knowledge sharing while receiving the necessary support to address their specific business challenges.

Form TECH-6 (for FTP and STP)

Team Composition, Assignment, and Key Experts’ inputs

| N° | Name | Expert’s input (in person/month) per each Deliverable (listed in TECH-5) |  |  |  |  |  |  |  |  |  |  |  |  | Total time-input (in Months) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Position |  | D-1 |  | D-2 |  | D-3 | ........ |  | D-... |  |  |  | Home | Field | Total |
| KEY EXPERTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| K-1 | {e.g., Mr. Abbbb} | [Team Leader] | [Home] | [2 month] |  | [1.0] |  | [1.0] |  |  |  |  |  |  |  |  |  |
|  |  |  | [Field] | [0.5 m] |  | [2.5] |  | [0] |  |  |  |  |  |  |  |  |  |
| K-2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| K-3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| n |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal |  |  |  |  |  |  |
| NON-KEY EXPERTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N-1 |  |  | [Home] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | [Field] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N-2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| n |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total |  |  |  |  |  |  |

1	For Key Experts, the input should be indicated individually for the same positions as required under the Data Sheet ITC21.1.

2	Months are counted from the start of the assignment/mobilization.  One (1) month equals twenty two (22) working (billable) days. One working (billable) day shall be not less than eight (8) working (billable) hours.

3	“Home” means work in the office in the expert’s country of residence. “Field” work means work carried out in the Client’s country or any other country outside the expert’s country of residence.

Full time input

Part time input

Form TECH-6

(Continued)

CURRICULUM VITAE (CV)

| Position Title and No. | Information Data Analysis and Digital Business Literacy Specialist |
| --- | --- |
| Introduction | Experienced Information and Digital Business Literacy Specialist with a robust background in educational technology and digital transformation, seeking to leverage expertise to drive organizational growth and innovation. |
| Name of Expert: | Hainsley P. Edwards |
| Date of Birth: | 12th April 1977 |
| Country of Citizenship/Residence | Grenada |
| Contact Details: | Email: runoutgd@gmail.com / +1 (473) 419-5115 |
|  | Education: - Master of Science in Software Engineering from University of Hertfordshire, Hartfield, England - 2015. - Master of Science in Data Analytics (currently writing thesis) 2024 - Power Bl Architecture Training - Power BI Rockstar - Bachelor of Science in Computer Science Engineering from Havana University of Technology - José Antonio Echeverría, La Habana, Cuba - 2004. - Diploma in Spanish from University of Cienfuegos, Cuba - 1999. |

________________________________________________________________________

Employment record relevant to the assignment:

Summary of Mr. Hainsley P. Edwards Qualifications

- Mr. Hainsley P. Edwards is a seasoned IT professional with over 20 years of expertise in software development, data analysis, business intelligence, and project management. He holds a Master of Science in Software Engineering from the University of Hertfordshire, UK, and a Bachelor of Science in Computer Science Engineering from the Havana University of Technology, Cuba. Throughout his career, he has successfully led digital transformation projects, developed business intelligence solutions, and enhanced business operations through data-driven insights.

- Mr. Edwards is certified in Power BI and data analytics, with ongoing practice in the retail and sales environments. He has completed several courses on data-driven decision-making, specifically for the retail sector, leveraging his hands-on experience. His expertise includes using tools and technologies such as Power BI, Power Apps, AI applications, and generative artificial intelligence techniques, along with machine learning to optimize business processes and improve decision-making. Mr. Edwards has extensive experience in managing large-scale IT projects, including simultaneous operations across multiple locations, as seen in his work at Riteway Food Markets in the British Virgin Islands. There, he not only managed projects but also trained staff in adopting enterprise-level tools like Celoxis and integrated MS Projects WBS into SharePoint for efficient project collaboration. His technical expertise includes proficiency in various programming languages such as C#, SQL, Python, and PHP, along with hands-on experience with Microsoft Power BI, Delphi, and SQL Server Integration Services.

- In addition to his technical skills, Mr. Edwards has a strong background in education, having taught Information Technology at both the secondary and university levels. His ability to translate complex IT concepts into accessible lessons, along with his mentorship of students and staff, demonstrates his capacity to foster digital literacy within organizations. This combination of technical proficiency, project management expertise, and a strong foundation in teaching positions Mr. Edwards as a well-qualified Information and Digital Business Literacy Specialist, capable of driving organizational growth and digital transformation.

- As a certified teacher, Mr. Edwards brings a wealth of experience in curriculum design and development, with a specific focus on the integration of technology within educational frameworks. His expertise includes guiding stakeholders through the adoption of educational technologies such as virtual learning platforms, digital collaboration tools, and online assessment systems.

- In addition to his work in education, Mr. Edwards has helped implement technology adoption strategies in the medium to large business environments. He has introduced business intelligence solutions, AI-driven decision-making tools, and cloud-based collaboration platforms to streamline operations and improve productivity. He has employed methodologies such as Agile project management, Lean processes for digital transformation, and data-driven business strategies to foster efficiency and scalability in both educational and corporate settings.

Past Assignment & related experiences to Current Role.

| Period | Employing Organization and Your Title/Position | Contact Information for References | Country | Summary of Activities Performed Relevant to the Assignment |
| --- | --- | --- | --- | --- |
| 2023 – 2024 | SPA (Simple Pure Agroprocessing) (Lead Support for Workflow Process Development during Digital Transformation) | Email: info@spa-agroprocessing.com Dawne St. Louis | Grenada | – Led the development of workflow processes to assist SPA in their digital transformation journey. – Supported the implementation of digital tools and systems to optimize agroprocessing operations. – Provided technical guidance on the integration of new digital technologies to enhance business efficiency. – Conducted training and knowledge transfer to ensure smooth adoption of digital workflows. |
| 2022 – 2024 | DG4R Consulting (Lead Consultant for Information Management and Records Management) | Email: info@azits.net Nigel Noel, AZitek. Project manager: Cleavon Noel, Government of Grenada. | Grenada | – Led the digitization project for records management, ensuring digital transformation of key documentation systems. – Developed strategies and best practices for information management and data integrity. – Provided training to staff on digital records management tools and practices to enhance business efficiency. – Ensured compliance with regulatory standards and oversaw the successful digitization and archiving of critical records. |
| April 2016 – Present | Roadtown Wholesale Trading Ltd. (Project Implementation Manager, Application Developer/DBA) | Email: info@riteway.vg Phone: +1-284-494-2496 | BVI | – Led the implementation of digital and non-construction projects across multiple locations. – Trained staff in Celoxis project management and integrated MS Project WBS into SharePoint. – Developed high-level management reports using Power BI and SQL for data-driven decision-making. – Managed database systems (SQL Server) and supported Microsoft Dynamics GP for enterprise resource planning. |
| Dec 2015 – Mar 2016 | LIAT (1974) Ltd. (Programmer Analyst) | Email: info@liat.com | Antigua | – Developed and deployed BI reports using Microsoft SQL Server. – Assisted in administering IBM AS/400 system. – Supported the proposal process for ERP and ticketing systems. |
| May 2010 – Dec 2015 | National Insurance Scheme (Computer Programmer) | Email: dnoel@nisgrenada.org Phone: +1-473-440-3309 | Grenada | – Designed and implemented an integrated system for customer service using Visual Studio and Crystal Reports. – Managed IBM AS/400 operations and SQL Server. – Provided technical support for network infrastructure, database management, and software development. |
| 2009 – 2010 | Inland Revenue Division/Ministry of Finance (Systems Analyst, VAT Unit) | Email: info@finance.gov.gd | Grenada | – Supported Oracle database administration, network infrastructure management, and Oracle Forms development. – Provided desktop support and advised management on IT infrastructure and systems. |
| 2006 – 2009 | Supreme Court Registry of Grenada (Systems Administrator) | Email: info@judiciary.gov.gd | Grenada | – Managed the IT infrastructure for the High Court and related registries, including SQL Server and Windows Server administration. – Advised on IT procurement and budgeting. – Developed digitized systems for court documentation management. |

Language Skills (indicate only languages in which you can work): English , Spanish

Adequacy for the Assignment:

| Detailed Tasks Assigned on Consultant’s Team of Experts | Reference to Prior Work/Assignments that Best Illustrates Capability to Handle the Assigned Tasks |
| --- | --- |
| Digital Workflow Development: Design and implement digital workflows to streamline processes for organizations undergoing digital transformation. | SPA (Simple Pure Agroprocessing) – 2023 to 2024: Led the development of workflow processes for SPA’s digital transformation journey, providing technical guidance, system integration, and training. |
| Records Management Digitization: Lead efforts in digitizing records management systems to improve accessibility and compliance. | DG4R Consulting – 2022 to 2024: Led the digitization project for information and records management, ensuring compliance with regulatory standards and optimizing document archiving systems. |
| Business Intelligence Reporting: Develop high-level management reports using BI tools for data-driven decision-making. | Roadtown Wholesale Trading Ltd. – 2016 to Present: Developed business intelligence reports using Power BI and SQL for key decision-makers across various departments, including HR, sales, and finance. |
| Database Administration and Support: Maintain and optimize database systems to ensure data integrity, performance, and accessibility. | National Insurance Scheme – 2010 to 2015: Managed SQL Server databases, conducted database performance tuning, and supported the IBM AS/400 system for the National Insurance Scheme. |
| Digital Transformation Support: Provide support for digital transformation efforts, including system integration and user training. | Roadtown Wholesale Trading Ltd. – 2016 to Present: Supported the digital transformation process by implementing ERP systems and training staff on digital tools like Celoxis and MS Project WBS integrated with SharePoint. |
| ERP System Development and Implementation: Design and implement Enterprise Resource Planning (ERP) systems to optimize business operations. | LIAT (1974) Ltd. – 2015 to 2016: Assisted in developing BI reports and supported the administration of IBM AS/400 and ERP systems for the airline company. |
| IT Infrastructure Management: Administer and maintain IT systems, including server management and network infrastructure. | Supreme Court Registry of Grenada – 2006 to 2009: Managed IT infrastructure for the High Court, including SQL Server and Windows Server administration, and advised on IT procurement and budgeting. |
| Training and Knowledge Transfer: Train staff on digital systems and tools to ensure smooth adoption and integration within organizations. | SPA (Simple Pure Agroprocessing) – 2023 to 2024: Conducted staff training on digital workflows and system integrations during the digital transformation phase of SPA. |
| General Training for AI Use Cases in Small and Micro Organizations: Provide training on how to utilize artificial intelligence systems to improve productivity and introduce other efficiency methods. | e-Learning Kings (2020–Present): Provided AI-focused digital transformation training for micro and small businesses across Grenada, using AI tools to optimize business processes and improve overall productivity in line with e-Learning Kings’ digital transformation framework. |
| Conduct Survey and Assessment: Provided support for data collection using various platforms for digital data collection in multiple sectors. | Edwards Consulting Services (e-Learning Kings): Worked with systems such as Android ODK for various survey design tools using offline and online survey methods, allowing clients to collect data from customers or farmers in the field. |

Expert ’s contact information:

Email: runoutgd@gmail.com

Phone: +1 (473) 419-5115

Certification:

I, the undersigned, certify that to the best of my knowledge and belief, this CV correctly describes myself, my qualifications, and my experience, and I am available, as and when necessary, to undertake the assignment in case of an award. I understand that any misstatement or misrepresentation described herein may lead to my disqualification or dismissal by the Client, and/or sanctions by the Bank.

Name of Expert 					 Signature 					Date

Name of authorized 				Signature						Date

Representative of the Consultant

(the same who signs the Proposal)

Form TECH-7 (for FTP and STP)

CODE OF CONDUCT FOR EXPERTS Form

Note to the Consultant:

The minimum content of the Code of Conduct form as set out by the Client shall not be substantially modified. However, the Consultant may add requirements as appropriate, including to take into account Contract-specific issues/risks.

The Consultant shall initial and submit the Code of Conduct form as part of its Proposal.

CODE OF CONDUCT FOR EXPERTS

We are the Consultant, [enter name of Consultant].  We have signed a contract with [enter name of Client] for [enter description of the Services]. Our contract requires us to implement measures to address social risks related to the Services, if any, including the risks of sexual exploitation, sexual abuse and sexual harassment.

This Code of Conduct is part of our measures to deal with social risks, if any, related to the Services.  This Code of Conduct identifies the behavior that we require from all Experts.

Our workplace for carrying the Services is an environment where unsafe, offensive, abusive or violent behavior will not be tolerated and where all persons should feel comfortable raising issues or concerns without fear of retaliation.

REQUIRED CONDUCT

Experts shall:

- carry out his/her duties competently and diligently;

- comply with this Code of Conduct and all applicable laws, regulations and other requirements;

- treat other people with respect, and not discriminate against specific groups such as women, people with disabilities, migrant workers or children;

- not engage in Sexual Harassment, which means unwelcome sexual advances, requests for sexual favors, and other verbal or physical conduct of a sexual nature with other Experts, or Client’s Personnel;

- not engage in Sexual Exploitation, which means any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another;

- not engage in Sexual Abuse, which means the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions;

- not engage in any form of sexual activity with individuals under the age of 18, except in case of pre-existing marriage;

- complete training/sensitization that may be provided related to the social aspects of the Contract, including on Sexual Exploitation and Abuse (SEA), and Sexual Harassment (SH);

- report violations of this Code of Conduct; and

- not retaliate against any person who reports violations of this Code of Conduct, whether to us or the Client.

RAISING CONCERNS

If any person observes behavior that he/she believes may represent a violation of this Code of Conduct, or that otherwise concerns him/her, he/she should raise the issue promptly. This can be done in either of the following ways:

- Contact [enter name of person assigned by the Consultant to handle such matters] in writing at this address [   ] or by telephone at [   ] or in person at [   ]; or

- Call [  ]  to reach the Consultant’s hotline (if any) and leave a message.

The person’s identity will be kept confidential, unless reporting of allegations is mandated by the country law. Anonymous complaints or allegations may also be submitted and will be given all due and appropriate consideration. We take seriously all reports of possible misconduct and will investigate and take appropriate action. We will provide warm referrals to service providers that may help support the person who experienced the alleged incident, as appropriate.

There will be no retaliation against any person who raises a concern in good faith about any behavior prohibited by this Code of Conduct.  Such retaliation would be a violation of this Code of Conduct.

CONSEQUENCES OF VIOLATING THE CODE OF CONDUCT

Any violation of this Code of Conduct by Experts may result in serious consequences, up to and including termination and possible referral to legal authorities.

FOR EXPERT:

I have received a copy of this Code of Conduct written in a language that I comprehend.  I understand that if I have any questions about this Code of Conduct, I can contact [enter name of the contact person(s) assigned by the Consultant] requesting an explanation.

Name of Expert: [insert name]

Signature: __________________________________________________________

Date: (day month year): _______________________________________________

Countersignature of authorized representative of the Consultant:

Signature: ________________________________________________________

Date: (day month year): ______________________________________________

Form TECH-8 (for FTP and STP)

Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Performance Declaration

[The following table shall be filled in for the Consultant, each member of a Joint Venture and each subconsultant proposed by the Consultant]

Consultant’s Name: [insert full name]
Date: [insert day, month, year]
Joint Venture Member’s or Subconsultant’s Name: [insert full name]
RFP No. and title: [insert RFP number and title]
Page [insert page number] of [insert total number] pages

SEA and/or SH Declaration

We: (a) have not been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations (b) are subject to disqualification by the Bank for non-compliance with SEA/ SH obligations (c) had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations. An arbitral award on the disqualification case has been made in our favor.

[If (c) above is applicable, attach evidence of an arbitral award reversing the findings on the issues underlying the disqualification.]

Section 4.  Financial Proposal - Standard Forms

{Notes to Consultant shown in brackets {  } provide guidance to the Consultant to prepare the Financial Proposals; they should not appear on the Financial Proposals to be submitted.}

Financial Proposal Standard Forms shall be used for the preparation of the Financial Proposal according to the instructions provided in Section 2.

FIN-1	Financial Proposal Submission Form

FIN-2	Summary of Costs

FIN-3	Breakdown of Remuneration, including Appendix A “Financial Negotiations - Breakdown of Remuneration Rates” in the case of QBS method

FIN-4	Reimbursable expenses

Form  FIN-1

Financial Proposal Submission Form

{Location, Date}

To:	Ministry of ICT

Sir Eric Matthew Gairy Botanical Gardens

St George’s

Grenada

Dear Sirs:

We, the undersigned, offer to provide the consulting services for [Insert title of assignment] in accordance with your Request for Proposal dated [Insert Date] and our Technical Proposal.

Our attached Financial Proposal is for the amount of {Indicate the corresponding to the amount(s) currency(ies)} {Insert amount(s) in words and figures}, [Insert “including” or “excluding”] of all indirect local taxes in accordance with ITC 25.1 in the Data Sheet. The estimated amount of local indirect taxes is {Insert currency} {Insert amount in words and figures} which shall be confirmed or adjusted, if needed, during negotiations. {Please note that all amounts shall be the same as in Form FIN-2}.

Our Financial Proposal shall be valid and remain binding upon us, subject to the modifications resulting from Contract negotiations, for the period of time specified in the Data Sheet, ITC 12.1.

Commissions and gratuities paid or to be paid by us to an agent or any third party relating to preparation or submission of this Proposal and Contract execution, paid if we are awarded the Contract, are listed below:

Name and Address	Amount and	Purpose of Commission

of Agents	Currency	or Gratuity

{If no payments are made or promised, add the following statement: “No commissions or gratuities have been or are to be paid by us to agents or any third party relating to this Proposal and Contract execution.”}

We understand you are not bound to accept any Proposal you receive.

We remain,

Yours sincerely,

_________________________________________________________________

Signature (of Consultant’s authorized representative) {In full and initials}:

Full name:	{insert full name of authorized representative}

Title: 	{insert title/position of authorized representative}

Name of Consultant (company’s name or JV’s name):

Capacity: 	{insert the person’s capacity to sign for the Consultant}

Address:  	{insert the authorized representative’s address}

Phone/fax:	{insert the authorized representative’s phone and fax number, if applicable}

Email:  	{insert the authorized representative’s email address}

{For a joint venture, either all members shall sign or only the lead member/consultant, in which case the power of attorney to sign on behalf of all members shall be attached}

Form FIN-2 Summary of Costs

| Item | Cost |  |  |  |
| --- | --- | --- | --- | --- |
|  | {Consultant must state the proposed Costs in accordance with ITC 16.4 of the Data Sheet; delete columns which are not used} |  |  |  |
|  | {Insert Foreign Currency # 1} | {Insert Foreign Currency # 2, if used} | {Insert Foreign Currency # 3, if used} | {Insert Local Currency, if used and/or required (16.4 Data Sheet} |
| Cost of the Financial Proposal |  |  |  |  |
| Including: |  |  |  |  |
| (1) Remuneration |  |  |  |  |
| (2) Reimbursables |  |  |  |  |
| Total Cost of the Financial Proposal: {Should match the amount in Form FIN-1} |  |  |  |  |
| Indirect Local Tax Estimates – to be discussed and finalized at the negotiations if the Contract is awarded |  |  |  |  |
| - {insert type of tax. e.g., VAT or sales tax} |  |  |  |  |
| - {e.g., income tax on non-resident experts} |  |  |  |  |
| - {insert type of tax} |  |  |  |  |
| Total Estimate for Indirect Local Tax: |  |  |  |  |

Footnote: Payments will be made in the currency(ies) expressed above (Reference to ITC 16.4).

FORM FIN-3 BREAKDOWN of Remuneration

When used for Lump-Sum contract assignment, information to be provided in this Form shall only be used to demonstrate the basis for the calculation of the Contract’s ceiling amount; to calculate applicable taxes at contract negotiations; and, if needed, to establish payments to the Consultant for possible additional services requested by the Client. This Form shall not be used as a basis for payments under Lump-Sum contracts

| A. Remuneration |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Name | Position (as in TECH-6) | Person-month Remuneration Rate | Time Input in Person/Month (from TECH-6) | {Currency # 1- as in FIN-2} | {Currency # 2- as in FIN-2} | {Currency# 3- as in FIN-2} | {Local Currency- as in FIN-2} |
|  | Key Experts |  |  |  |  |  |  |  |
| K-1 |  |  | [Home] |  |  |  |  |  |
|  |  |  | [Field] |  |  |  |  |  |
| K-2 |  |  |  |  |  |  |  |  |
|  | Non-Key Experts |  |  |  |  |  |  |  |
| N-1 |  |  | [Home] |  |  |  |  |  |
| N-2 |  |  | [Field] |  |  |  |  |  |
|  |  |  |  | Total Costs |  |  |  |  |

Appendix A. Financial Negotiations - Breakdown of Remuneration Rates

- Review of Remuneration Rates

  - The remuneration rates are made up of salary or a base fee, social costs, overheads, profit, and any premium or allowance that may be paid for assignments away from headquarters or a home office.  An attached Sample Form can be used to provide a breakdown of rates.

  - If the RFP requests submission of a technical proposal only, the Sample Form is used by the selected Consultant to prepare for the negotiations of the Contract. If the RFP requests submission of the financial proposal, the Sample Form shall be completed and attached to the Financial Form-3.  Agreed (at the negotiations) breakdown sheets shall form part of the negotiated Contract and included in its Appendix D or C.

  - At the negotiations the firm shall be prepared to disclose its audited financial statements for the last three years, to substantiate its rates, and accept that its proposed rates and other financial matters are subject to scrutiny.  The Client is charged with the custody of government funds and is expected to exercise prudence in the expenditure of these funds.

  - Rate details are discussed below:

- Salary is the gross regular cash salary or fee paid to the individual in the firm’s home office.  It shall not contain any premium for work away from headquarters or bonus (except where these are included by law or government regulations).

- Bonuses are normally paid out of profits.  To avoid double counting, any bonuses shall not normally be included in the “Salary” and should be shown separately.  Where the Consultant’s accounting system is such that the percentages of social costs and overheads are based on total revenue, including bonuses, those percentages shall be adjusted downward accordingly.  Where national policy requires that 13 months’ pay be given for 12 months’ work, the profit element need not be adjusted downward.  Any discussions on bonuses shall be supported by audited documentation, which shall be treated as confidential.

- Social Charges are the costs of non-monetary benefits and may include, inter alia, social security (including pension, medical, and life insurance costs) and the cost of a paid sick and/or annual leave.  In this regard, a paid leave during public holidays or an annual leave taken during an assignment if no Expert’s replacement has been provided is not considered social charges.

- Cost of Leave. The principles of calculating the cost of total days leave per annum as a percentage of basic salary is normally calculated as follows:

Leave cost as percentage of salary =

Where w = weekends, ph = public holidays, v = vacation, and s = sick leave.

Please note that leave can be considered as a social cost only if the Client is not charged for the leave taken.

- Overheads are the Consultant’s business costs that are not directly related to the execution of the assignment and shall not be reimbursed as separate items under the Contract. Typical items are home office costs (non-billable time, time of senior Consultant’s staff monitoring the project, rent of headquarters’ office, support staff, research, staff training, marketing, etc.), the cost of Consultant’s personnel not currently employed on revenue-earning projects, taxes on business activities, and business promotion costs. During negotiations, audited financial statements, certified as correct by an independent auditor and supporting the last three years’ overheads, shall be available for discussion, together with detailed lists of items making up the overheads and the percentage by which each relates to basic salary.  The Client does not accept an add-on margin for social charges, overhead expenses, etc. for Experts who are not permanent employees of the Consultant.  In such case, the Consultant shall be entitled only to administrative costs and a fee on the monthly payments charged for sub-contracted Experts.

- Profit is normally based on the sum of the Salary, Social costs, and Overheads.  If any bonuses paid on a regular basis are listed, a corresponding reduction shall be made in the profit amount. Profit shall not be allowed on travel or any other reimbursable expenses.

- Away from Home Office Allowance or Premium or Subsistence Allowances. Some Consultants pay allowances to Experts working away from headquarters or outside of the home office.  Such allowances are calculated as a percentage of salary (or a fee) and shall not draw overheads or profit.  Sometimes, by law, such allowances may draw social costs.  In this case, the amount of this social cost shall still be shown under social costs, with the net allowance shown separately.

UNDP standard rates for the particular country may be used as reference to determine subsistence allowances.

Sample Form

Consultant:	Country:

Assignment:	Date:

Consultant’s Representations Regarding Costs and Charges

We hereby confirm that:

(a)	the basic fees  indicated in the attached table are taken from the firm’s payroll records and reflect the current  rates of the Experts listed which have not been raised other than within the normal annual pay increase policy as applied to all the Consultant’s Experts;

(b)	attached are true copies of the latest pay slips of the Experts listed;

(c)	the away- from- home office allowances indicated below are those that the Consultant has agreed to pay for this assignment to the Experts listed;

(d)	the factors listed in the attached table for social charges and overhead are based on the firm’s average cost experiences for the latest three years as represented by the firm’s financial statements; and

(e)	said factors for overhead and social charges do not include any bonuses or other means of profit-sharing.

[Name of Consultant]

Signature of Authorized Representative	Date

Name:

Title:

Consultant’s Representations Regarding Costs and Charges

(Model Form I)

(Expressed in {insert name of currency*})

| Personnel |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name | Position | Basic Remuneration Rate per Working Month/Day/Year | Social Charges1 | Overhead1 | Subtotal | Profit2 | Away from Home Office Allowance | Proposed Fixed Rate per Working Month/Day/Hour | Proposed Fixed Rate per Working Month/Day/Hour1 |
| Home Office |  |  |  |  |  |  |  |  |  |
| Client’s Country |  |  |  |  |  |  |  |  |  |

{* If more than one currency is used, use additional table(s), one for each currency}

1.	Expressed as percentage of 1

2.	Expressed as percentage of 4

Form  FIN-4  Breakdown of Reimbursable Expenses

When used for Lump-Sum contract assignment, information to be provided in this Form shall only be used to demonstrate the basis for calculation of the Contract ceiling amount, to calculate applicable taxes at contract negotiations and, if needed, to establish payments to the Consultant for possible additional services requested by the Client. This form shall not be used as a basis for payments under Lump-Sum contracts

| B. Reimbursable Expenses |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| N° | Type of Reimbursable Expenses | Unit | Unit Cost | Quantity | {Currency # 1- as in FIN-2} | {Currency # 2- as in FIN-2} | {Currency# 3- as in FIN-2} | {Local Currency- as in FIN-2} |
|  | {e.g., Per diem allowances**} | {Day} |  |  |  |  |  |  |
|  | {e.g., International flights} | {Ticket} |  |  |  |  |  |  |
|  | {e.g., In/out airport transportation} | {Trip} |  |  |  |  |  |  |
|  | {e.g., Communication costs between Insert place and Insert place} |  |  |  |  |  |  |  |
|  | { e.g., reproduction of reports} |  |  |  |  |  |  |  |
|  | {e.g., Office rent} |  |  |  |  |  |  |  |
|  | .................................... |  |  |  |  |  |  |  |
|  | {Training of the Client’s personnel – if required in TOR} |  |  |  |  |  |  |  |
| Total Costs |  |  |  |  |  |  |  |  |

Legend:

“Per diem allowance” is paid for each night the expert is required by the Contract to be away from his/her usual place of residence. Client can set up a ceiling.

Section 5.  Eligible Countries

In reference to ITC 6.3.2, for the information of shortlisted Consultants, at the present time firms, goods and services from the following countries are excluded from this selection:

Under the ITC 6.3.2 (a): ________________ [list country/countries following approval by the Bank to apply the restriction or state “none”]

Under the ITC 6.3.2 (b): ________________ [list country/countries or indicate “none”]

Section 6.  Fraud and Corruption

(This Section 6, Fraud and Corruption shall not be modified)

- Purpose

  - The Bank’s Anti-Corruption Guidelines and this annex apply with respect to procurement under Bank Investment Project Financing operations.

- Requirements

- The Bank requires that Borrowers (including beneficiaries of Bank financing); bidders (applicants/proposers), consultants, contractors and suppliers; any sub-contractors, sub-consultants, service providers or suppliers; any agents (whether declared or not); and any of their personnel, observe the highest standard of ethics during the procurement process, selection and contract execution of Bank-financed contracts, and refrain from Fraud and Corruption.

- To this end, the Bank:

- Defines, for the purposes of this provision, the terms set forth below as follows:

- “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party;

- “fraudulent practice” is any act or omission, including misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial or other benefit or to avoid an obligation;

- “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party;

- “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;

- “obstructive practice” is:

- deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive, or collusive practice; and/or threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or

- acts intended to materially impede the exercise of the Bank’s inspection and audit rights provided for under paragraph 2.2 e. below.

- Rejects a proposal for award if the Bank determines that the firm or individual recommended for award, any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, suppliers and/ or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;

- In addition to the legal remedies set out in the relevant Legal Agreement, may take other appropriate actions, including declaring misprocurement, if the Bank determines at any time that representatives of the Borrower or of a recipient of any part of the proceeds of the loan engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the procurement process, selection and/or execution of the contract in question,  without the Borrower having taken timely and appropriate action satisfactory to the Bank to address such practices when they occur, including by failing to inform the Bank in a timely manner at the time  they knew of the practices;

- Pursuant to the Bank’s Anti- Corruption Guidelines and in accordance with the Bank’s prevailing sanctions policies and procedures, may sanction a firm or individual, either indefinitely or for a stated period of time, including by publicly declaring such firm or individual ineligible (i) to be awarded or otherwise benefit from a Bank-financed contract, financially or in any other manner; (ii) to be a nominated sub-contractor, consultant, manufacturer or supplier, or service provider of an otherwise eligible firm being awarded a Bank-financed contract; and (iii) to receive the proceeds of any loan made by the Bank or otherwise to participate further in the preparation or implementation of any Bank-financed project;

- Requires that a clause be included in bidding/request for proposals documents and in contracts financed by a Bank loan, requiring (i) bidders (applicants/proposers),, consultants, contractors, and suppliers, and their sub-contractors, sub-consultants, service providers, suppliers, agents, personnel, permit the Bank to inspect all accounts, records and other documents relating to the procurement process, selection and/or contract execution, and to have them audited by auditors appointed by the Bank.

Section 7.  Terms of Reference

Project Title: Development and Delivery of Managerial Training.

Terms of Reference (TOR) for the hiring of a firm to

Create Content and Deliver training to Managers and Business Owners

1. INTRODUCTION

The Government of Grenada, in collaboration with the World Bank Group, is embarking on a transformative journey toward a digitally empowered future. The Caribbean Digital Transformation Project (CARDTP) represents a significant endeavor aimed at addressing critical challenges and harnessing opportunities to cultivate the Eastern Caribbean Digital Economy. This visionary initiative seeks to drive economic growth, foster job creation, and enhance service delivery across the region.

At its core, the project envisions a future where every individual and business within the Eastern Caribbean region possesses the tools and knowledge required to actively participate in an increasingly digital marketplace and society. It emphasizes the importance of universal access to broadband, digital financial services, and the acquisition of essential digital skills.

One of the goals of the project is to stimulate the adoption of digital technologies, platforms, and digitally enabled business models by small and medium enterprises (SMEs) throughout Grenada. This strategic initiative aims to bolster the productivity and competitiveness of traditional industries, catalyze a shift toward modernization and innovation in the private sector, and address the current shortage of demand for digitally skilled professionals and IT services in the regional market. Activities to achieve this goal include a program to provide managerial training and business advisory services to business managers and owners.

The Government of Grenada through the CARDTP Project is therefore seeking a reputable training institute to design, develop, coordinate, and implement a comprehensive training program tailored for managers and business owners. The goal of the program is to increase the number of firms completing technology adoption programs by training at least 125 business owners/ managers. By the end of this program, we aim to have these firms ready and able to adopt technology within their businesses.

The program will provide Support to Small and Medium Enterprises in Grenada. The specific eligibility criteria for the program participants are:

- Gender: Female and Male-  The program aims to assist managers and business owners of both genders to adopt technology in their businesses. However, to ensure gender inclusivity and diversity at least 30 % of the participants in this training must be Females.

- Business Type - Exclusively for Non-ICT Businesses: This training aims to promote the integration of digital technologies and platforms into non-ICT businesses. Therefore, businesses that are already fully engaged in ICT, having incorporated digital technologies and platforms, will not be eligible for participation.

- Years of Operation: 6 months – 15 years - This requirement aims to ensure that applicants have a substantial history of engagement and experience within the industry, sector, or field in which they operate.

- Reliable access to a computer and the internet – given the objective of the training and the method of training reliable access to a computer and the internet, is an eligibility requirement for the training program participants.

- Target Sectors: The training program is open to participants from all sectors.

- Country of residence: Grenada – financing for this training has been attributed to benefit the citizens of Grenada only. Therefore, the eligible entity must be a Grenadian with a business registered in Grenada.

The training program will be designed and implemented in close coordination with the Ministry of ICT through the CARDTP Project. The selected private sector training provider will have primary responsibility for designing and implementing the training program. However, all stages of the program will be closely coordinated with key parts of the CARDTP Unit. At the end of the program, the training documents designed and developed will be the property of the Government of Grenada.

.

2. OBJECTIVE

The primary objective of this consultancy is to engage a Content developer to create and execute a mentorship and training program that addresses the specific needs of managers and business owners. The program should equip participants with the knowledge, skills, and tools necessary to excel in their roles, navigate challenges, and drive business growth. The focus of the courses should include digital technologies and platforms with a focus on Data Analytics, Cloud Computing, Cybersecurity essentials, and the use of AI in the workplace.

3. Scope of Work

The Content developer/ training firm will be responsible for providing training to at least 125 SMEs, of which 30% must be female business owners/ managers. The following are the tasks involved:

3.1 Needs Assessment

1. Conduct a needs assessment to identify the specific challenges, gaps, and opportunities faced by managers and business owners in the target market.

2. Analyze the current skill levels and training requirements of the target audience.

3.2 Program Design and Development

- Based on the needs assessment, design, develop, coordinate, and implement a digital adoption program for business owners that covers essential topics such as:

  - Improving productivity by browsing, searching, and filtering data, with a special focus on leveraging cloud computing for efficient data storage, management and retrieval

  - Managing data efficiently with emphasis on data analytics for insightful decision-making.

  - Utilizing Digital Technologies and Platforms to streamline business operations, fostering operational efficiency and seamless interactions.

  - Enhancing customer engagement and business partnership by using digital platforms to communicate with customers, vendors, and partners in real-time

  - Implementing digital tools, software and artificial Intelligence for process automation, advanced workflow improvement, and increased operational efficiency.

  - Leveraging social media platforms to connect with customers, promote products and services, and build brand awareness.

  - Cybersecurity Essentials: Protecting devices, personal data and managing digital identity to help prevent security breaches, data theft, and other cyber threats in your business.

- Provide support to learners and assist with the resolution of training-related issues.

- Collaborate with the PIU to organize a learning workshop to disseminate information on observations, lessons learned, and recommendations on the adoption of business coaching as a tool for digital skills development in the private sector.

- Develop a detailed program outline, including session objectives, content, and learning materials.

- Create engaging and interactive digital training modules, incorporating case studies, practical exercises, and real-world examples.

- Provide guidance to participants to ensure that they complete all required courses

3.3 Program Coordination and Implementation

- Coordinate the logistics of the program, including venue selection and scheduling

- Deliver the training program through a combination of in-person and online sessions, as appropriate.

- Provide training materials, resources, and access to online platforms for participants.

- Monitor participant progress throughout the program and provide support as needed.

3.4 Evaluation and Reporting

- Develop evaluation tools and mechanisms to assess the effectiveness of the program.

- Conduct regular assessments and gather feedback from participants and mentors.

- Compile and analyze data to measure the impact of the program on participants' skills and business outcomes.

- Prepare comprehensive reports, including recommendations for program improvement.

4. DURATION

The proposed activity is expected to commence in (April 2024) and will have a duration of approximately 2 years.

5. Deliverables

The following will be the expected deliverables of the consultancy:

- Work plan for creating content and delivering training – 1 week after contract signing

- Develop a detailed program outline, including session objectives, content, and learning materials for each of the 4 categories – 4 weeks after contract signing

- Submission of the 4 digital training modules - 3 months after contract signing.

- Execution of 3- 4 cohorts of training (report at the start and end of each cohort)

- Quarterly reports on the number of SMEs being trained.

- Final report on the implementation of the tasks after the two years (2 week before end of contract)

6. QUALIFICATIONS

Skills and Experience

- 3 years’ experience in delivering digital skills training in a hybrid manner (virtual and in-person)

- Proven experience in curriculum and instructional design

- Proven experience in conducting assessments of learners and learning outcomes.

- 3 years’ experience in managing e-learning content and platforms

- Proven experience with education and training, human resource development, or related tasks with youths and SMEs in Grenada.

- Proven knowledge of business management, leadership, and entrepreneurship.

- The team should be made up of persons who are knowledgeable in the 4 different categories (information & data literacy, communication & collaboration, small business operations, and safety.)

 Information & Data Literacy:

- Description: This encompasses the ability to identify, locate, evaluate, and effectively use information to support business decision-making. It involves understanding data sources, data analysis, and interpretation to improve business strategies and outcomes. Training in this area equips small business owners with the skills to harness data for competitive advantage, enhancing their capacity to make informed decisions based on market and customer insights.

 Communication & Collaboration:

- Description: Essential for the modern digital workplace, this skill set focuses on the use of digital tools to communicate and collaborate effectively within and outside the organization. It includes mastering communication platforms, social media, and project management tools that facilitate efficient teamwork and customer interaction. Training aims to improve internal communication processes and external engagement with clients and stakeholders.

 Small Business Operations:

- Description: This area covers the operational aspects of running a small business, including finance management, supply chain logistics, and customer service, tailored for the digital age. Training might involve the use of software for inventory management, e-commerce platforms, and digital accounting tools, enabling business owners to streamline operations and improve productivity.

 Safety:

- Description: In the context of digital transformation, safety training focuses on securing business data, protecting online transactions, and ensuring the privacy of customer information. This includes cybersecurity best practices, risk assessment, and response strategies to mitigate threats in the digital environment. Training ensures that businesses not only adopt new technologies but also safeguard their operations against digital threats.

PART II

Section 8. Conditions of Contract and Contract Forms

Foreword

- Part II includes two types of standard Contract forms for Consulting Services (a Time-Based Contract and a Lump-Sum Contract) that are based on the contract forms included in the harmonized Request for Proposals (RFP) (Master Document for Selection of Consultants prepared by participating Multilateral Development Banks (MDBs).

- Time-Based Contract. This type of contract is appropriate when it is difficult to define or fix the scope and the duration of the services, either because they are related to activities carried out by others for which the completion period may vary, or because the input of the consultants required for attaining the objectives of the assignment is difficult to assess. In time-based contracts the Consultant provides services on a timed basis according to quality specifications, and Consultant’s remuneration is determined on the basis of the time actually spent by the Consultant in carrying out the Services and is based on (i) agreed upon unit rates for the Consultant’s experts multiplied by the actual time spent by the experts in executing the assignment, and (ii) reimbursable expenses using actual expenses and/or agreed unit prices.  This type of contract requires the Client to closely supervise the Consultant and to be involved in the daily execution of the assignment.

- Lump-Sum Contract. This type of contract is used mainly for assignments in which the scope and the duration of the Services and the required output of the Consultant are clearly defined. Payments are linked to outputs (deliverables) such as reports, drawings, bill of quantities, bidding documents, or software programs. Lump-sum contracts are easier to administer because they operate on the principle of a fixed price for a fixed scope, and payments are due on clearly specified outputs and milestones. Nevertheless, quality control of the Consultant’s outputs by the Client is paramount.

- The templates are designed for use in assignments with consulting firms and shall not be used for contracting of individual experts. These standard Contract forms are to be used for complex and/or large value assignments, and/or for contracts above US$300,000 equivalent or more unless otherwise approved by the Bank.

###### Time-Based Form of Contract

STANDARD FORM OF CONTRACT

Consultant’s Services

Time-Based

TABLE OF CONTENTS

I.	Form of Contract	95

II.	General Conditions of Contract	99

A.  General Provisions	99

1.	Definitions	99

2.	Relationship between the Parties	101

3.	Law Governing Contract	101

4.	Language	101

5.	Headings	101

6.	Communications	101

7.	Location	101

8.	Authority of Member in Charge	101

9.	Authorized Representatives	101

10.	Fraud and Corruption	102

11.	Effectiveness of Contract	102

12.	Termination of Contract for Failure to Become Effective	102

13.	Commencement of Services	102

14.	Expiration of Contract	102

15.	Entire Agreement	102

16.	Modifications or Variations	103

17.	Force Majeure	103

18.	Suspension	104

19.	Termination	104

C.  Obligations of the Consultant	107

20.	General	107

21.	Conflict of Interest	108

22.	Confidentiality	109

23.	Liability of the Consultant	109

24.	Insurance to be taken out by the Consultant	109

25.	Accounting, Inspection and Auditing	109

26.	Reporting Obligations	110

27.	Proprietary Rights of the Client in Reports and Records	110

28.	Equipment, Vehicles and Materials	110

29.	Code of Conduct	111

30.	Forced Labor	111

31.	Child Labor	111

32.	Non-Discrimination and Equal Opportunity	112

33.	Training of Experts	113

D.  Consultant’s Experts and Sub-Consultants	113

34.	Description of Key Experts	113

35.	Replacement of Key Experts	113

36.	Approval of Additional Key Experts	114

37.	Removal of Experts or Sub-consultants	114

38.	Replacement/ Removal of Experts – Impact on Payments	115

39.	Working Hours, Overtime, Leave, etc.	115

E.  Obligations of the Client	115

40.	Assistance and Exemptions	115

41.	Access to Project Site	116

42.	Change in the Applicable Law Related to Taxes and Duties	116

43.	Services, Facilities and Property of the Client	116

44.	Counterpart Personnel	117

45.	Payment Obligation	117

46.	Ceiling Amount	117

47.	Remuneration and Reimbursable Expenses	118

48.	Taxes and Duties	118

49.	Currency of Payment	118

50.	Mode of Billing and Payment	118

51.	Interest on Delayed Payments	120

G.  Fairness and Good Faith	120

52.	Good Faith	120

H.  Settlement of Disputes	120

53.	Amicable Settlement	120

54.	Dispute Resolution	121

III.	Special Conditions of Contract	125

IV.	Appendices	135

Appendix A – Terms of Reference	135

Appendix B - Key Experts	135

Appendix C – Remuneration Cost Estimates	135

Appendix D – Reimbursable Expenses Cost Estimates	139

Appendix E - Form of Advance Payments Guarantee	140

Appendix F - Code of Conduct for Experts	142

Appendix G  - Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Performance Declaration for Sub-consultants	143

Contract for Consultant’s Services

Time-Based

Project Name: Caribbean Digital Transformation Project

Credit No.: IDA-66790

Contract No.: GD-PCU - GRENADA-381458-CS-QCBS

Assignment Title: Development and delivery of managerial training

between

Ministry of ICT

and

[Name of the Consultant]

Dated:

Form of Contract

Time-Based

(Text in brackets [ ] is optional; all notes should be deleted in the final text)

This CONTRACT (hereinafter called the “Contract”) is made the [number] day of the month of June, 2024, between, on the one hand, Ministry of ICT (hereinafter called the “Client”) and, on the other hand, [name of Consultant] (hereinafter called the “Consultant”).

[If the Consultant consist of more than one entity, the above should be partially amended to read as follows: “…(hereinafter called the “Client”) and, on the other hand, a Joint Venture (name of the JV) consisting of the following entities, each member of which will be jointly and severally liable to the Client for all the Consultant’s obligations under this Contract, namely, [name of member] and [name of member] (hereinafter called the “Consultant”).]

WHEREAS

(a)	the Client has requested the Consultant to provide certain consulting services as defined in this Contract (hereinafter called the “Services”);

(b)	the Consultant, having represented to the Client that it has the required professional skills, expertise and technical resources, has agreed to provide the Services on the terms and conditions set forth in this Contract;

(c)	the Client has received a credit from the International Development Association (IDA) toward the cost of the Services and intends to apply a portion of the proceeds of this credit to eligible payments under this Contract, it being understood that (i) payments by the Bank will be made only at the request of the Client and upon approval by the Bank; (ii) such payments will be subject, in all respects, to the terms and conditions of the financing agreement, including prohibitions of withdrawal from the credit account for the purpose of any payment to persons or entities, or for any import of goods, if such payment or import, to the knowledge of the Bank, is prohibited by the decision of the United Nations Security council taken under Chapter VII of the Charter of the United Nations; and (iii) no party other than the Client shall derive any rights from the financing agreement or have any claim to the credit proceeds;

NOW THEREFORE the parties hereto hereby agree as follows:

1.	The following documents attached hereto shall be deemed to form an integral part of this Contract:

(a)	The General Conditions of Contract (including Attachment 1 “Fraud and Corruption”;

(b)	The Special Conditions of Contract;

(c)	Appendices:

Appendix A:	Terms of Reference

Appendix B:	Key Experts

Appendix C:	Remuneration Cost Estimates

Appendix D:	Reimbursables Cost Estimates

Appendix E:	Form of Advance Payments Guarantee

Appendix F:	Code of Conduct for Experts

Appendix G :  Sexual exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Performance Declaration

In the event of any inconsistency between the documents, the following order of precedence shall prevail: the Special Conditions of Contract; the General Conditions of Contract, including Attachment 1; Appendix A; Appendix B; Appendix C and Appendix D; Appendix E; and Appendix F; and Appendix G. Any reference to this Contract shall include, where the context permits, a reference to its Appendices.

2.	The mutual rights and obligations of the Client and the Consultant shall be as set forth in the Contract, in particular:

(a)	the Consultant shall carry out the Services in accordance with the provisions of the Contract; and

(b)	the Client shall make payments to the Consultant in accordance with the provisions of the Contract.

IN WITNESS WHEREOF, the Parties hereto have caused this Contract to be signed in their respective names as of the day and year first above written.

For and on behalf of Ministry of ICT

Permanent Secretary of Ministry of ICT

For and on behalf of [Name of Consultant or Name of a Joint Venture]

[Authorized Representative of the Consultant – name and signature]

[For a joint venture, either all members shall sign or only the lead member, in which case the power of attorney to sign on behalf of all members shall be attached.]

For and on behalf of each of the members of the Consultant [insert the name of the Joint Venture]

[Name of the lead member]

[Authorized Representative on behalf of a Joint Venture]

[add signature blocks for each member if all are signing]

General Conditions of Contract

A.  General Provisions

| Definitions | Unless the context otherwise requires, the following terms whenever used in this Contract have the following meanings: - “Applicable Law” means the laws and any other instruments having the force of law in the Client’s country, or in such other country as may be specified in the Special Conditions of Contract (SCC), as they may be issued and in force from time to time. - “Bank” means the International Bank for Reconstruction and Development (IBRD) or the International Development Association (IDA). - “Borrower” means the Government, Government agency or other entity that signs the financing agreement with the Bank. - “Client” means the implementing agency that signs the Contract for the Services with the Selected Consultant. - “Client’s Personnel” refers to the staff, labor and other employees (if any) of the Client engaged in fulfilling the Client’s obligations under the Contract; and any other personnel identified as Client’s Personnel, by a notice from the Client to the Consultant. - “Consultant” means a legally-established professional consulting firm or entity selected by the Client to provide the Services under the signed Contract. - “Contract” means the legally binding written agreement signed between the Client and the Consultant and which includes all the attached documents listed in its paragraph 1 of the Form of Contract (the General Conditions (GCC), the Special Conditions (SCC), and the Appendices). - “Day” means a working day unless indicated otherwise. - “Effective Date” means the date on which this Contract comes into force and effect pursuant to Clause GCC 11. - “Experts” means, collectively, Key Experts, Non-Key Experts, or any other personnel of the Consultant, Sub-consultant or JV member(s) assigned by the Consultant to perform the Services or any part thereof under the Contract. - “Foreign Currency” means any currency other than the currency of the Client’s country. - “GCC” means these General Conditions of Contract. - “Government” means the government of the Client’s country. - “Joint Venture (JV)” means an association with or without a legal personality distinct from that of its members, of more than one entity where one member has the authority to conduct all businesses for and on behalf of any and all the members of the JV, and where the members of the JV are jointly and severally liable to the Client for the performance of the Contract. - “Key Expert(s)” means an individual professional whose skills, qualifications, knowledge and experience are critical to the performance of the Services under the Contract and whose Curricula Vitae (CV) was taken into account in the technical evaluation of the Consultant’s proposal. - “Local Currency” means the currency of the Client’s country. - “Non-Key Expert(s)” means an individual professional provided by the Consultant or its Sub-consultant to perform the Services or any part thereof under the Contract. - “Party” means the Client or the Consultant, as the case may be, and “Parties” means both of them. - “SCC” means the Special Conditions of Contract by which the GCC may be amended or supplemented but not over-written. - “Services” means the work to be performed by the Consultant pursuant to this Contract, as described in Appendix A hereto. - “Sexual Exploitation and Abuse” “(SEA)” means the following: Sexual Exploitation is defined as any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another; Sexual Abuse is defined as the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions. - “Sexual Harassment” “(SH)” is defined as unwelcome sexual advances, requests for sexual favors, and other verbal or physical conduct of a sexual nature by the Experts with other Experts, or Client’s Personnel - “Sub-consultants” means an entity to whom/which the Consultant subcontracts any part of the Services while remaining solely liable for the execution of the Contract. - “Third Party” means any person or entity other than the Government, the Client, the Consultant or a Sub-consultant. |
| --- | --- |
| Relationship between the Parties | Nothing contained herein shall be construed as establishing a relationship of master and servant or of principal and agent as between the Client and the Consultant. The Consultant, subject to this Contract, has complete charge of the Experts and Sub-consultants, if any, performing the Services and shall be fully responsible for the Services performed by them or on their behalf hereunder. |
| Law Governing Contract | This Contract, its meaning and interpretation, and the relation between the Parties shall be governed by the Applicable Law. |
| Language | This Contract has been executed in the language specified in the SCC, which shall be the binding and controlling language for all matters relating to the meaning or interpretation of this Contract. |
| Headings | The headings shall not limit, alter or affect the meaning of this Contract. |
| Communications | Any communication required or permitted to be given or made pursuant to this Contract shall be in writing in the language specified in Clause GCC 4. Any such notice, request or consent shall be deemed to have been given or made when delivered in person to an authorized representative of the Party to whom the communication is addressed, or when sent to such Party at the address specified in the SCC. A Party may change its address for notice hereunder by giving the other Party any communication of such change to the address specified in the SCC. |
| Location | The Services shall be performed at such locations as are specified in Appendix A hereto and, where the location of a particular task is not so specified, at such locations, whether in the Government’s country or elsewhere, as the Client may approve. |
| Authority of Member in Charge | In case the Consultant is a Joint Venture, the members hereby authorize the member specified in the SCC to act on their behalf in exercising all the Consultant’s rights and obligations towards the Client under this Contract, including without limitation the receiving of instructions and payments from the Client. |
| Authorized Representatives | Any action required or permitted to be taken, and any document required or permitted to be executed under this Contract by the Client or the Consultant may be taken or executed by the officials specified in the SCC. |
| Fraud and Corruption | The Bank requires compliance with the Bank’s Anti-Corruption Guidelines and its prevailing sanctions policies and procedures as set forth in the Bank’s Sanctions Framework, as set forth in Attachment 1 to the GCC. |
| a. Commissions and Fees | The Client requires the Consultant to disclose any commissions or fees that may have been paid or are to be paid to agents or any other party with respect to the selection process or execution of the Contract. The information disclosed must include at least the name and address of the agent or other party, the amount and currency, and the purpose of the commission, gratuity or fee. Failure to disclose such commissions, gratuities or fees may result in termination of the Contract and/or sanctions by the Bank. |

# B.  Commencement, Completion, Modification and Termination of Contract

| Effectiveness of Contract | This Contract shall come into force and effect on the date (the “Effective Date”) of the Client’s notice to the Consultant instructing the Consultant to begin carrying out the Services. This notice shall confirm that the effectiveness conditions, if any, listed in the SCC have been met. |
| --- | --- |
| Termination of Contract for Failure to Become Effective | If this Contract has not become effective within such time period after the date of Contract signature as specified in the SCC, either Party may, by not less than twenty two (22) days written notice to the other Party, declare this Contract to be null and void, and in the event of such a declaration by either Party, neither Party shall have any claim against the other Party with respect hereto. |
| Commencement of Services | The Consultant shall confirm availability of Key Experts and begin carrying out the Services not later than the number of days after the Effective Date specified in the SCC. |
| Expiration of Contract | Unless terminated earlier pursuant to Clause GCC 19 hereof, this Contract shall expire at the end of such time period after the Effective Date as specified in the SCC. |
| Entire Agreement | This Contract contains all covenants, stipulations and provisions agreed by the Parties. No agent or representative of either Party has authority to make, and the Parties shall not be bound by or be liable for, any statement, representation, promise or agreement not set forth herein. |
| Modifications or Variations | Any modification or variation of the terms and conditions of this Contract, including any modification or variation of the scope of the Services, may only be made by written agreement between the Parties. However, each Party shall give due consideration to any proposals for modification or variation made by the other Party. |
| Force Majeure |  |
| a. Definition | For the purposes of this Contract, “Force Majeure” means an event which is beyond the reasonable control of a Party, is not foreseeable, is unavoidable, and makes a Party’s performance of its obligations hereunder impossible or so impractical as reasonably to be considered impossible under the circumstances, and subject to those requirements, includes, but is not limited to, war, riots, civil disorder, earthquake, fire, explosion, storm, flood or other adverse weather conditions, strikes, lockouts or other industrial action confiscation or any other action by Government agencies. Force Majeure shall not include (i) any event which is caused by the negligence or intentional action of a Party or such Party’s Experts, Sub-consultants or agents or employees, nor (ii) any event which a diligent Party could reasonably have been expected to both take into account at the time of the conclusion of this Contract, and avoid or overcome in the carrying out of its obligations hereunder. Force Majeure shall not include insufficiency of funds or failure to make any payment required hereunder. |
| b. No Breach of Contract | The failure of a Party to fulfill any of its obligations hereunder shall not be considered to be a breach of, or default under, this Contract insofar as such inability arises from an event of Force Majeure, provided that the Party affected by such an event has taken all reasonable precautions, due care and reasonable alternative measures, all with the objective of carrying out the terms and conditions of this Contract. |
| c. Measures to be Taken | A Party affected by an event of Force Majeure shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall take all reasonable measures to minimize the consequences of any event of Force Majeure. A Party affected by an event of Force Majeure shall notify the other Party of such event as soon as possible, and in any case not later than fourteen (14) calendar days following the occurrence of such event, providing evidence of the nature and cause of such event, and shall similarly give written notice of the restoration of normal conditions as soon as possible. Any period within which a Party shall, pursuant to this Contract, complete any action or task, shall be extended for a period equal to the time during which such Party was unable to perform such action as a result of Force Majeure. During the period of their inability to perform the Services as a result of an event of Force Majeure, the Consultant, upon instructions by the Client, shall either: (a) demobilize, in which case the Consultant shall be reimbursed for additional costs they reasonably and necessarily incurred, and, if required by the Client, in reactivating the Services; or (b) continue with the Services to the extent reasonably possible, in which case the Consultant shall continue to be paid under the terms of this Contract and be reimbursed for additional costs reasonably and necessarily incurred. In the case of disagreement between the Parties as to the existence or extent of Force Majeure, the matter shall be settled according to Clauses GCC 53 & 54. |  |
| Suspension | The Client may, by written notice of suspension to the Consultant, suspend all payments to the Consultant hereunder if the Consultant fails to perform any of its obligations under this Contract, including the carrying out of the Services, provided that such notice of suspension (i) shall specify the nature of the failure, and (ii) shall request the Consultant to remedy such failure within a period not exceeding thirty (30) calendar days after receipt by the Consultant of such notice of suspension. |
| Termination | This Contract may be terminated by either Party as per provisions set up below: |
| a. By the Client | 19.1.1 The Client may terminate this Contract in case of the occurrence of any of the events specified in paragraphs (a) through (f) of this Clause. In such an occurrence the Client shall give at least thirty (30) calendar days’ written notice of termination to the Consultant in case of the events referred to in (a) through (d); at least sixty (60) calendar days’ written notice in case of the event referred to in (e); and at least five (5) calendar days’ written notice in case of the event referred to in (f): (a) If the Consultant fails to remedy a failure in the performance of its obligations hereunder, as specified in a notice of suspension pursuant to Clause GCC 18; (b) If the Consultant becomes (or, if the Consultant consists of more than one entity, if any of its members becomes) insolvent or bankrupt or enter into any agreements with their creditors for relief of debt or take advantage of any law for the benefit of debtors or go into liquidation or receivership whether compulsory or voluntary; (c) If the Consultant fails to comply with any final decision reached as a result of arbitration proceedings pursuant to Clause GCC 54.1; (d) If, as the result of Force Majeure, the Consultant is unable to perform a material portion of the Services for a period of not less than sixty (60) calendar days; (e) If the Client, in its sole discretion and for any reason whatsoever, decides to terminate this Contract; (f) If the Consultant fails to confirm availability of Key Experts as required in Clause GCC 13. 19.1.2 if the Consultant, in the judgment of the Client has engaged in Fraud and Corruption, as defined in paragraph 2.2 a of the Attachment 1 to the GCC, in competing for or in executing the Contract, then the Client may, after giving fourteen (14) calendar days written notice to the Consultant, terminate the Consultant's employment under the Contract. |  |
| b. By the Consultant | 19.1.3 The Consultant may terminate this Contract, by not less than thirty (30) calendar days’ written notice to the Client, in case of the occurrence of any of the events specified in paragraphs (a) through (d) of this Clause. (a) If the Client fails to pay any money due to the Consultant pursuant to this Contract and not subject to dispute pursuant to Clauses GCC 54.1 within forty-five (45) calendar days after receiving written notice from the Consultant that such payment is overdue. (b) If, as the result of Force Majeure, the Consultant is unable to perform a material portion of the Services for a period of not less than sixty (60) calendar days. (c) If the Client fails to comply with any final decision reached as a result of arbitration pursuant to Clause GCC 54.1. (d) If the Client is in material breach of its obligations pursuant to this Contract and has not remedied the same within forty-five (45) days (or such longer period as the Consultant may have subsequently approved in writing) following the receipt by the Client of the Consultant’s notice specifying such breach. |  |
| c. Cessation of Rights and Obligations | 19.1.4 Upon termination of this Contract pursuant to Clauses GCC 12 or GCC 19 hereof, or upon expiration of this Contract pursuant to Clause GCC 14, all rights and obligations of the Parties hereunder shall cease, except (i) such rights and obligations as may have accrued on the date of termination or expiration, (ii) the obligation of confidentiality set forth in Clause GCC 22, (iii) the Consultant’s obligation to permit inspection, copying and auditing of their accounts and records set forth in Clause GCC 25 and to cooperate and assist in any inspection or investigation, and (iv) any right which a Party may have under the Applicable Law. |
| d. Cessation of Services | 19.1.5 Upon termination of this Contract by notice of either Party to the other pursuant to Clauses GCC 19a or GCC 19b, the Consultant shall, immediately upon dispatch or receipt of such notice, take all necessary steps to bring the Services to a close in a prompt and orderly manner and shall make every reasonable effort to keep expenditures for this purpose to a minimum. With respect to documents prepared by the Consultant and equipment and materials furnished by the Client, the Consultant shall proceed as provided, respectively, by Clauses GCC 27 or GCC 28. |
| e. Payment upon Termination | 19.1.6 Upon termination of this Contract, the Client shall make the following payments to the Consultant: (a) remuneration for Services satisfactorily performed prior to the effective date of termination, and reimbursable expenditures for expenditures actually incurred prior to the effective date of termination; and pursuant to Clause GCC 47; (b) in the case of termination pursuant to paragraphs (d) and (e) of Clause GCC 19.1.1, reimbursement of any reasonable cost incidental to the prompt and orderly termination of this Contract, including the cost of the return travel of the Experts. |  |

C.  Obligations of the Consultant

| General |  |
| --- | --- |
| a. Standard of Performance | The Consultant shall perform the Services and carry out the Services with all due diligence, efficiency and economy, in accordance with generally accepted professional standards and practices, and shall observe sound management practices, and employ appropriate technology and safe and effective equipment, machinery, materials and methods. As required in the SCC, the Consultant shall take additional measures to manage cyber security risks related to the Contract. The Consultant shall always act, in respect of any matter relating to this Contract or to the Services, as a faithful adviser to the Client, and shall at all times support and safeguard the Client’s legitimate interests in any dealings with the third parties. The Consultant shall employ and provide such qualified and experienced Experts and Sub-consultants as are required to carry out the Services. The Consultant may subcontract part of the Services to an extent and with such Key Experts and Sub-consultants as may be approved in advance by the Client. Submission by the Consultant for the Client’s approval, for addition of any Sub-consultant not named in the Contract, shall also include the Sub-consultant’s declaration in accordance with Appendix G- Sexual exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Performance Declaration. Notwithstanding such approval, the Consultant shall retain full responsibility for the Services. |
| b. Law Applicable to Services | The Consultant shall perform the Services in accordance with the Contract and the Applicable Law and shall take all practicable steps to ensure that any of its Experts and Sub-consultants, comply with the Applicable Law. Throughout the execution of the Contract, the Consultant shall comply with the import of goods and services prohibitions in the Client’s country when (a) as a matter of law or official regulations, the Borrower’s country prohibits commercial relations with that country; or (b) by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s Country prohibits any import of goods from that country or any payments to any country, person, or entity in that country. The Client shall notify the Consultant in writing of relevant local customs, and the Consultant shall, after such notification, respect such customs. |
| Conflict of Interest | The Consultant shall hold the Client’s interests paramount, without any consideration for future work, and strictly avoid conflict with other assignments or their own corporate interests. |
| a. Consultant Not to Benefit from Commissions, Discounts, etc. | 21.1.1 The payment of the Consultant pursuant to GCC F (Clauses GCC 46 through 51) shall constitute the Consultant’s only payment in connection with this Contract and, subject to Clause GCC 21.1.3, the Consultant shall not accept for its own benefit any trade commission, discount or similar payment in connection with activities pursuant to this Contract or in the discharge of its obligations hereunder, and the Consultant shall use its best efforts to ensure that any Sub-consultants, as well as the Experts and agents of either of them, similarly shall not receive any such additional payment. 21.1.2 Furthermore, if the Consultant, as part of the Services, has the responsibility of advising the Client on the procurement of goods, works or services, the Consultant shall comply with the Bank’s Applicable Regulations, and shall at all times exercise such responsibility in the best interest of the Client. Any discounts or commissions obtained by the Consultant in the exercise of such procurement responsibility shall be for the account of the Client. |
| b. Consultant and Affiliates Not to Engage in Certain Activities | 21.1.3 The Consultant agrees that, during the term of this Contract and after its termination, the Consultant and any entity affiliated with the Consultant, as well as any Sub-consultants and any entity affiliated with such Sub-consultants, shall be disqualified from providing goods, works or non-consulting services resulting from or directly related to the Consultant’s Services for the preparation or implementation of the project. |
| c. Prohibition of Conflicting Activities | 21.1.4 The Consultant shall not engage, and shall cause its Experts as well as its Sub-consultants not to engage, either directly or indirectly, in any business or professional activities that would conflict with the activities assigned to them under this Contract. |
| d. Strict Duty to Disclose Conflicting Activities | 21.1.5 The Consultant has an obligation and shall ensure that its Experts and Sub-consultants shall have an obligation to disclose any situation of actual or potential conflict that impacts their capacity to serve the best interest of their Client, or that may reasonably be perceived as having this effect. Failure to disclose said situations may lead to the disqualification of the Consultant or the termination of its Contract. |
| Confidentiality | Except with the prior written consent of the Client, the Consultant and the Experts shall not at any time communicate to any person or entity any confidential information acquired in the course of the Services, nor shall the Consultant and the Experts make public the recommendations formulated in the course of, or as a result of, the Services. |
| Liability of the Consultant | Subject to additional provisions, if any, set forth in the SCC, the Consultant’s liability under this Contract shall be as determined under the Applicable Law. |
| Insurance to be taken out by the Consultant | The Consultant (i) shall take out and maintain, and shall cause any Sub-consultants to take out and maintain, at its (or the Sub-consultants’, as the case may be) own cost but on terms and conditions approved by the Client, insurance against the risks, and for the coverage specified in the SCC, and (ii) at the Client’s request, shall provide evidence to the Client showing that such insurance has been taken out and maintained and that the current premiums therefore have been paid. The Consultant shall ensure that such insurance is in place prior to commencing the Services as stated in Clause GCC 13. |
| Accounting, Inspection and Auditing | The Consultant shall keep, and shall make all reasonable efforts to cause its Sub-consultants to keep, accurate and systematic accounts and records in respect of the Services in such form and detail as will clearly identify relevant time changes and costs. Pursuant to paragraph 2.2 e. of Attachment 1 to the General Conditions, the Consultant shall permit and shall cause its agents (where declared or not), subcontractors, subconsultants, service providers, suppliers, and personnel, to permit, the Bank and/or persons appointed by the Bank to inspect the site and/or the accounts, records and other documents relating to the procurement process, selection and/or contract execution, and to have such accounts, records and other documents audited by auditors appointed by the Bank. The Consultant’s and its Subcontractors’ and subconsultants’ attention is drawn to Sub-Clause 10.1 (Fraud and Corruption) which provides, inter alia, that acts intended to materially impede the exercise of the Bank’s inspection and audit rights constitute a prohibited practice subject to contract termination (as well as to a determination of ineligibility pursuant to the Bank’s prevailing sanctions procedures). |
| Reporting Obligations | The Consultant shall submit to the Client the reports and documents specified in Appendix A, in the form, in the numbers and within the time periods set forth in the said Appendix. |
| Proprietary Rights of the Client in Reports and Records | Unless otherwise indicated in the SCC, all reports and relevant data and information such as maps, diagrams, plans, databases, other documents and software, supporting records or material compiled or prepared by the Consultant for the Client in the course of the Services shall be confidential and become and remain the absolute property of the Client. The Consultant shall, not later than upon termination or expiration of this Contract, deliver all such documents to the Client, together with a detailed inventory thereof. The Consultant may retain a copy of such documents, data and/or software but shall not use the same for purposes unrelated to this Contract without prior written approval of the Client. If license agreements are necessary or appropriate between the Consultant and third parties for purposes of development of the plans, drawings, specifications, designs, databases, other documents and software, the Consultant shall obtain the Client’s prior written approval to such agreements, and the Client shall be entitled at its discretion to require recovering the expenses related to the development of the program(s) concerned. Other restrictions about the future use of these documents and software, if any, shall be specified in the SCC. |
| Equipment, Vehicles and Materials | Equipment, vehicles and materials made available to the Consultant by the Client, or purchased by the Consultant wholly or partly with funds provided by the Client, shall be the property of the Client and shall be marked accordingly. Upon termination or expiration of this Contract, the Consultant shall make available to the Client an inventory of such equipment, vehicles and materials and shall dispose of such equipment, vehicles and materials in accordance with the Client’s instructions. While in possession of such equipment, vehicles and materials, the Consultant, unless otherwise instructed by the Client in writing, shall insure them at the expense of the Client in an amount equal to their full replacement value. Any equipment or materials brought by the Consultant or its Experts into the Client’s country for the use either for the project or personal use shall remain the property of the Consultant or the Experts concerned, as applicable. |
| Code of Conduct | The Consultant shall have a Code of Conduct for the Experts. The Consultant shall take all necessary measures to ensure that each Expert is made aware of the Code of Conduct including specific behaviors that are prohibited, and understands the consequences of engaging in such prohibited behaviors. These measures include providing instructions and documentation that can be understood by the Experts and seeking to obtain that person’s signature acknowledging receipt of such instructions and/or documentation, as appropriate. The Consultant shall also ensure that the Code of Conduct is visibly displayed in locations where the Services are carried out. The posted Code of Conduct shall be provided in languages comprehensible to Experts and Client’s Personnel. |
| Forced Labor | The Consultant, including its Subconsultants, shall not employ or engage forced labor. Forced labor consists of any work or service, not voluntarily performed, that is exacted from an individual under threat of force or penalty, and includes any kind of involuntary or compulsory labor, such as indentured labor, bonded labor or similar labor-contracting arrangements. No persons shall be employed or engaged who have been subject to trafficking. Trafficking in persons is defined as the recruitment, transportation, transfer, harboring or receipt of persons by means of the threat or use of force or other forms of coercion, abduction, fraud, deception, abuse of power, or of a position of vulnerability, or of the giving or receiving of payments or benefits to achieve the consent of a person having control over another person, for the purposes of exploitation. |
| Child Labor | The Consultant, including its Subconsultants, shall not employ or engage a child under the age of 14 unless the national law specifies a higher age (the minimum age). The Consultant, including its Subconsultants, shall not employ or engage a child between the minimum age and the age of 18 in a manner that is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. The Consultant, including its Subconsultants, shall only employ or engage children between the minimum age and the age of 18 after an appropriate risk assessment has been conducted by the Client. The Consultant shall be subject to regular monitoring by the Client that includes monitoring of health, working conditions and hours of work. Work considered hazardous for children is work that, by its nature or the circumstances in which it is carried out, is likely to jeopardize the health, safety, or morals of children. Such work activities prohibited for children include work: - with exposure to physical, psychological or sexual abuse; - underground, underwater, working at heights or in confined spaces; - with dangerous machinery, equipment or tools, or involving handling or transport of heavy loads; - in unhealthy environments exposing children to hazardous substances, agents, or processes, or to temperatures, noise or vibration damaging to health; or - under difficult conditions such as work for long hours, during the night or in confinement on the premises of the employer. |
| Non-Discrimination and Equal Opportunity | The Consultant shall not make decisions relating to the employment or treatment of Experts on the basis of personal characteristics unrelated to inherent job requirements. The Consultant shall base the employment of Experts on the principle of equal opportunity and fair treatment, and shall not discriminate with respect to any aspects of the employment relationship, including recruitment and hiring, compensation (including wages and benefits), working conditions and terms of employment, access to training, job assignment, promotion, termination of employment or retirement, and disciplinary practices. Special measures of protection or assistance to remedy past discrimination or selection for a particular job based on the inherent requirements of the job shall not be deemed discrimination. The Consultant shall provide protection and assistance as necessary to ensure non-discrimination and equal opportunity, including for specific groups such as women, people with disabilities, migrant workers and children (of working age in accordance with Clause GCC 31). |
| Training of Experts | The Consultant shall provide appropriate training/sensitization to the Experts on social aspects of the Contract, including on prohibition of SEA and SH . The Consultant shall provide training on SEA and SH, including its prevention, to any of its Experts who has a role to supervise other Experts. |

D.  Consultant’s Experts and Sub-Consultants

| Description of Key Experts | The title, agreed job description, minimum qualification and time-input estimates to carry out the Services of each of the Consultant’s Key Experts are described in Appendix B. If required to comply with the provisions of Clause GCC 20a, adjustments with respect to the estimated time-input of Key Experts set forth in Appendix B may be made by the Consultant by a written notice to the Client, provided (i) that such adjustments shall not alter the original time-input estimates for any individual by more than 10% or one week, whichever is larger; and (ii) that the aggregate of such adjustments shall not cause payments under this Contract to exceed the ceilings set forth in Clause GCC 46.2. If additional work is required beyond the scope of the Services specified in Appendix A, the estimated time-input for the Key Experts may be increased by agreement in writing between the Client and the Consultant. In case where payments under this Contract exceed the ceilings set forth in Clause GCC 46.2, the Parties shall sign a Contract amendment. |
| --- | --- |
| Replacement of Key Experts | Except as the Client may otherwise agree in writing, no changes shall be made in the Key Experts. Notwithstanding the above, the substitution of Key Experts during Contract execution may be considered only based on the Consultant’s written request and due to circumstances outside the reasonable control of the Consultant, including but not limited to death or medical incapacity. In such case, the Consultant shall forthwith provide as a replacement, a person of equivalent or better qualifications and experience, meet eligibility requirements, and at the same rate of remuneration. |
| Approval of Additional Key Experts | If during execution of the Contract, additional Key Experts are required to carry out the Services, the Consultant shall submit to the Client for review and approval a copy of their Curricula Vitae (CVs). If the Client does not object in writing (stating the reasons for the objection) within twenty two (22) days from the date of receipt of such CVs, such additional Key Experts shall be deemed to have been approved by the Client. The rate of remuneration payable to such new additional Key Experts shall be based on the rates for other Key Experts position which require similar qualifications and experience. |
| Removal of Experts or Sub-consultants | If the Client finds that any of the Experts or Sub-consultant: - persists in any misconduct or lack of care; - carries out duties incompetently or negligently; - fails to comply with any provision of the Contract; - based on reasonable evidence, is determined to have engaged in Fraud and Corruption during the execution of the Works; or - undertakes behaviour which breaches the Code of Conduct; the Consultant shall, at the Client’s written request, provide a replacement. In the event that any of Key Experts, Non-Key Experts or Sub-consultants is found by the Client to be incompetent or incapable in discharging assigned duties, the Client, specifying the grounds therefore, may request the Consultant to provide a replacement. Any replacement of the removed Experts or Sub-consultants shall possess better qualifications and experience and shall be acceptable to the Client. Subject to the requirements in Sub-Clause 37.3, and notwithstanding any requirement from the Client to request a replacement, the Consultant shall take immediate action as appropriate in response to any violation of (a) through (e) above. Such immediate action shall include removing (or causing to be removed) from carrying out Services, any Expert who engages in (a) to (e) above. |
| Replacement/ Removal of Experts – Impact on Payments | Except as the Client may otherwise agree, (i) the Consultant shall bear all additional travel and other costs arising out of or incidental to any removal and/or replacement, and (ii) the remuneration to be paid for any of the Experts provided as a replacement shall not exceed the remuneration which would have been payable to the Experts replaced or removed. |
| Working Hours, Overtime, Leave, etc. | Working hours and holidays for Experts are set forth in Appendix B. To account for travel time to/from the Client’s country, experts carrying out Services inside the Client’s country shall be deemed to have commenced or finished work in respect of the Services such number of days before their arrival in, or after their departure from, the Client’s country as is specified in Appendix B. The Experts shall not be entitled to be paid for overtime nor to take paid sick leave or vacation leave except as specified in Appendix B, and the Consultant’s remuneration shall be deemed to cover these items. Any taking of leave by Key Experts shall be subject to the prior approval by the Consultant who shall ensure that absence for leave purposes will not delay the progress and or impact adequate supervision of the Services. |

E.  Obligations of the Client

| Assistance and Exemptions | Unless otherwise specified in the SCC, the Client shall use its best efforts to: - Assist the Consultant with obtaining work permits and such other documents as shall be necessary to enable the Consultant to perform the Services. - Assist the Consultant with promptly obtaining, for the Experts and, if appropriate, their eligible dependents, all necessary entry and exit visas, residence permits, exchange permits and any other documents required for their stay in the Client’s country while carrying out the Services under the Contract. - Facilitate prompt clearance through customs of any property required for the Services and of the personal effects of the Experts and their eligible dependents. - Issue to officials, agents and representatives of the Government all such instructions and information as may be necessary or appropriate for the prompt and effective implementation of the Services. - Assist the Consultant and the Experts and any Sub-consultants employed by the Consultant for the Services with obtaining exemption from any requirement to register or obtain any permit to practice their profession or to establish themselves either individually or as a corporate entity in the Client’s country according to the applicable law in the Client’s country. - Assist the Consultant, any Sub-consultants and the Experts of either of them with obtaining the privilege, pursuant to the applicable law in the Client’s country, of bringing into the Client’s country reasonable amounts of foreign currency for the purposes of the Services or for the personal use of the Experts and of withdrawing any such amounts as may be earned therein by the Experts in the execution of the Services. - Provide to the Consultant any such other assistance as may be specified in the SCC. |  |
| --- | --- | --- |
| Access to Project Site | The Client warrants that the Consultant shall have, free of charge, unimpeded access to the project site in respect of which access is required for the performance of the Services. The Client will be responsible for any damage to the project site or any property thereon resulting from such access and will indemnify the Consultant and each of the experts in respect of liability for any such damage, unless such damage is caused by the willful default or negligence of the Consultant or any Sub-consultants or the Experts of either of them. |  |
| Change in the Applicable Law Related to Taxes and Duties | If, after the date of this Contract, there is any change in the applicable law in the Client’s country with respect to taxes and duties which increases or decreases the cost incurred by the Consultant in performing the Services, then the remuneration and reimbursable expenses otherwise payable to the Consultant under this Contract shall be increased or decreased accordingly by agreement between the Parties hereto, and corresponding adjustments shall be made to the ceiling amounts specified in Clause GCC 46.2 |  |
| Services, Facilities and Property of the Client | The Client shall make available to the Consultant and the Experts, for the purposes of the Services and free of any charge, the services, facilities and property described in the Terms of Reference (Appendix A) at the times and in the manner specified in said Appendix A. In case that such services, facilities and property shall not be made available to the Consultant as and when specified in Appendix A, the Parties shall agree on (i) any time extension that it may be appropriate to grant to the Consultant for the performance of the Services, (ii) the manner in which the Consultant shall procure any such services, facilities and property from other sources, and (iii) the additional payments, if any, to be made to the Consultant as a result thereof pursuant to Clause GCC 46.3. |  |
| Counterpart Personnel | The Client shall make available to the Consultant free of charge such professional and support counterpart personnel, to be nominated by the Client with the Consultant’s advice, if specified in Appendix A. If counterpart personnel are not provided by the Client to the Consultant as and when specified in Appendix A, the Client and the Consultant shall agree on (i) how the affected part of the Services shall be carried out, and (ii) the additional payments, if any, to be made by the Client to the Consultant as a result thereof pursuant to Clause GCC 46.3. Professional and support counterpart personnel, excluding Client’s liaison personnel, shall work under the exclusive direction of the Consultant. If any member of the counterpart personnel fails to perform adequately any work assigned to such member by the Consultant that is consistent with the position occupied by such member, the Consultant may request the replacement of such member, and the Client shall not unreasonably refuse to act upon such request. |
| Payment Obligation | In consideration of the Services performed by the Consultant under this Contract, the Client shall make such payments to the Consultant and in such manner as is provided by GCC F below. |  |

# F.  Payments to the Consultant

| Ceiling Amount | An estimate of the cost of the Services is set forth in Appendix C (Remuneration) and Appendix D (Reimbursable expenses). Payments under this Contract shall not exceed the ceilings in foreign currency and in local currency specified in the SCC. For any payments in excess of the ceilings specified in GCC46.2, an amendment to the Contract shall be signed by the Parties referring to the provision of this Contract that evokes such amendment. |
| --- | --- |
| Remuneration and Reimbursable Expenses | The Client shall pay to the Consultant (i) remuneration that shall be determined on the basis of time actually spent by each Expert in the performance of the Services after the date of commencing of Services or such other date as the Parties shall agree in writing; and (ii) reimbursable expenses that are actually and reasonably incurred by the Consultant in the performance of the Services. All payments shall be at the rates set forth in Appendix C and Appendix D. Unless the SCC provides for the price adjustment of the remuneration rates, said remuneration shall be fixed for the duration of the Contract. The remuneration rates shall cover: (i) such salaries and allowances as the Consultant shall have agreed to pay to the Experts as well as factors for social charges and overheads (bonuses or other means of profit-sharing shall not be allowed as an element of overheads), (ii) the cost of backstopping by home office staff not included in the Experts’ list in Appendix B, (iii) the Consultant’s profit, and (iv) any other items as specified in the SCC. Any rates specified for Experts not yet appointed shall be provisional and shall be subject to revision, with the written approval of the Client, once the applicable remuneration rates and allowances are known. |
| Taxes and Duties | The Consultant, Sub-consultants and Experts are responsible for meeting any and all tax liabilities arising out of the Contract unless it is stated otherwise in the SCC. As an exception to the above and as stated in the SCC, all local identifiable indirect taxes (itemized and finalized at Contract negotiations) are reimbursed to the Consultant or are paid by the Client on behalf of the Consultant. |
| Currency of Payment | Any payment under this Contract shall be made in the currency(ies) specified in the SCC. |
| Mode of Billing and Payment | Billings and payments in respect of the Services shall be made as follows: - Advance payment. Within the number of days after the Effective Date, the Client shall pay to the Consultant an advance payment as specified in the SCC. Unless otherwise indicated in the SCC, an advance payment shall be made against an advance payment bank guarantee acceptable to the Client in an amount (or amounts) and in a currency (or currencies) specified in the SCC. Such guarantee (i) is to remain effective until the advance payment has been fully set off, and (ii) is to be in the form set forth in Appendix E, or in such other form as the Client shall have approved in writing. The advance payments will be set off by the Client in equal installments against the statements for the number of months of the Services specified in the SCC until said advance payments have been fully set off. - The Itemized Invoices. As soon as practicable and not later than fifteen (15) days after the end of each calendar month during the period of the Services, or after the end of each time interval otherwise indicated in the SCC, the Consultant shall submit to the Client, in duplicate, itemized invoices, accompanied by the receipts or other appropriate supporting documents, of the amounts payable pursuant to Clauses GCC 49 and GCC 50 for such interval, or any other period indicated in the SCC. Separate invoices shall be submitted for expenses incurred in foreign currency and in local currency. Each invoice shall show remuneration and reimbursable expenses separately. - The Client shall pay the Consultant’s invoices within sixty (60) days after the receipt by the Client of such itemized invoices with supporting documents. Only such portion of an invoice that is not satisfactorily supported may be withheld from payment. Should any discrepancy be found to exist between actual payment and costs authorized to be incurred by the Consultant, the Client may add or subtract the difference from any subsequent payments. - The Final Payment. The final payment under this Clause shall be made only after the final report and a final invoice, identified as such, shall have been submitted by the Consultant and approved as satisfactory by the Client. The Services shall be deemed completed and finally accepted by the Client and the final report and final invoice shall be deemed approved by the Client as satisfactory ninety (90) calendar days after receipt of the final report and final invoice by the Client unless the Client, within such ninety (90) calendar day period, gives written notice to the Consultant specifying in detail deficiencies in the Services, the final report or final invoice. The Consultant shall thereupon promptly make any necessary corrections, and thereafter the foregoing process shall be repeated. Any amount that the Client has paid or has caused to be paid in accordance with this Clause in excess of the amounts payable in accordance with the provisions of this Contract shall be reimbursed by the Consultant to the Client within thirty (30) days after receipt by the Consultant of notice thereof. Any such claim by the Client for reimbursement must be made within twelve (12) calendar months after receipt by the Client of a final report and a final invoice approved by the Client in accordance with the above. - All payments under this Contract shall be made to the accounts of the Consultant specified in the SCC. - With the exception of the final payment under (d) above, payments do not constitute acceptance of the Services nor relieve the Consultant of any obligations hereunder. |
| Interest on Delayed Payments | If the Client had delayed payments beyond fifteen (15) days after the due date stated in Clause GCC 50.1 (c), interest shall be paid to the Consultant on any amount due by, not paid on, such due date for each day of delay at the annual rate stated in the SCC. |

G.  Fairness and Good Faith

| Good Faith | The Parties undertake to act in good faith with respect to each other’s rights under this Contract and to adopt all reasonable measures to ensure the realization of the objectives of this Contract. |
| --- | --- |

H.  Settlement of Disputes

| Amicable Settlement | The Parties shall seek to resolve any dispute amicably by mutual consultation. If either Party objects to any action or inaction of the other Party, the objecting Party may file a written Notice of Dispute to the other Party providing in detail the basis of the dispute. The Party receiving the Notice of Dispute will consider it and respond in writing within fourteen (14) days after receipt. If that Party fails to respond within fourteen (14) days, or the dispute cannot be amicably settled within fourteen (14) days following the response of that Party, Clause GCC 54.1 shall apply. |
| --- | --- |
| Dispute Resolution | Any dispute between the Parties arising under or related to this Contract that cannot be settled amicably may be referred to by either Party to the adjudication/arbitration in accordance with the provisions specified in the SCC. |

II. General Conditions

Attachment 1

Fraud and Corruption

(Text in this Attachment shall not be modified)

- Purpose

  - The Bank’s Anti-Corruption Guidelines and this annex apply with respect to procurement under Bank Investment Project Financing operations.

- Requirements

- The Bank requires that Borrowers (including beneficiaries of Bank financing); bidders (applicants/proposers), consultants, contractors and suppliers; any sub-contractors, sub-consultants, service providers or suppliers; any agents (whether declared or not); and any of their personnel, observe the highest standard of ethics during the procurement process, selection and contract execution of Bank-financed contracts, and refrain from Fraud and Corruption.

- To this end, the Bank:

- Defines, for the purposes of this provision, the terms set forth below as follows:

- “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party;

- “fraudulent practice” is any act or omission, including misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial or other benefit or to avoid an obligation;

- “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party;

- “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;

- “obstructive practice” is:

- deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive, or collusive practice; and/or threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or

- acts intended to materially impede the exercise of the Bank’s inspection and audit rights provided for under paragraph 2.2 e. below.

- Rejects a proposal for award if the Bank determines that the firm or individual recommended for award, any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, suppliers and/ or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;

- In addition to the legal remedies set out in the relevant Legal Agreement, may take other appropriate actions, including declaring misprocurement, if the Bank determines at any time that representatives of the Borrower or of a recipient of any part of the proceeds of the loan engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the procurement process, selection and/or execution of the contract in question,  without the Borrower having taken timely and appropriate action satisfactory to the Bank to address such practices when they occur, including by failing to inform the Bank in a timely manner at the time  they knew of the practices;

- Pursuant to the Bank’s Anti- Corruption Guidelines and in accordance with the Bank’s prevailing sanctions policies and procedures, may sanction a firm or individual, either indefinitely or for a stated period of time, including by publicly declaring such firm or individual ineligible (i) to be awarded or otherwise benefit from a Bank-financed contract, financially or in any other manner; (ii) to be a nominated sub-contractor, consultant, manufacturer or supplier, or service provider of an otherwise eligible firm being awarded a Bank-financed contract; and (iii) to receive the proceeds of any loan made by the Bank or otherwise to participate further in the preparation or implementation of any Bank-financed project;

- Requires that a clause be included in bidding/request for proposals documents and in contracts financed by a Bank loan, requiring (i) bidders (applicants/proposers), consultants, contractors, and suppliers, and their sub-contractors, sub-consultants, service providers, suppliers, agents, personnel, permit the Bank to inspect all accounts, records and other documents relating to the procurement process, selection and/or contract execution,, and to have them audited by auditors appointed by the Bank.

Special Conditions of Contract

| Number of GC Clause | Amendments of, and Supplements to, Clauses in the General Conditions of Contract |
| --- | --- |
| 1.1(a) | The Contract shall be construed in accordance with the law of: Grenada |
| 4.1 | The language is: English |
| 6.1 and 6.2 | The addresses are [fill in at negotiations with the selected firm]: Client : Attention : Facsimile : E-mail (where permitted): Consultant : Attention : Facsimile : E-mail (where permitted) : |
| 8.1 | [Note: If the Consultant consists only of one entity, state “N/A”; OR If the Consultant is a Joint Venture consisting of more than one entity, the name of the JV member whose address is specified in Clause SCC6.1 should be inserted here. ] The Lead Member on behalf of the JV is NOT REQUIRED |
| 9.1 | The Authorized Representatives are: For the Client: Finley Jeffrey, Permanent Secretary of ICT For the Consultant: Kendell Daniel ( Project Manager) |
| 11.1 | The effectiveness conditions are the following: N/A |
| 12.1 | Termination of Contract for Failure to Become Effective: The time period shall be: Twenty-eight (28) Days |
| 13.1 | Commencement of Services: The number of days shall be: Fourteen (14) Confirmation of Key Experts’ availability to start the Assignment shall be submitted to the Client in writing as a written statement signed by each Key Expert. |
| 14.1 | Expiration of Contract: The time period shall be Eighteen (18) Months |
| 23.1 | No additional provisions. |
| 24.1 | The insurance coverage against the risks shall be as follows: [Note: Delete what is not applicable except (a)]. (a) Professional liability insurance, with a minimum coverage of ______________________ [insert amount and currency which should be not less than the total ceiling amount of the Contract]; (b) Third Party motor vehicle liability insurance in respect of motor vehicles operated in the Client’s country by the Consultant or its Experts or Sub-consultants, with a minimum coverage of [insert amount and currency or state “in accordance with the applicable law in the Client’s country”]; (c) Third Party liability insurance, with a minimum coverage of [insert amount and currency or state “in accordance with the applicable law in the Client’s country”]; (d) employer’s liability and workers’ compensation insurance in respect of the experts and Sub-consultants in accordance with the relevant provisions of the applicable law in the Client’s country, as well as, with respect to such Experts, any such life, health, accident, travel or other insurance as may be appropriate; and (e) insurance against loss of or damage to (i) equipment purchased in whole or in part with funds provided under this Contract, (ii) the Consultant’s property used in the performance of the Services, and (iii) any documents prepared by the Consultant in the performance of the Services. |
| 27.1 | [If applicable, insert any exceptions to proprietary rights provision____________________________________] |
| 27.2 | [If there is to be no restriction on the future use of these documents by either Party, this Clause SCC 27.2 should be deleted. If the Parties wish to restrict such use, any of the following options, or any other option agreed to by the Parties, could be used: [The Consultant shall not use these [insert what applies…… documents and software………..] for purposes unrelated to this Contract without the prior written approval of the Client.] OR [The Client shall not use these [insert what applies…….documents and software………..] for purposes unrelated to this Contract without the prior written approval of the Consultant.] OR [Neither Party shall use these [insert what applies…….documents and software………..] for purposes unrelated to this Contract without the prior written approval of the other Party.] |
| 40.1 (a) through (f) | [List here any changes or additions to Clause GCC 40.1. If there are no such changes or additions, delete this Clause SCC 40.1.] |
| 40.1(g) | [List here any other assistance to be provided by the Client. If there is no such other assistance, delete this Clause SCC 40.1(g).] |
| 46.2 | The ceiling in foreign currency or currencies is: ____________________ [insert amount and currency for each currency] [indicate: inclusive or exclusive] of local indirect taxes. The ceiling in local currency is: ___________________ [insert amount and currency] [indicate: inclusive or exclusive] of local indirect taxes. Any indirect local taxes chargeable in respect of this Contract for the Services provided by the Consultant shall [insert as appropriate: “be paid” or “reimbursed”] by the Client [insert as appropriate: “for“ or “to”] the Consultant. The amount of such taxes is ____________________ [insert the amount as finalized at the Contract’s negotiations on the basis of the estimates provided by the Consultant in Form FIN-2 of the Consultant’s Financial Proposal.] |
| 47.3 | Price adjustment on the remuneration “applies” [If the Contract is less than 18 months, price adjustment does not apply. If the Contract has duration of more than 18 months, a price adjustment provision on the remuneration for foreign and/or local inflation shall be included here. The adjustment should be made every 12 months after the date of the contract for remuneration in foreign currency and – except if there is very high inflation in the Client’s country, in which case more frequent adjustments should be provided for – at the same intervals for remuneration in local currency. Remuneration in foreign currency should be adjusted by using the relevant index for salaries in the country of the respective foreign currency (which normally is the country of the Consultant) and remuneration in local currency by using the corresponding index for the Client’s country. A sample provision is provided below for guidance: Payments for remuneration made in [foreign and/or local] currency shall be adjusted as follows: (1) Remuneration paid in foreign currency on the basis of the rates set forth in Appendix C shall be adjusted every 12 months (and, the first time, with effect for the remuneration earned in the 13th calendar month after the date of the Contract Effectiveness date) by applying the following formula: {or } where Rf is the adjusted remuneration; Rfo is the remuneration payable on the basis of the remuneration rates (Appendix C) in foreign currency; If is the official index for salaries in the country of the foreign currency for the first month for which the adjustment is supposed to have effect; and Ifo is the official index for salaries in the country of the foreign currency for the month of the date of the Contract. The Consultant shall state here the name, source institution, and any necessary identifying characteristics of the official index for salaries corresponding to If and Ifo in the adjustment formula for remuneration paid in foreign currency: [Insert the name, source institution, and necessary identifying characteristics of the index for foreign currency, e.g. “Consumer Price Index for all Urban Consumers (CPI-U), not seasonally adjusted; U.S. Department of Labor, Bureau of Labor Statistics”] (2) Remuneration paid in local currency pursuant to the rates set forth in Appendix D shall be adjusted every [insert number] months (and, for the first time, with effect for the remuneration earned in the [insert number]the calendar month after the date of the Contract) by applying the following formula: {or } where Rl is the adjusted remuneration; Rlo is the remuneration payable on the basis of the remuneration rates (Appendix D) in local currency; Il is the official index for salaries in the Client’s country for the first month for which the adjustment is to have effect; and Ilo is the official index for salaries in the Client’s country for the month of the date of the Contract. The Client shall state here the name, source institution, and any necessary identifying characteristics of the official index for salaries corresponding to Il and Ilo in the adjustment formula for remuneration paid in local currency: [Insert the name, source institution, and necessary identifying characteristics of the index for foreign currency] (3) Any part of the remuneration that is paid in a currency different from the currency of the official index for salaries used in the adjustment formula, shall be adjusted by a correction factor X0/X. X0 is the number of units of currency of the country of the official index, equivalent to one unit of the currency of payment on the date of the contract. X is the number of units of currency of the country of the official index, equivalent to one unit of the currency of payment on the first day of the first month for which the adjustment is supposed to have effect. |
| 48.1 and 48.2 | [The Bank leaves it to the Client to decide whether the Consultant (i) should be exempted from indirect local tax, or (ii) should be reimbursed by the Client for any such tax they might have to pay (or that the Client would pay such tax on behalf of the Consultant] The Client warrants that [choose one applicable option consistent with the ITC 16.3 and the outcome of the Contract’s negotiations (Form FIN-2, part B “Indirect Local Tax – Estimates”): If ITC16.3 indicates a tax exemption status, include the following: “the Consultant, the Sub-consultants and the Experts shall be exempt from” OR If ITC16.3 does not indicate the exemption and, depending on whether the Client shall pay the withholding tax or the Consultant has to pay, include the following: “the Client shall pay on behalf of the Consultant, the Sub-consultants and the Experts,” OR “the Client shall reimburse the Consultant, the Sub-consultants and the Experts”] any indirect taxes, duties, fees, levies and other impositions imposed, under the applicable law in the Client’s country, on the Consultant, the Sub-consultants and the Experts in respect of: (a) any payments whatsoever made to the Consultant, Sub-consultants and the Experts (other than nationals or permanent residents of the Client’s country), in connection with the carrying out of the Services; (b) any equipment, materials and supplies brought into the Client’s country by the Consultant or Sub-consultants for the purpose of carrying out the Services and which, after having been brought into such territories, will be subsequently withdrawn by them; (c) any equipment imported for the purpose of carrying out the Services and paid for out of funds provided by the Client and which is treated as property of the Client; (d) any property brought into the Client’s country by the Consultant, any Sub-consultants or the Experts (other than nationals or permanent residents of the Client’s country), or the eligible dependents of such experts for their personal use and which will subsequently be withdrawn by them upon their respective departure from the Client’s country, provided that: - the Consultant, Sub-consultants and experts shall follow the usual customs procedures of the Client’s country in importing property into the Client’s country; and - if the Consultant, Sub-consultants or Experts do not withdraw but dispose of any property in the Client’s country upon which customs duties and taxes have been exempted, the Consultant, Sub-consultants or Experts, as the case may be, (a) shall bear such customs duties and taxes in conformity with the regulations of the Client’s country, or (b) shall reimburse them to the Client if they were paid by the Client at the time the property in question was brought into the Client’s country. |
| 49.1 | The currency [currencies] of payment shall be the following: [list currency(ies) which should be the same as in the Financial Proposal, Form FIN-2] |
| 50.1(a) | [The advance payment could be in either the foreign currency, or the local currency, or both; select the correct wording in the Clause here below. The advance bank payment guarantee should be in the same currency(ies)] The following provisions shall apply to the advance payment and the advance bank payment guarantee: (1) An advance payment [of [insert amount] in foreign currency] [and of [insert amount] in local currency] shall be made within [insert number] days after the Effective Date. The advance payment will be set off by the Client in equal installments against the statements for the first [insert number] months of the Services until the advance payment has been fully set off. (2) The advance bank payment guarantee shall be in the amount and in the currency of the currency(ies) of the advance payment. |
| 50.1(b) | [Delete this Clause SCC 50.1(b) if the Consultant shall have to submit its itemized statements monthly. Otherwise, the following text can be used to indicate the required intervals: The Consultant shall submit to the Client itemized statements at time intervals of __________________ [e.g. “every quarter”, “every six months”, “every two weeks”, etc.]. |
| 50.1(e) | The accounts are: for foreign currency: [insert account]. for local currency: [insert account]. |
| 51.1 | The interest rate is: one (1) per cent |
| 54. | [In contracts with foreign consultants, the Bank requires that the international commercial arbitration in a neutral venue is used.] Disputes shall be settled by arbitration in accordance with the following provisions: 1. Selection of Arbitrators. Each dispute submitted by a Party to arbitration shall be heard by a sole arbitrator or an arbitration panel composed of three (3) arbitrators, in accordance with the following provisions: (a) Where the Parties agree that the dispute concerns a technical matter, they may agree to appoint a sole arbitrator or, failing agreement on the identity of such sole arbitrator within thirty (30) days after receipt by the other Party of the proposal of a name for such an appointment by the Party who initiated the proceedings, either Party may apply to [name an appropriate international professional body, e.g., the Federation Internationale des Ingenieurs-Conseil (FIDIC) of Lausanne, Switzerland] for a list of not fewer than five (5) nominees and, on receipt of such list, the Parties shall alternately strike names therefrom, and the last remaining nominee on the list shall be the sole arbitrator for the matter in dispute. If the last remaining nominee has not been determined in this manner within sixty (60) days of the date of the list, [insert the name of the same professional body as above] shall appoint, upon the request of either Party and from such list or otherwise, a sole arbitrator for the matter in dispute. (b) Where the Parties do not agree that the dispute concerns a technical matter, the Client and the Consultant shall each appoint one (1) arbitrator, and these two arbitrators shall jointly appoint a third arbitrator, who shall chair the arbitration panel. If the arbitrators named by the Parties do not succeed in appointing a third arbitrator within thirty (30) days after the latter of the two (2) arbitrators named by the Parties has been appointed, the third arbitrator shall, at the request of either Party, be appointed by [name an appropriate international appointing authority, e.g., the Secretary General of the Permanent Court of Arbitration, The Hague; the Secretary General of the International Centre for Settlement of Investment Disputes, Washington, D.C.; the International Chamber of Commerce, Paris; etc.]. (c) If, in a dispute subject to paragraph (b) above, one Party fails to appoint its arbitrator within thirty (30) days after the other Party has appointed its arbitrator, the Party which has named an arbitrator may apply to the [name the same appointing authority as in said paragraph (b)] to appoint a sole arbitrator for the matter in dispute, and the arbitrator appointed pursuant to such application shall be the sole arbitrator for that dispute. |
|  | 2. Rules of Procedure. Except as otherwise stated herein, arbitration proceedings shall be conducted in accordance with the rules of procedure for arbitration of the United Nations Commission on International Trade Law (UNCITRAL) as in force on the date of this Contract. 3. Substitute Arbitrators. If for any reason an arbitrator is unable to perform his/her function, a substitute shall be appointed in the same manner as the original arbitrator. 4. Nationality and Qualifications of Arbitrators. The sole arbitrator or the third arbitrator appointed pursuant to paragraphs 1(a) through 1(c) above shall be an internationally recognized legal or technical expert with extensive experience in relation to the matter in dispute and shall not be a national of the Consultant’s home country [Note: If the Consultant consists of more than one entity, add: or of the home country of any of their members or Parties] or of the Government’s country. For the purposes of this Clause, “home country” means any of: (a) the country of incorporation of the Consultant [Note: If the Consultant consists of more than one entity, add: or of any of their members or Parties]; or (b) the country in which the Consultant’s [or any of their members’ or Parties’] principal place of business is located; or (c) the country of nationality of a majority of the Consultant’s [or of any members’ or Parties’] shareholders; or (d) the country of nationality of the Sub-consultants concerned, where the dispute involves a subcontract. |
|  | 5. Miscellaneous. In any arbitration proceeding hereunder: (a) proceedings shall, unless otherwise agreed by the Parties, be held in [select a country which is neither the Client’s country nor the Consultant’s country]; (b) the [type of language] language shall be the official language for all purposes; and (c) the decision of the sole arbitrator or of a majority of the arbitrators (or of the third arbitrator if there is no such majority) shall be final and binding and shall be enforceable in any court of competent jurisdiction, and the Parties hereby waive any objections to or claims of immunity in respect of such enforcement. |

Appendices

Appendix A – Terms of Reference

[This Appendix shall include the final Terms of Reference (TORs) worked out by the Client and the Consultant during the negotiations; dates for completion of various tasks; location of performance for different tasks; detailed reporting requirements; Client’s input, including counterpart personnel assigned by the Client to work on the Consultant’s team; specific tasks that require prior approval by the Client.

Insert the text based on the Section 7 (Terms of Reference) of the ITC in the RFP and modified based on the Forms TECH-1 through TECH-5 in the Consultant’s Proposal. Highlight the changes to Section 7 of the RFP]

Appendix B - Key Experts

[Insert a table based on Form TECH-6 of the Consultant’s Technical Proposal and finalized at the Contract’s negotiations. Attach the CVs (updated and signed by the respective Key Experts) demonstrating the qualifications of Key Experts.]

[Specify Hours of Work for Key Experts:  List here the hours of work for Key Experts; travel time to/ from the Client’s country; entitlement, if any, to leave pay; public holidays in the Client’s country that may affect Consultant’s work; etc. Make sure there is consistency with Form TECH-6. In particular: one month equals twenty two (22) working (billable) days. One working (billable) day shall be not less than eight (8) working (billable) hours. ]

Appendix C – Remuneration Cost Estimates

1.	Monthly rates for the Experts:

[Insert the table with the remuneration rates. The table shall be based on [Form FIN-3] of the Consultant’s Proposal and reflect any changes agreed at the Contract negotiations, if any. The footnote shall list such changes made to [Form FIN-3] at the negotiations or state that none has been made.]

2. 	[When the Consultant has been selected under Quality-Based Selection method, or the Client has requested the Consultant to clarify the breakdown of very high remuneration rates at the Contract’s negotiations also add the following:

“The agreed remuneration rates shall be stated in the attached Model Form I. This form shall be prepared on the basis of Appendix A to Form FIN-3 of the RFP “Consultants’ Representations regarding Costs and Charges” submitted by the Consultant to the Client prior to the Contract’s negotiations.

Should these representations be found by the Client (either through inspections or audits pursuant to Clause GCC 25.2 or through other means) to be materially incomplete or inaccurate, the Client shall be entitled to introduce appropriate modifications in the remuneration rates affected by such materially incomplete or inaccurate representations.  Any such modification shall have retroactive effect and, in case remuneration has already been paid by the Client before any such modification, (i) the Client shall be entitled to offset any excess payment against the next monthly payment to the Consultants, or (ii) if there are no further payments to be made by the Client to the Consultants, the Consultants shall reimburse to the Client any excess payment within thirty (30) days of receipt of a written claim of the Client.  Any such claim by the Client for reimbursement must be made within twelve (12) calendar months after receipt by the Client of a final report and a final statement approved by the Client in accordance with Clause GCC 50.1(d) of this Contract.”

Model Form I

Breakdown of Agreed Fixed Rates in Consultant’s Contract

We hereby confirm that we have agreed to pay to the Experts listed, who will be involved in performing the Services, the basic fees and away from the home office allowances (if applicable) indicated below:

(Expressed in [insert name of currency])*

| Experts |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name | Position | Basic Remuneration rate per Working Month/Day/Year | Social Charges1 | Overhead1 | Subtotal | Profit2 | Away from Home Office Allowance | Agreed Fixed Rate per Working Month/Day/Hour | Agreed Fixed Rate per Working Month/Day/Hour1 |
| Home Office |  |  |  |  |  |  |  |  |  |
| Work in the Client’s Country |  |  |  |  |  |  |  |  |  |

1	Expressed as percentage of 1

2	Expressed as percentage of 4

*    If more than one currency, add a table

Signature	Date

Name and Title:

Appendix D – Reimbursable Expenses Cost Estimates

1. [Insert the table with the reimbursable expenses rates. The table shall be based on [Form FIN-4] of the Consultant’s Proposal and reflect any changes agreed at the Contract negotiations, if any. The footnote shall list such changes made to [Form FIN-4] at the negotiations or state that none has been made.

2. All reimbursable expenses shall be reimbursed at actual cost, unless otherwise explicitly provided in this Appendix, and in no event shall reimbursement be made in excess of the Contract amount. ]

Appendix E - Form of Advance Payments Guarantee

[See Clause GCC 50.1(a) and SCC 50.1(a)]

{Guarantor letterhead or SWIFT identifier code}

Bank Guarantee for Advance Payment

Guarantor: ___________________ [insert commercial Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	_________________ [insert Name and Address of Client]

Date:	____________[insert date]____

ADVANCE PAYMENT GUARANTEE No.:	___________[insert number]______

We have been informed that ____________ [name of Consultant or a name of the Joint Venture, same as appears on the signed Contract] (hereinafter called "the Consultant") has entered into Contract No. _____________ [reference number of the contract] dated ___[insert date]_________ with the Beneficiary, for the provision of __________________ [brief description of Services] (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, an advance payment in the sum of ___________ [insert amount in figures] (                       ) [amount in words] is to be made against an advance payment guarantee.

At the request of the Consultant, we, as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of ___________ [amount in figures] (                       ) [amount in words]1 upon receipt by us of the Beneficiary’s complying demand  supported by the Beneficiary’s a written statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Consultant is  in breach of  its obligation under the Contract because the Consultant:

(a)   	has failed to repay the advance payment in accordance with the Contract conditions, specifying the amount which the Consultant has failed to repay;

(b)	has used the advance payment for purposes other than toward providing the Services under the Contract.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Consultant on its account number ___________ at _________________ [name and address of bank].

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Consultant as indicated in certified statements or invoices marked as “paid” by the Client which shall be presented to us.  This guarantee shall expire, at the latest, upon our receipt of the payment certificate or paid invoice indicating that the Consultant has made full repayment of the amount of the advance payment, or on the __ day of _[month]__________, [year]__,2  whichever is earlier.  Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 revision, ICC Publication No. 758.

_____________________

[signature(s)]

{Note:	All italicized text is for indicative purposes only to assist in preparing this form and shall be deleted from the final product.}

Appendix F - Code of Conduct for Experts

Appendix G  - Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Performance Declaration for Sub-consultants

[The following table shall be filled in for the Consultant, each member of a Joint Venture and each Sub-consultant proposed by the Consultant]

Consultant’s Name: [insert full name]
Date: [insert day, month, year]
Joint Venture Member’s or Sub-consultant’s Name: [insert full name]
RFP No. and title: [insert RFP number and title]
Page [insert page number] of [insert total number] pages

SEA and/or SH Declaration

We: (a) have not been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations (b) are subject to disqualification by the Bank for non-compliance with SEA/ SH obligations (c) had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations. An arbitral award on the disqualification case has been made in our favor.

[If (c) above is applicable, attach evidence of an arbitral award reversing the findings on the issues underlying the disqualification.]

###### Lump-Sum Form of Contract

STANDARD FORM OF CONTRACT

Consultant’s Services

Lump-Sum

TABLE OF CONTENTS

I.	Form of Contract	151

II.	General Conditions of Contract	155

A.  General Provisions	155

1.	Definitions	155

2.	Relationship between the Parties	157

3.	Law Governing Contract	157

4.	Language	157

5.	Headings	157

6.	Communications	157

7.	Location	157

8.	Authority of Member in Charge	158

9.	Authorized Representatives	158

10.	Fraud and Corruption	158

B.  Commencement, Completion, Modification and Termination of Contract	158

11.	Effectiveness of Contract	158

12.	Termination of Contract for Failure to Become Effective	158

13.	Commencement of Services	159

14.	Expiration of Contract	159

15.	Entire Agreement	159

16.	Modifications or Variations	159

17.	Force Majeure	159

18.	Suspension	160

19.	Termination	161

C.  Obligations of the Consultant	163

20.	General	163

21.	Conflict of Interest	164

22.	Confidentiality	165

23.	Liability of the Consultant	165

24.	Insurance to be taken out by the Consultant	165

25.	Accounting, Inspection and Auditing	166

26.	Reporting Obligations	166

27.	Proprietary Rights of the Client in Reports and Records	166

28.	Equipment, Vehicles and Materials	167

29.	Code of Conduct	167

30.	Forced Labor	167

31.	Child Labor	168

32.	Non-Discrimination and Equal Opportunity	169

33.	Training of Experts	169

D.  Consultant’s Experts and Sub-Consultants	169

34.	Description of Key Experts	169

35.	Replacement of Key Experts	169

36.	Removal of Experts or Sub-consultants	170

E.  Obligations of the Client	170

37.	Assistance and Exemptions	170

38.	Access to Project Site	171

39.	Change in the Applicable Law Related to Taxes and Duties	171

40.	Services, Facilities and Property of the Client	172

41.	Counterpart Personnel	172

42.	Payment Obligation	172

F.  Payments to the Consultant	172

43.	Contract Price	172

44.	Taxes and Duties	172

45.	Currency of Payment	173

46.	Mode of Billing and Payment	173

47.	Interest on Delayed Payments	174

G.  Fairness and Good Faith	174

48.	Good Faith	174

H.  Settlement of Disputes	174

49.	Amicable Settlement	174

50.	Dispute Resolution	174

III.	Special Conditions of Contract	177

IV.	Appendices	187

Appendix A – Terms of Reference	187

Appendix B - Key Experts	187

Appendix C – Breakdown of Contract Price	187

Appendix D - Form of Advance Payments Guarantee	190

Appendix E - Code of Conduct for Experts	192

Appendix F  - Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Performance Declaration for Sub-consultants	193

Contract for Consultant’s Services

Lump-Sum

Project Name ___________________________

[Loan/Credit/Grant] No.____________________

Contract No. ____________________________

Assignment Title:_____________________________

between

[Name of the Client]

and

[Name of the Consultant]

Dated:

Form of Contract

Lump-Sum

(Text in brackets [ ] is optional; all notes should be deleted in the final text)

This CONTRACT (hereinafter called the “Contract”) is made the [number] day of the month of [month], [year], between, on the one hand, [name of Client or Recipient] (hereinafter called the “Client”) and, on the other hand, [name of Consultant] (hereinafter called the “Consultant”).

[If the Consultant consist of more than one entity, the above should be partially amended to read as follows: “…(hereinafter called the “Client”) and, on the other hand, a Joint Venture (name of the JV) consisting of the following entities, each member of which will be jointly and severally liable to the Client for all the Consultant’s obligations under this Contract, namely, [name of member] and [name of member] (hereinafter called the “Consultant”).]

WHEREAS

(a)	the Client has requested the Consultant to provide certain consulting services as defined in this Contract (hereinafter called the “Services”);

(b)	the Consultant, having represented to the Client that it has the required professional skills, expertise and technical resources, has agreed to provide the Services on the terms and conditions set forth in this Contract;

(c)	the Client has received [or has applied for] a loan [or credit or grant] from the [insert as relevant, International Bank for Reconstruction and Development (IBRD) or International Development Association (IDA)]: toward the cost of the Services and intends to apply a portion of the proceeds of this [loan/credit/grant] to eligible payments under this Contract, it being understood that (i) payments by the Bank will be made only at the request of the Client and upon approval by the Bank; (ii) such payments will be subject, in all respects, to the terms and conditions of the [loan/financing/grant] agreement, including prohibitions of withdrawal from the [loan/credit/grant] account for the purpose of any payment to persons or entities, or for any import of goods, if such payment or import, to the knowledge of the Bank, is prohibited by the decision of the United Nations Security council taken under Chapter VII of the Charter of the United Nations; and (iii) no party other than the Client shall derive any rights from the [loan/financing/grant] agreement or have any claim to the [loan/credit/grant] proceeds;

NOW THEREFORE the parties hereto hereby agree as follows:

1.	The following documents attached hereto shall be deemed to form an integral part of this Contract:

(a)	The General Conditions of Contract (including Attachment 1 “Fraud and Corruption”);

(b)	The Special Conditions of Contract;

(c)	Appendices:

Appendix A:	Terms of Reference

Appendix B:	Key Experts

Appendix C:	Breakdown of Contract Price

Appendix D:	Form of Advance Payments Guarantee

Appendix E:	Code of Conduct for Experts

Appendix F:    Sexual exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Performance Declaration

In the event of any inconsistency between the documents, the following order of precedence shall prevail: the Special Conditions of Contract; the General Conditions of Contract, including Attachment 1; Appendix A; Appendix B; Appendix C; Appendix D; Appendix E; and Appendix F. Any reference to this Contract shall include, where the context permits, a reference to its Appendices.

2.	The mutual rights and obligations of the Client and the Consultant shall be as set forth in the Contract, in particular:

(a)	the Consultant shall carry out the Services in accordance with the provisions of the Contract; and

(b)	the Client shall make payments to the Consultant in accordance with the provisions of the Contract.

IN WITNESS WHEREOF, the Parties hereto have caused this Contract to be signed in their respective names as of the day and year first above written.

For and on behalf of Ministry of ICT

Finley Jeffrey, Permanent Secretary of ICT

For and on behalf of [Name of Consultant or Name of a Joint Venture]

[Authorized Representative of the Consultant – name and signature]

[For a joint venture, either all members shall sign or only the lead member, in which case the power of attorney to sign on behalf of all members shall be attached.

For and on behalf of each of the members of the Consultant [insert the Name of the Joint Venture]

[Name of the lead member]

[Authorized Representative on behalf of a Joint Venture]

[add signature blocks for each member if all are signing]

General Conditions of Contract

A.  General Provisions

| - Definitions | Unless the context otherwise requires, the following terms whenever used in this Contract have the following meanings: - “Applicable Law” means the laws and any other instruments having the force of law in the Client’s country, or in such other country as may be specified in the Special Conditions of Contract (SCC), as they may be issued and in force from time to time. - “Bank” means the International Bank for Reconstruction and Development (IBRD) or the International Development Association (IDA). - “Borrower” means the Government, Government agency or other entity that signs the financing agreement with the Bank. - “Client” means the implementing agency that signs the Contract for the Services with the Selected Consultant. - Client’s Personnel” refers to the staff, labor and other employees (if any) of the Client engaged in fulfilling the Client’s obligations under the Contract; and any other personnel identified as Client’s Personnel, by a notice from the Client to the Consultant. - “Consultant” means a legally-established professional consulting firm or entity selected by the Client to provide the Services under the signed Contract. - “Contract” means the legally binding written agreement signed between the Client and the Consultant and which includes all the attached documents listed in its paragraph 1 of the Form of Contract (the General Conditions (GCC), the Special Conditions (SCC), and the Appendices). - “Day” means a working day unless indicated otherwise. - “Effective Date” means the date on which this Contract comes into force and effect pursuant to Clause GCC 11. - “Experts” means, collectively, Key Experts, Non-Key Experts, or any other personnel of the Consultant, Sub-consultant or JV member(s) assigned by the Consultant to perform the Services or any part thereof under the Contract. - “Foreign Currency” means any currency other than the currency of the Client’s country. - “GCC” means these General Conditions of Contract. - “Government” means the government of the Client’s country. - “Joint Venture (JV)” means an association with or without a legal personality distinct from that of its members, of more than one entity where one member has the authority to conduct all businesses for and on behalf of any and all the members of the JV, and where the members of the JV are jointly and severally liable to the Client for the performance of the Contract. - “Key Expert(s)” means an individual professional whose skills, qualifications, knowledge and experience are critical to the performance of the Services under the Contract and whose Curricula Vitae (CV) was taken into account in the technical evaluation of the Consultant’s proposal. - “Local Currency” means the currency of the Client’s country. - “Non-Key Expert(s)” means an individual professional provided by the Consultant or its Sub-consultant to perform the Services or any part thereof under the Contract. - “Party” means the Client or the Consultant, as the case may be, and “Parties” means both of them. - “SCC” means the Special Conditions of Contract by which the GCC may be amended or supplemented but not over-written. - “Services” means the work to be performed by the Consultant pursuant to this Contract, as described in Appendix A hereto. - “Sexual Exploitation and Abuse” “(SEA)” means the following: Sexual Exploitation is defined as any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another. Sexual Abuse is defined as the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions. - “Sexual Harassment” “(SH)” is defined as unwelcome sexual advances, requests for sexual favors, and other verbal or physical conduct of a sexual nature by the Experts with other Experts or Client’s Personnel. - “Sub-consultants” means an entity to whom/which the Consultant subcontracts any part of the Services while remaining solely liable for the execution of the Contract. - “Third Party” means any person or entity other than the Government, the Client, the Consultant or a Sub-consultant. |
| --- | --- |
| - Relationship between the Parties | Nothing contained herein shall be construed as establishing a relationship of master and servant or of principal and agent as between the Client and the Consultant. The Consultant, subject to this Contract, has complete charge of the Experts and Sub-consultants, if any, performing the Services and shall be fully responsible for the Services performed by them or on their behalf hereunder. |
| - Law Governing Contract | This Contract, its meaning and interpretation, and the relation between the Parties shall be governed by the Applicable Law. |
| - Language | This Contract has been executed in the language specified in the SCC, which shall be the binding and controlling language for all matters relating to the meaning or interpretation of this Contract. |
| - Headings | The headings shall not limit, alter or affect the meaning of this Contract. |
| - Communications | Any communication required or permitted to be given or made pursuant to this Contract shall be in writing in the language specified in Clause GCC 4. Any such notice, request or consent shall be deemed to have been given or made when delivered in person to an authorized representative of the Party to whom the communication is addressed, or when sent to such Party at the address specified in the SCC. A Party may change its address for notice hereunder by giving the other Party any communication of such change to the address specified in the SCC. |
| - Location | The Services shall be performed at such locations as are specified in Appendix A hereto and, where the location of a particular task is not so specified, at such locations, whether in the Government’s country or elsewhere, as the Client may approve. |
| - Authority of Member in Charge | In case the Consultant is a Joint Venture, the members hereby authorize the member specified in the SCC to act on their behalf in exercising all the Consultant’s rights and obligations towards the Client under this Contract, including without limitation the receiving of instructions and payments from the Client. |
| - Authorized Representatives | Any action required or permitted to be taken, and any document required or permitted to be executed under this Contract by the Client or the Consultant may be taken or executed by the officials specified in the SCC. |
| - Fraud and Corruption | The Bank requires compliance with the Bank’s Anti-Corruption Guidelines and its prevailing sanctions policies and procedures as set forth in the Bank’s Sanctions Framework, as set forth in Attachment 1 to the GCC. |
| a. Commissions and Fees | The Client requires the Consultant to disclose any commissions, gratuities or fees that may have been paid or are to be paid to agents or any other party with respect to the selection process or execution of the Contract. The information disclosed must include at least the name and address of the agent or other party, the amount and currency, and the purpose of the commission, gratuity or fee. Failure to disclose such commissions, gratuities or fees may result in termination of the Contract and/or sanctions by the Bank. |

B.  Commencement, Completion, Modification and Termination of Contract

| - Effectiveness of Contract | This Contract shall come into force and effect on the date (the “Effective Date”) of the Client’s notice to the Consultant instructing the Consultant to begin carrying out the Services. This notice shall confirm that the effectiveness conditions, if any, listed in the SCC have been met. |
| --- | --- |
| - Termination of Contract for Failure to Become Effective | If this Contract has not become effective within such time period after the date of Contract signature as specified in the SCC, either Party may, by not less than twenty two (22) days written notice to the other Party, declare this Contract to be null and void, and in the event of such a declaration by either Party, neither Party shall have any claim against the other Party with respect hereto. |
| - Commencement of Services | The Consultant shall confirm availability of Key Experts and begin carrying out the Services not later than the number of days after the Effective Date specified in the SCC. |
| - Expiration of Contract | Unless terminated earlier pursuant to Clause GCC 19 hereof, this Contract shall expire at the end of such time period after the Effective Date as specified in the SCC. |
| - Entire Agreement | This Contract contains all covenants, stipulations and provisions agreed by the Parties. No agent or representative of either Party has authority to make, and the Parties shall not be bound by or be liable for, any statement, representation, promise or agreement not set forth herein. |
| - Modifications or Variations | Any modification or variation of the terms and conditions of this Contract, including any modification or variation of the scope of the Services, may only be made by written agreement between the Parties. However, each Party shall give due consideration to any proposals for modification or variation made by the other Party. |
| - Force Majeure |  |
| a. Definition | For the purposes of this Contract, “Force Majeure” means an event which is beyond the reasonable control of a Party, is not foreseeable, is unavoidable, and makes a Party’s performance of its obligations hereunder impossible or so impractical as reasonably to be considered impossible under the circumstances, and subject to those requirements, includes, but is not limited to, war, riots, civil disorder, earthquake, fire, explosion, storm, flood or other adverse weather conditions, strikes, lockouts or other industrial action confiscation or any other action by Government agencies. Force Majeure shall not include (i) any event which is caused by the negligence or intentional action of a Party or such Party’s Experts, Sub-consultants or agents or employees, nor (ii) any event which a diligent Party could reasonably have been expected to both take into account at the time of the conclusion of this Contract, and avoid or overcome in the carrying out of its obligations hereunder. Force Majeure shall not include insufficiency of funds or failure to make any payment required hereunder. |
| b. No Breach of Contract | The failure of a Party to fulfill any of its obligations hereunder shall not be considered to be a breach of, or default under, this Contract insofar as such inability arises from an event of Force Majeure, provided that the Party affected by such an event has taken all reasonable precautions, due care and reasonable alternative measures, all with the objective of carrying out the terms and conditions of this Contract. |
| c. Measures to be Taken | A Party affected by an event of Force Majeure shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall take all reasonable measures to minimize the consequences of any event of Force Majeure. A Party affected by an event of Force Majeure shall notify the other Party of such event as soon as possible, and in any case not later than fourteen (14) calendar days following the occurrence of such event, providing evidence of the nature and cause of such event, and shall similarly give written notice of the restoration of normal conditions as soon as possible. Any period within which a Party shall, pursuant to this Contract, complete any action or task, shall be extended for a period equal to the time during which such Party was unable to perform such action as a result of Force Majeure. During the period of their inability to perform the Services as a result of an event of Force Majeure, the Consultant, upon instructions by the Client, shall either: (a) demobilize, in which case the Consultant shall be reimbursed for additional costs they reasonably and necessarily incurred, and, if required by the Client, in reactivating the Services; or (b) continue with the Services to the extent reasonably possible, in which case the Consultant shall continue to be paid under the terms of this Contract and be reimbursed for additional costs reasonably and necessarily incurred. In the case of disagreement between the Parties as to the existence or extent of Force Majeure, the matter shall be settled according to Clauses GCC 49 & 50. |
| - Suspension | The Client may, by written notice of suspension to the Consultant, suspend part or all payments to the Consultant hereunder if the Consultant fails to perform any of its obligations under this Contract, including the carrying out of the Services, provided that such notice of suspension (i) shall specify the nature of the failure, and (ii) shall request the Consultant to remedy such failure within a period not exceeding thirty (30) calendar days after receipt by the Consultant of such notice of suspension. |
| - Termination | This Contract may be terminated by either Party as per provisions set up below: |
| a. By the Client | 19.1.1. The Client may terminate this Contract in case of the occurrence of any of the events specified in paragraphs (a) through (f) of this Clause. In such an occurrence the Client shall give at least thirty (30) calendar days’ written notice of termination to the Consultant in case of the events referred to in (a) through (d); at least sixty (60) calendar days’ written notice in case of the event referred to in (e); and at least five (5) calendar days’ written notice in case of the event referred to in (f): - If the Consultant fails to remedy a failure in the performance of its obligations hereunder, as specified in a notice of suspension pursuant to Clause GCC 18; - If the Consultant becomes (or, if the Consultant consists of more than one entity, if any of its members becomes) insolvent or bankrupt or enter into any agreements with their creditors for relief of debt or take advantage of any law for the benefit of debtors or go into liquidation or receivership whether compulsory or voluntary; - If the Consultant fails to comply with any final decision reached as a result of arbitration proceedings pursuant to Clause GCC 50.1; - If, as the result of Force Majeure, the Consultant is unable to perform a material portion of the Services for a period of not less than sixty (60) calendar days; - If the Client, in its sole discretion and for any reason whatsoever, decides to terminate this Contract; - If the Consultant fails to confirm availability of Key Experts as required in Clause GCC 13. 19.1.2. Furthermore, if the Client determines that the Consultant has engaged in Fraud and Corruption in competing for or in executing the Contract, then the Client may, after giving fourteen (14) calendar days written notice to the Consultant, terminate the Consultant's employment under the Contract. |
| b. By the Consultant | 19.1.3. The Consultant may terminate this Contract, by not less than thirty (30) calendar days’ written notice to the Client, in case of the occurrence of any of the events specified in paragraphs (a) through (d) of this Clause. - If the Client fails to pay any money due to the Consultant pursuant to this Contract and not subject to dispute pursuant to Clause GCC 45.1 within forty-five (45) calendar days after receiving written notice from the Consultant that such payment is overdue. - If, as the result of Force Majeure, the Consultant is unable to perform a material portion of the Services for a period of not less than sixty (60) calendar days. - If the Client fails to comply with any final decision reached as a result of arbitration pursuant to Clause GCC 50.1. - If the Client is in material breach of its obligations pursuant to this Contract and has not remedied the same within forty-five (45) days (or such longer period as the Consultant may have subsequently approved in writing) following the receipt by the Client of the Consultant’s notice specifying such breach. |
| c. Cessation of Rights and Obligations | 19.1.4. Upon termination of this Contract pursuant to Clauses GCC 12 or GCC 19 hereof, or upon expiration of this Contract pursuant to Clause GCC 14, all rights and obligations of the Parties hereunder shall cease, except (i) such rights and obligations as may have accrued on the date of termination or expiration, (ii) the obligation of confidentiality set forth in Clause GCC 22, (iii) the Consultant’s obligation to permit inspection, copying and auditing of their accounts and records set forth in Clause GCC 25 and to cooperate and assist in any inspection or investigation, and (iv) any right which a Party may have under the Applicable Law. |
| d. Cessation of Services | 19.1.5. Upon termination of this Contract by notice of either Party to the other pursuant to Clauses GCC 19a or GCC 19b, the Consultant shall, immediately upon dispatch or receipt of such notice, take all necessary steps to bring the Services to a close in a prompt and orderly manner and shall make every reasonable effort to keep expenditures for this purpose to a minimum. With respect to documents prepared by the Consultant and equipment and materials furnished by the Client, the Consultant shall proceed as provided, respectively, by Clauses GCC 27 or GCC 28. |
| e. Payment upon Termination | 19.1.6. Upon termination of this Contract, the Client shall make the following payments to the Consultant: - payment for Services satisfactorily performed prior to the effective date of termination; and - in the case of termination pursuant to paragraphs (d) and (e) of Clause GCC 19.1.1, reimbursement of any reasonable cost incidental to the prompt and orderly termination of this Contract, including the cost of the return travel of the Experts. |

C.  Obligations of the Consultant

| - General |  |
| --- | --- |
| a. Standard of Performance | The Consultant shall perform the Services and carry out the Services with all due diligence, efficiency and economy, in accordance with generally accepted professional standards and practices, and shall observe sound management practices, and employ appropriate technology and safe and effective equipment, machinery, materials and methods. As required in the SCC, the Consultant shall take additional measures to manage cyber security risks related to the Contract. The Consultant shall always act, in respect of any matter relating to this Contract or to the Services, as a faithful adviser to the Client, and shall at all times support and safeguard the Client’s legitimate interests in any dealings with the third parties. The Consultant shall employ and provide such qualified and experienced Experts and Sub-consultants as are required to carry out the Services. The Consultant may subcontract part of the Services to an extent and with such Key Experts and Sub-consultants as may be approved in advance by the Client. Submission by the Consultant for the Client’s approval, for addition of any Sub-consultant not named in the Contract, shall also include the Sub-consultant’s declaration in accordance with Appendix F- Sexual exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Performance Declaration. Notwithstanding such approval, the Consultant shall retain full responsibility for the Services. |
| b. Law Applicable to Services | The Consultant shall perform the Services in accordance with the Contract and the Applicable Law and shall take all practicable steps to ensure that any of its Experts and Sub-consultants, comply with the Applicable Law. Throughout the execution of the Contract, the Consultant shall comply with the import of goods and services prohibitions in the Client’s country when - as a matter of law or official regulations, the Borrower’s country prohibits commercial relations with that country; or - by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s Country prohibits any import of goods from that country or any payments to any country, person, or entity in that country. The Client shall notify the Consultant in writing of relevant local customs, and the Consultant shall, after such notification, respect such customs. |
| - Conflict of Interest | The Consultant shall hold the Client’s interests paramount, without any consideration for future work, and strictly avoid conflict with other assignments or their own corporate interests. |
| a. Consultant Not to Benefit from Commissions, Discounts, etc. | 21.1.1 The payment of the Consultant pursuant to GCC F (Clauses GCC 43 through 47) shall constitute the Consultant’s only payment in connection with this Contract and, subject to Clause GCC 21.1.3, the Consultant shall not accept for its own benefit any trade commission, discount or similar payment in connection with activities pursuant to this Contract or in the discharge of its obligations hereunder, and the Consultant shall use its best efforts to ensure that any Sub-consultants, as well as the Experts and agents of either of them, similarly shall not receive any such additional payment. 21.1.2 Furthermore, if the Consultant, as part of the Services, has the responsibility of advising the Client on the procurement of goods, works or services, the Consultant shall comply with the Bank’s Applicable Regulations, and shall at all times exercise such responsibility in the best interest of the Client. Any discounts or commissions obtained by the Consultant in the exercise of such procurement responsibility shall be for the account of the Client. |
| b. Consultant and Affiliates Not to Engage in Certain Activities | 21.1.3 The Consultant agrees that, during the term of this Contract and after its termination, the Consultant and any entity affiliated with the Consultant, as well as any Sub-consultants and any entity affiliated with such Sub-consultants, shall be disqualified from providing goods, works or non-consulting services resulting from or directly related to the Consultant’s Services for the preparation or implementation of the project. |
| c. Prohibition of Conflicting Activities | 21.1.4 The Consultant shall not engage, and shall cause its Experts as well as its Sub-consultants not to engage, either directly or indirectly, in any business or professional activities that would conflict with the activities assigned to them under this Contract. |
| d. Strict Duty to Disclose Conflicting Activities | 21.1.5 The Consultant has an obligation and shall ensure that its Experts and Sub-consultants shall have an obligation to disclose any situation of actual or potential conflict that impacts their capacity to serve the best interest of their Client, or that may reasonably be perceived as having this effect. Failure to disclose said situations may lead to the disqualification of the Consultant or the termination of its Contract. |
| - Confidentiality | Except with the prior written consent of the Client, the Consultant and the Experts shall not at any time communicate to any person or entity any confidential information acquired in the course of the Services, nor shall the Consultant and the Experts make public the recommendations formulated in the course of, or as a result of, the Services. |
| - Liability of the Consultant | Subject to additional provisions, if any, set forth in the SCC, the Consultant’s liability under this Contract shall be provided by the Applicable Law. |
| - Insurance to be taken out by the Consultant | The Consultant (i) shall take out and maintain, and shall cause any Sub-consultants to take out and maintain, at its (or the Sub-consultants’, as the case may be) own cost but on terms and conditions approved by the Client, insurance against the risks, and for the coverage specified in the SCC, and (ii) at the Client’s request, shall provide evidence to the Client showing that such insurance has been taken out and maintained and that the current premiums therefore have been paid. The Consultant shall ensure that such insurance is in place prior to commencing the Services as stated in Clause GCC 13. |
| - Accounting, Inspection and Auditing | The Consultant shall keep, and shall make all reasonable efforts to cause its Sub-consultants to keep, accurate and systematic accounts and records in respect of the Services and in such form and detail as will clearly identify relevant time changes and costs. Pursuant to paragraph 2.2 e. of Attachment 1 to the General Conditions, the Consultant shall permit and shall cause its agents (where declared or not), subcontractors, subconsultants, service providers, suppliers, and personnel, to permit, the Bank and/or persons appointed by the Bank to inspect the site and/or the accounts, records and other documents relating to the procurement process, selection and/or contract execution, and to have such accounts, records and other documents audited by auditors appointed by the Bank. The Consultant’s and its Subcontractors’ and subconsultants’ attention is drawn to Sub-Clause 10.1 (Fraud and Corruption) which provides, inter alia, that acts intended to materially impede the exercise of the Bank’s inspection and audit rights constitute a prohibited practice subject to contract termination (as well as to a determination of ineligibility pursuant to the Bank’s prevailing sanctions procedures). |
| - Reporting Obligations | The Consultant shall submit to the Client the reports and documents specified in Appendix A, in the form, in the numbers and within the time periods set forth in the said Appendix. |
| - Proprietary Rights of the Client in Reports and Records | Unless otherwise indicated in the SCC, all reports and relevant data and information such as maps, diagrams, plans, databases, other documents and software, supporting records or material compiled or prepared by the Consultant for the Client in the course of the Services shall be confidential and become and remain the absolute property of the Client. The Consultant shall, not later than upon termination or expiration of this Contract, deliver all such documents to the Client, together with a detailed inventory thereof. The Consultant may retain a copy of such documents, data and/or software but shall not use the same for purposes unrelated to this Contract without prior written approval of the Client. If license agreements are necessary or appropriate between the Consultant and third parties for purposes of development of the plans, drawings, specifications, designs, databases, other documents and software, the Consultant shall obtain the Client’s prior written approval to such agreements, and the Client shall be entitled at its discretion to require recovering the expenses related to the development of the program(s) concerned. Other restrictions about the future use of these documents and software, if any, shall be specified in the SCC. |
| - Equipment, Vehicles and Materials | Equipment, vehicles and materials made available to the Consultant by the Client, or purchased by the Consultant wholly or partly with funds provided by the Client, shall be the property of the Client and shall be marked accordingly. Upon termination or expiration of this Contract, the Consultant shall make available to the Client an inventory of such equipment, vehicles and materials and shall dispose of such equipment, vehicles and materials in accordance with the Client’s instructions. While in possession of such equipment, vehicles and materials, the Consultant, unless otherwise instructed by the Client in writing, shall insure them at the expense of the Client in an amount equal to their full replacement value. Any equipment or materials brought by the Consultant or its Experts into the Client’s country for the use either for the project or personal use shall remain the property of the Consultant or the Experts concerned, as applicable. |
| - Code of Conduct | The Consultant shall have a Code of Conduct for the Experts. Consultant shall take all necessary measures to ensure that each Expert is made aware of the Code of Conduct including specific behaviors that are prohibited, and understands the consequences of engaging in such prohibited behaviors. These measures include providing instructions and documentation that can be understood by the Expert and seeking to obtain that person’s signature acknowledging receipt of such instructions and/or documentation, as appropriate. The Consultant shall also ensure that the Code of Conduct is visibly displayed in locations where the Services are provided. The posted Code of Conduct shall be provided in languages comprehensible to the Experts and the Client’s Personnel. |
| - Forced Labor | The Consultant, including its Subconsultants, shall not employ or engage forced labor. Forced labor consists of any work or service, not voluntarily performed, that is exacted from an individual under threat of force or penalty, and includes any kind of involuntary or compulsory labor, such as indentured labor, bonded labor or similar labor-contracting arrangements. No persons shall be employed or engaged who have been subject to trafficking. Trafficking in persons is defined as the recruitment, transportation, transfer, harboring or receipt of persons by means of the threat or use of force or other forms of coercion, abduction, fraud, deception, abuse of power, or of a position of vulnerability, or of the giving or receiving of payments or benefits to achieve the consent of a person having control over another person, for the purposes of exploitation. |
| - Child Labor | The Consultant, including its Subconsultants, shall not employ or engage a child under the age of 14 unless the national law specifies a higher age (the minimum age). The Consultant, including its Subconsultants, shall not employ or engage a child between the minimum age and the age of 18 in a manner that is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. The Consultant, including its Subconsultants, shall only employ or engage children between the minimum age and the age of 18 after an appropriate risk assessment has been conducted by the Consultant with the Client’s consent. The Consultant shall be subject to regular monitoring by the Client that includes monitoring of health, working conditions and hours of work. Work considered hazardous for children is work that, by its nature or the circumstances in which it is carried out, is likely to jeopardize the health, safety, or morals of children. Such work activities prohibited for children include work: - with exposure to physical, psychological or sexual abuse; - underground, underwater, working at heights or in confined spaces; - with dangerous machinery, equipment or tools, or involving handling or transport of heavy loads; - in unhealthy environments exposing children to hazardous substances, agents, or processes, or to temperatures, noise or vibration damaging to health; or - under difficult conditions such as work for long hours, during the night or in confinement on the premises of the employer. |
| - Non-Discrimination and Equal Opportunity | The Consultant shall not make decisions relating to the employment or treatment of Experts on the basis of personal characteristics unrelated to inherent job requirements. The Consultant shall base the employment of Experts on the principle of equal opportunity and fair treatment, and shall not discriminate with respect to any aspects of the employment relationship, including recruitment and hiring, compensation (including wages and benefits), working conditions and terms of employment, access to training, job assignment, promotion, termination of employment or retirement, and disciplinary practices. Special measures of protection or assistance to remedy past discrimination or selection for a particular job based on the inherent requirements of the job shall not be deemed discrimination. The Consultant shall provide protection and assistance as necessary to ensure non-discrimination and equal opportunity, including for specific groups such as women, people with disabilities, migrant workers and children (of working age in accordance with Clause GCC 31). |
| - Training of Experts | The Consultant shall provide appropriate sensitization to the Experts on social aspects of the Contract, including on prohibition of SEA and SH. The Consultant shall provide training on SEA and SH, including its prevention, to any of its Experts who has a role to supervise other Experts. |

D.  Consultant’s Experts and Sub-Consultants

| - Description of Key Experts | The title, agreed job description, minimum qualification and estimated period of engagement to carry out the Services of each of the Consultant’s Key Experts are described in Appendix B. |
| --- | --- |
| - Replacement of Key Experts | Except as the Client may otherwise agree in writing, no changes shall be made in the Key Experts. Notwithstanding the above, the substitution of Key Experts during Contract execution may be considered only based on the Consultant’s written request and due to circumstances outside the reasonable control of the Consultant, including but not limited to death or medical incapacity. In such case, the Consultant shall forthwith provide as a replacement, a person of equivalent or better qualifications and experience, and at the same rate of remuneration. |
| - Removal of Experts or Sub-consultants | If the Client finds that any of the Experts or Sub-consultant: - persists in any misconduct or lack of care; - carries out duties incompetently or negligently; - fails to comply with any provision of the Contract; - based on reasonable evidence, is determined to have engaged in Fraud and Corruption during the execution of the Works; or - undertakes behaviour which breaches the Code of Conduct; - the Consultant shall, at the Client’s written request, provide a replacement. In the event that any of Key Experts, Non-Key Experts or Sub-consultants is found by the Client to be incompetent or incapable in discharging assigned duties, the Client, specifying the grounds therefore, may request the Consultant to provide a replacement. Any replacement of the removed Experts or Sub-consultants shall possess better qualifications and experience and shall be acceptable to the Client. Subject to the requirements in Sub-Clause 36.3, and notwithstanding any requirement from the Client to request a replacement, the Consultant shall take immediate action as appropriate in response to any violation of (a) through (e) above. Such immediate action shall include removing (or causing to be removed) from carrying out the Services, any Expert who engages in (a) to (e) above. The Consultant shall bear all costs arising out of or incidental to any removal and/or replacement of such Experts. |

E.  Obligations of the Client

| - Assistance and Exemptions | Unless otherwise specified in the SCC, the Client shall use its best efforts to: - Assist the Consultant with obtaining work permits and such other documents as shall be necessary to enable the Consultant to perform the Services. - Assist the Consultant with promptly obtaining, for the Experts and, if appropriate, their eligible dependents, all necessary entry and exit visas, residence permits, exchange permits and any other documents required for their stay in the Client’s country while carrying out the Services under the Contract. - Facilitate prompt clearance through customs of any property required for the Services and of the personal effects of the Experts and their eligible dependents. - Issue to officials, agents and representatives of the Government all such instructions and information as may be necessary or appropriate for the prompt and effective implementation of the Services. - Assist the Consultant and the Experts and any Sub-consultants employed by the Consultant for the Services with obtaining exemption from any requirement to register or obtain any permit to practice their profession or to establish themselves either individually or as a corporate entity in the Client’s country according to the applicable law in the Client’s country. - Assist the Consultant, any Sub-consultants and the Experts of either of them with obtaining the privilege, pursuant to the applicable law in the Client’s country, of bringing into the Client’s country reasonable amounts of foreign currency for the purposes of the Services or for the personal use of the Experts and of withdrawing any such amounts as may be earned therein by the Experts in the execution of the Services. - Provide to the Consultant any such other assistance as may be specified in the SCC. |  |
| --- | --- | --- |
| - Access to Project Site | The Client warrants that the Consultant shall have, free of charge, unimpeded access to the project site in respect of which access is required for the performance of the Services. The Client will be responsible for any damage to the project site or any property thereon resulting from such access and will indemnify the Consultant and each of the experts in respect of liability for any such damage, unless such damage is caused by the willful default or negligence of the Consultant or any Sub-consultants or the Experts of either of them. |  |
| - Change in the Applicable Law Related to Taxes and Duties | If, after the date of this Contract, there is any change in the applicable law in the Client’s country with respect to taxes and duties which increases or decreases the cost incurred by the Consultant in performing the Services, then the remuneration and reimbursable expenses otherwise payable to the Consultant under this Contract shall be increased or decreased accordingly by agreement between the Parties hereto, and corresponding adjustments shall be made to the Contract price amount specified in Clause GCC 39.1 |  |
| - Services, Facilities and Property of the Client | The Client shall make available to the Consultant and the Experts, for the purposes of the Services and free of any charge, the services, facilities and property described in the Terms of Reference (Appendix A) at the times and in the manner specified in said Appendix A. |  |
| - Counterpart Personnel | The Client shall make available to the Consultant free of charge such professional and support counterpart personnel, to be nominated by the Client with the Consultant’s advice, if specified in Appendix A. Professional and support counterpart personnel, excluding Client’s liaison personnel, shall work under the exclusive direction of the Consultant. If any member of the counterpart personnel fails to perform adequately any work assigned to such member by the Consultant that is consistent with the position occupied by such member, the Consultant may request the replacement of such member, and the Client shall not unreasonably refuse to act upon such request. |
| - Payment Obligation | In consideration of the Services performed by the Consultant under this Contract, the Client shall make such payments to the Consultant for the deliverables specified in Appendix A and in such manner as is provided by GCC F below. |  |

F.  Payments to the Consultant

| - Contract Price | The Contract price is fixed and is set forth in the SCC. The Contract price breakdown is provided in Appendix C. Any change to the Contract price specified in Clause GCC 43.1 can be made only if the Parties have agreed to the revised scope of Services pursuant to Clause GCC 16 and have amended in writing the Terms of Reference in Appendix A. |
| --- | --- |
| - Taxes and Duties | The Consultant, Sub-consultants and Experts are responsible for meeting any and all tax liabilities arising out of the Contract unless it is stated otherwise in the SCC. As an exception to the above and as stated in the SCC, all local identifiable indirect taxes (itemized and finalized at Contract negotiations) are reimbursed to the Consultant or are paid by the Client on behalf of the Consultant. |
| - Currency of Payment | Any payment under this Contract shall be made in the currency (ies) of the Contract. |
| - Mode of Billing and Payment | The total payments under this Contract shall not exceed the Contract price set forth in Clause GCC 43.1. The payments under this Contract shall be made in lump-sum instalments against deliverables specified in Appendix A. The payments will be made according to the payment schedule stated in the SCC. 46.2.1 Advance payment: Unless otherwise indicated in the SCC, an advance payment shall be made against an advance payment bank guarantee acceptable to the Client in an amount (or amounts) and in a currency (or currencies) specified in the SCC. Such guarantee (i) is to remain effective until the advance payment has been fully set off, and (ii) is to be in the form set forth in Appendix D, or in such other form as the Client shall have approved in writing. The advance payments will be set off by the Client in equal portions against the lump-sum installments specified in the SCC until said advance payments have been fully set off. 46.2.2 The Lump-Sum Installment Payments. The Client shall pay the Consultant within sixty (60) days after the receipt by the Client of the deliverable(s) and the cover invoice for the related lump-sum installment payment. The payment can be withheld if the Client does not approve the submitted deliverable(s) as satisfactory in which case the Client shall provide comments to the Consultant within the same sixty (60) days period. The Consultant shall thereupon promptly make any necessary corrections, and thereafter the foregoing process shall be repeated. 46.2.3 The Final Payment. The final payment under this Clause shall be made only after the final report have been submitted by the Consultant and approved as satisfactory by the Client. The Services shall then be deemed completed and finally accepted by the Client. The last lump-sum installment shall be deemed approved for payment by the Client within ninety (90) calendar days after receipt of the final report by the Client unless the Client, within such ninety (90) calendar day period, gives written notice to the Consultant specifying in detail deficiencies in the Services, the final report. The Consultant shall thereupon promptly make any necessary corrections, and thereafter the foregoing process shall be repeated. 46.2.4 All payments under this Contract shall be made to the accounts of the Consultant specified in the SCC. 46.2.5 With the exception of the final payment under 46.2.3 above, payments do not constitute acceptance of the whole Services nor relieve the Consultant of any obligations hereunder. |
| - Interest on Delayed Payments | If the Client had delayed payments beyond fifteen (15) days after the due date stated in Clause GCC 46.2.2, interest shall be paid to the Consultant on any amount due by, not paid on, such due date for each day of delay at the annual rate stated in the SCC. |

G.  Fairness and Good Faith

| - Good Faith | The Parties undertake to act in good faith with respect to each other’s rights under this Contract and to adopt all reasonable measures to ensure the realization of the objectives of this Contract. |
| --- | --- |

H.  Settlement of Disputes

| - Amicable Settlement | The Parties shall seek to resolve any dispute amicably by mutual consultation. If either Party objects to any action or inaction of the other Party, the objecting Party may file a written Notice of Dispute to the other Party providing in detail the basis of the dispute. The Party receiving the Notice of Dispute will consider it and respond in writing within fourteen (14) days after receipt. If that Party fails to respond within fourteen (14) days, or the dispute cannot be amicably settled within fourteen (14) days following the response of that Party, Clause GCC 50.1 shall apply. |
| --- | --- |
| - Dispute Resolution | Any dispute between the Parties arising under or related to this Contract that cannot be settled amicably may be referred to by either Party to the adjudication/arbitration in accordance with the provisions specified in the SCC. |

II. General Conditions

Attachment 1

Fraud and Corruption

(Text in this Attachment shall not be modified)

- Purpose

  - The Bank’s Anti-Corruption Guidelines and this annex apply with respect to procurement under Bank Investment Project Financing operations.

- Requirements

- The Bank requires that Borrowers (including beneficiaries of Bank financing); bidders (applicants/proposers), consultants, contractors and suppliers; any sub-contractors, sub-consultants, service providers or suppliers; any agents (whether declared or not); and any of their personnel, observe the highest standard of ethics during the procurement process, selection and contract execution of Bank-financed contracts, and refrain from Fraud and Corruption.

- To this end, the Bank:

- Defines, for the purposes of this provision, the terms set forth below as follows:

- “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party;

- “fraudulent practice” is any act or omission, including misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial or other benefit or to avoid an obligation;

- “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party;

- “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;

- “obstructive practice” is:

- deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive, or collusive practice; and/or threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or

- acts intended to materially impede the exercise of the Bank’s inspection and audit rights provided for under paragraph 2.2 e. below.

- Rejects a proposal for award if the Bank determines that the firm or individual recommended for award, any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, suppliers and/ or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;

- In addition to the legal remedies set out in the relevant Legal Agreement, may take other appropriate actions, including declaring misprocurement, if the Bank determines at any time that representatives of the Borrower or of a recipient of any part of the proceeds of the loan engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the procurement process, selection and/or execution of the contract in question,  without the Borrower having taken timely and appropriate action satisfactory to the Bank to address such practices when they occur, including by failing to inform the Bank in a timely manner at the time  they knew of the practices;

- Pursuant to the Bank’s Anti- Corruption Guidelines and in accordance with the Bank’s prevailing sanctions policies and procedures, may sanction a firm or individual, either indefinitely or for a stated period of time, including by publicly declaring such firm or individual ineligible (i) to be awarded or otherwise benefit from a Bank-financed contract, financially or in any other manner; (ii) to be a nominated sub-contractor, consultant, manufacturer or supplier, or service provider of an otherwise eligible firm being awarded a Bank-financed contract; and (iii) to receive the proceeds of any loan made by the Bank or otherwise to participate further in the preparation or implementation of any Bank-financed project;

- Requires that a clause be included in bidding/request for proposals documents and in contracts financed by a Bank loan, requiring (i) bidders (applicants/proposers), consultants, contractors, and suppliers, and their sub-contractors, sub-consultants, service providers, suppliers, agents, personnel, permit the Bank to inspect all accounts, records and other documents relating to the  procurement process, selection and/or contract execution,, and to have them audited by auditors appointed by the Bank.

Special Conditions of Contract

[Notes in brackets are for guidance purposes only and should be deleted in the final text of the signed contract]

| Number of GC Clause | Amendments of, and Supplements to, Clauses in the General Conditions of Contract |
| --- | --- |
| 1.1(a) | The Contract shall be construed in accordance with the law of Grenada |
| 4.1 | The language is: English |
| 6.1 and 6.2 | The addresses are : Client: Permanent Secretary, Ministry of ICT Street Address: Botanical Gardens Floor/ Room number: 2nd Floor, Financial Complex Building City: St. George’s Country: Grenada Telephone: 473-440-2731 Email address: ps@ict.gov.gd Consultant : Attention : Facsimile : E-mail (where permitted) : |
| 8.1 | [If the Consultant consists only of one entity, state “N/A”; OR If the Consultant is a Joint Venture consisting of more than one entity, the name of the JV member whose address is specified in Clause SCC6.1 should be inserted here. ] The Lead Member on behalf of the JV is ___________ ______________________________ [insert name of the member] |
| 9.1 | The Authorized Representatives are: For the Client: Finley Jeffrey, Permanent Secretary of ICT For the Consultant: [name, title] |
| 11.1 | [Note: If there are no effectiveness conditions, state “N/A”] OR List here any conditions of effectiveness of the Contract, e.g., approval of the Contract by the Bank, effectiveness of the Bank [loan/credit/grant], receipt by the Consultant of an advance payment, and by the Client of an advance payment guarantee (see Clause SCC46.2.1), etc.] The effectiveness conditions are the following: signing of Beneficiary Ownership form |
| 12.1 | Termination of Contract for Failure to Become Effective: The time period shall be Twenty-eight (28) Days |
| 13.1 | Commencement of Services: The number of days shall be Fourteen (14) Days. Confirmation of Key Experts’ availability to start the Assignment shall be submitted to the Client in writing as a written statement signed by each Key Expert. |
| 14.1 | Expiration of Contract: June 2026 The time period shall be 20 months |
| 20.1 | [include the following if the Contract has been assessed to present potential or actual cyber security risks: The Consultant, including its Sub-consultants/suppliers/ service providers shall take all technical and organizational measures necessary to protect the information technology systems and data used in connection with the Contract. Without limiting the foregoing, the Consultant, including its Sub-consultants/ suppliers/ service providers, shall use all reasonable efforts to establish, maintain, implement and comply with, reasonable information technology, information security, cyber security and data protection controls, policies and procedures, including oversight, access controls, encryption, technological and physical safeguards and business continuity/disaster recovery and security plans that are designed to protect against and prevent breach, destruction, loss, unauthorized distribution, use, access, disablement, misappropriation or modification, or other compromise or misuse of or relating to any information technology system or data used in connection with the Contract]. |
| 21 b. | The Client reserves the right to determine on a case-by-case basis whether the Consultant should be disqualified from providing goods, works or non-consulting services due to a conflict of a nature described in Clause GCC 21.1.3 Yes______ No _____ |

| 23.1 | No additional provisions. [OR The following limitation of the Consultant’s Liability towards the Client can be subject to the Contract’s negotiations: “Limitation of the Consultant’s Liability towards the Client: (a) Except in the case of gross negligence or willful misconduct on the part of the Consultant or on the part of any person or a firm acting on behalf of the Consultant in carrying out the Services, the Consultant, with respect to damage caused by the Consultant to the Client’s property, shall not be liable to the Client: (i) for any indirect or consequential loss or damage; and (ii) for any direct loss or damage that exceeds [insert a multiplier, e.g.: one, two, three] times the total value of the Contract; (b) This limitation of liability shall not (i) affect the Consultant’s liability, if any, for damage to Third Parties caused by the Consultant or any person or firm acting on behalf of the Consultant in carrying out the Services; (ii) be construed as providing the Consultant with any limitation or exclusion from liability which is prohibited by the [insert “Applicable Law”, if it is the law of the Client’s country, or insert “applicable law in the Client’s country”, if the Applicable Law stated in Clause SCC1.1 (b) is different from the law of the Client’s country]. [Notes to the Client and the Consultant: Any suggestions made by the Consultant in the Proposal to introduce exclusions/limitations of the Consultant’s liability under the Contract should be carefully scrutinized by the Client and discussed with the Bank prior to accepting any changes to what was included in the issued RFP. In this regard, the Parties should be aware of the Bank’s policy on this matter which is as follows: To be acceptable to the Bank, any limitation of the Consultant’s liability should at the very least be reasonably related to (a) the damage the Consultant might potentially cause to the Client, and (b) the Consultant’s ability to pay compensation using its own assets and reasonably obtainable insurance coverage. The Consultant’s liability shall not be limited to less than a multiplier of the total payments to the Consultant under the Contract for remuneration and reimbursable expenses. A statement to the effect that the Consultant is liable only for the re-performance of faulty Services is not acceptable to the Bank. Also, the Consultant’s liability should never be limited for loss or damage caused by the Consultant’s gross negligence or willful misconduct. The Bank does not accept a provision to the effect that the Client shall indemnify and hold harmless the Consultant against Third Party claims, except, of course, if a claim is based on loss or damage caused by a default or wrongful act of the Client to the extent permissible by the law applicable in the Client’s country.] |
| --- | --- |
| 27.1 | [If applicable, insert any exceptions to proprietary rights provision____________________________________] |
| 27.2 | The Consultant shall not use any data, documents and reports obtained and/or produced under this consultancy for purposes unrelated to this Contract without the prior written approval of the Client. |
| 37.1 (a) through (f) | [List here any changes or additions to Clause GCC 37.1. If there are no such changes or additions, delete this Clause SCC 37.1.] |
| 37.1(g) | [List here any other assistance to be provided by the Client. If there is no such other assistance, delete this Clause SCC 37.1(g).] |
| 43.1 | The Contract price is: ____________________ [insert amount and currency for each currency as applicable] [indicate: inclusive or exclusive] of local indirect taxes. Any indirect local taxes chargeable in respect of this Contract for the Services provided by the Consultant shall [insert as appropriate: “be paid” or “reimbursed”] by the Client [insert as appropriate: “for“ or “to”] the Consultant. The amount of such taxes is ____________________ [insert the amount as finalized at the Contract’s negotiations on the basis of the estimates provided by the Consultant in Form FIN-2 of the Consultant’s Financial Proposal. |
| 44.1 and 44.2 | [The Bank leaves it to the Client to decide whether the Consultant (i) should be exempted from indirect local tax, or (ii) should be reimbursed by the Client for any such tax they might have to pay (or that the Client would pay such tax on behalf of the Consultant] The Client warrants that [choose one applicable option consistent with the ITC 16.3 and the outcome of the Contract’s negotiations (Form FIN-2, part B “Indirect Local Tax – Estimates”): If ITC16.3 indicates a tax exemption status, include the following: “the Consultant, the Sub-consultants and the Experts shall be exempt from” OR If ITC16.3 does not indicate the exemption and, depending on whether the Client shall pay the withholding tax or the Consultant has to pay, include the following: “the Client shall pay on behalf of the Consultant, the Sub-consultants and the Experts,” OR “the Client shall reimburse the Consultant, the Sub-consultants and the Experts”] any indirect taxes, duties, fees, levies and other impositions imposed, under the applicable law in the Client’s country, on the Consultant, the Sub-consultants and the Experts in respect of: (a) any payments whatsoever made to the Consultant, Sub-consultants and the Experts (other than nationals or permanent residents of the Client’s country), in connection with the carrying out of the Services; (b) any equipment, materials and supplies brought into the Client’s country by the Consultant or Sub-consultants for the purpose of carrying out the Services and which, after having been brought into such territories, will be subsequently withdrawn by them; (c) any equipment imported for the purpose of carrying out the Services and paid for out of funds provided by the Client and which is treated as property of the Client; (d) any property brought into the Client’s country by the Consultant, any Sub-consultants or the Experts (other than nationals or permanent residents of the Client’s country), or the eligible dependents of such experts for their personal use and which will subsequently be withdrawn by them upon their respective departure from the Client’s country, provided that: (i) the Consultant, Sub-consultants and experts shall follow the usual customs procedures of the Client’s country in importing property into the Client’s country; and (ii) if the Consultant, Sub-consultants or Experts do not withdraw but dispose of any property in the Client’s country upon which customs duties and taxes have been exempted, the Consultant, Sub-consultants or Experts, as the case may be, (a) shall bear such customs duties and taxes in conformity with the regulations of the Client’s country, or (b) shall reimburse them to the Client if they were paid by the Client at the time the property in question was brought into the Client’s country. |
| 46.2 | The payment schedule: [Payment of installments shall be linked to the deliverables specified in the Terms of Reference in Appendix A] 1st payment: [insert the amount of the installment, percentage of the total Contract price, and the currency. If the first payment is an advance payment, it shall be made against the bank guarantee for the same amount as per GCC 46.2.1] 2nd payment: ________________ ……………:__________________ Final payment: ________________ [Total sum of all installments shall not exceed the Contract price set up in SCC43.1.] |
| 46.2.1 | [The advance payment could be in either the foreign currency, or the local currency, or both; select the correct wording in the Clause here below. The advance bank payment guarantee should be in the same currency(ies)] The following provisions shall apply to the advance payment and the advance bank payment guarantee: (1) An advance payment [of [insert amount] in foreign currency] [and of [insert amount] in local currency] shall be made within [insert number] days after the receipt of an advance bank payment guarantee by the Client. The advance payment will be set off by the Client in equal portions against [list the payments against which the advance is offset]. (2) The advance bank payment guarantee shall be in the amount and in the currency of the currency(ies) of the advance payment. (3) The bank guarantee will be released when the advance payment has been fully set off. |
| 46.2.4 | The accounts are: for foreign currency: [insert account]. for local currency: [insert account]. |
| 47.1 | The interest rate is: 1% |
| 50.1 | [In contracts with foreign consultants, the Bank requires that the international commercial arbitration in a neutral venue is used.] Disputes shall be settled by arbitration in accordance with the following provisions: 1. Selection of Arbitrators. Each dispute submitted by a Party to arbitration shall be heard by a sole arbitrator or an arbitration panel composed of three (3) arbitrators, in accordance with the following provisions: (a) Where the Parties agree that the dispute concerns a technical matter, they may agree to appoint a sole arbitrator or, failing agreement on the identity of such sole arbitrator within thirty (30) days after receipt by the other Party of the proposal of a name for such an appointment by the Party who initiated the proceedings, either Party may apply to [name an appropriate international professional body, e.g., the Federation Internationale des Ingenieurs-Conseil (FIDIC) of Lausanne, Switzerland] for a list of not fewer than five (5) nominees and, on receipt of such list, the Parties shall alternately strike names therefrom, and the last remaining nominee on the list shall be the sole arbitrator for the matter in dispute. If the last remaining nominee has not been determined in this manner within sixty (60) days of the date of the list, [insert the name of the same professional body as above] shall appoint, upon the request of either Party and from such list or otherwise, a sole arbitrator for the matter in dispute. (b) Where the Parties do not agree that the dispute concerns a technical matter, the Client and the Consultant shall each appoint one (1) arbitrator, and these two arbitrators shall jointly appoint a third arbitrator, who shall chair the arbitration panel. If the arbitrators named by the Parties do not succeed in appointing a third arbitrator within thirty (30) days after the latter of the two (2) arbitrators named by the Parties has been appointed, the third arbitrator shall, at the request of either Party, be appointed by [name an appropriate international appointing authority, e.g., the Secretary General of the Permanent Court of Arbitration, The Hague; the Secretary General of the International Centre for Settlement of Investment Disputes, Washington, D.C.; the International Chamber of Commerce, Paris; etc.]. (c) If, in a dispute subject to paragraph (b) above, one Party fails to appoint its arbitrator within thirty (30) days after the other Party has appointed its arbitrator, the Party which has named an arbitrator may apply to the [name the same appointing authority as in said paragraph (b)] to appoint a sole arbitrator for the matter in dispute, and the arbitrator appointed pursuant to such application shall be the sole arbitrator for that dispute. |
|  | 2. Rules of Procedure. Except as otherwise stated herein, arbitration proceedings shall be conducted in accordance with the rules of procedure for arbitration of the United Nations Commission on International Trade Law (UNCITRAL) as in force on the date of this Contract. 3. Substitute Arbitrators. If for any reason an arbitrator is unable to perform his/her function, a substitute shall be appointed in the same manner as the original arbitrator. 4. Nationality and Qualifications of Arbitrators. The sole arbitrator or the third arbitrator appointed pursuant to paragraphs 1(a) through 1(c) above shall be an internationally recognized legal or technical expert with extensive experience in relation to the matter in dispute and shall not be a national of the Consultant’s home country [If the Consultant consists of more than one entity, add: or of the home country of any of their members or Parties] or of the Government’s country. For the purposes of this Clause, “home country” means any of: (a) the country of incorporation of the Consultant [If the Consultant consists of more than one entity, add: or of any of their members or Parties]; or (b) the country in which the Consultant’s [or any of their members’ or Parties’] principal place of business is located; or (c) the country of nationality of a majority of the Consultant’s [or of any members’ or Parties’] shareholders; or (d) the country of nationality of the Sub-consultants concerned, where the dispute involves a subcontract. |
|  | 5. Miscellaneous. In any arbitration proceeding hereunder: (a) proceedings shall, unless otherwise agreed by the Parties, be held in [select a country which is neither the Client’s country nor the Consultant’s country]; (b) the [type of language] language shall be the official language for all purposes; and (c) the decision of the sole arbitrator or of a majority of the arbitrators (or of the third arbitrator if there is no such majority) shall be final and binding and shall be enforceable in any court of competent jurisdiction, and the Parties hereby waive any objections to or claims of immunity in respect of such enforcement. |

Appendices

Appendix A – Terms of Reference

[This Appendix shall include the final Terms of Reference (TORs) worked out by the Client and the Consultant during the negotiations; dates for completion of various tasks; location of performance for different tasks; detailed reporting requirements and list of deliverables against which the payments to the Consultant will be made; Client’s input, including counterpart personnel assigned by the Client to work on the Consultant’s team; specific tasks or actions that require prior approval by the Client.

Insert the text based on the Section 7 (Terms of Reference) of the ITC in the RFP and modified based on the Forms TECH-1 through TECH-5 of the Consultant’s Proposal. Highlight the changes to Section 7 of the RFP]

………………………………………………………………………………………………

Appendix B - Key Experts

[Insert a table based on Form TECH-6 of the Consultant’s Technical Proposal and finalized at the Contract’s negotiations. Attach the CVs (updated and signed by the respective Key Experts) demonstrating the qualifications of Key Experts.]

……………………………………………………………………………………………………

Appendix C – Breakdown of Contract Price

[Insert the table with the unit rates to arrive at the breakdown of the lump-sum price. The table shall be based on [Form FIN-3 and FIN-4] of the Consultant’s Proposal and reflect any changes agreed at the Contract negotiations, if any. The footnote shall list such changes made to [Form FIN-3 and FIN-4] at the negotiations or state that none has been made.]

When the Consultant has been selected under Quality-Based Selection method, also add the following:

“The agreed remuneration rates shall be stated in the attached Model Form I. This form shall be prepared on the basis of Appendix A to Form FIN-3 of the RFP “Consultants’ Representations regarding Costs and Charges” submitted by the Consultant to the Client prior to the Contract’s negotiations.

Should these representations be found by the Client (either through inspections or audits pursuant to Clause GCC 25.2 or through other means) to be materially incomplete or inaccurate, the Client shall be entitled to introduce appropriate modifications in the remuneration rates affected by such materially incomplete or inaccurate representations.  Any such modification shall have retroactive effect and, in case remuneration has already been paid by the Client before any such modification, (i) the Client shall be entitled to offset any excess payment against the next monthly payment to the Consultants, or (ii) if there are no further payments to be made by the Client to the Consultants, the Consultants shall reimburse to the Client any excess payment within thirty (30) days of receipt of a written claim of the Client.  Any such claim by the Client for reimbursement must be made within twelve (12) calendar months after receipt by the Client of a final report and a final statement approved by the Client in accordance with Clause GCC 46.2.3 of this Contract.”]

Model Form I

Breakdown of Agreed Fixed Rates in Consultant’s Contract

We hereby confirm that we have agreed to pay to the Experts listed, who will be involved in performing the Services, the basic fees and away from the home office allowances (if applicable) indicated below:

(Expressed in [insert name of currency])*

| Experts |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name | Position | Basic Remuneration rate per Working Month/Day/Year | Social Charges1 | Overhead1 | Subtotal | Profit2 | Away from Home Office Allowance | Agreed Fixed Rate per Working Month/Day/Hour | Agreed Fixed Rate per Working Month/Day/Hour1 |
| Home Office |  |  |  |  |  |  |  |  |  |
| Work in the Client’s Country |  |  |  |  |  |  |  |  |  |

1	Expressed as percentage of 1

2	Expressed as percentage of 4

*    If more than one currency, add a table

Signature	Date

Name and Title:

Appendix D - Form of Advance Payments Guarantee

[See Clause GCC 42.2.1 and SCC 46.2.1]

{Guarantor letterhead or SWIFT identifier code}

Bank Guarantee for Advance Payment

Guarantor: ___________________ [insert commercial Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	_________________ [insert Name and Address of Client]

Date:	____________[insert date]____

ADVANCE PAYMENT GUARANTEE No.:	___________[insert number]______

We have been informed that ____________ [name of Consultant or a name of the Joint Venture, same as appears on the signed Contract] (hereinafter called "the Consultant") has entered into Contract No. _____________ [reference number of the contract] dated ___[insert date]_________ with the Beneficiary, for the provision of __________________ [brief description of Services] (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, an advance payment in the sum of ___________ [insert amount in figures] (                       ) [amount in words] is to be made against an advance payment guarantee.

At the request of the Consultant, we, as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of ___________ [amount in figures] (                       ) [amount in words]1 upon receipt by us of the Beneficiary’s complying demand  supported by the Beneficiary’s a written statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Consultant is  in breach of its obligation under the Contract because the Consultant:

(a)   	has failed to repay the advance payment in accordance with the Contract conditions, specifying the amount which the Consultant has failed to repay;

(b)	has used the advance payment for purposes other than toward providing the Services under the Contract.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Consultant on their account number ___________ at _________________ [name and address of bank].

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Consultant as indicated in certified statements or invoices marked as “paid” by the Client which shall be presented to us.  This guarantee shall expire, at the latest, upon our receipt of the payment certificate or paid invoice indicating that the Consultant has made full repayment of the amount of the advance payment, or on the __ day of _[month]__________, [year]__,2  whichever is earlier.  Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 revision, ICC Publication No. 758.

_____________________

[signature(s)]

{Note:	All italicized text is for indicative purposes only to assist in preparing this form and shall be deleted from the final product.}

Appendix E - Code of Conduct for Experts

Appendix F  - Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH) Performance Declaration for Sub-consultants

[The following table shall be filled in for the Consultant, each member of a Joint Venture and each Sub-consultant proposed by the Consultant]

Consultant’s Name: [insert full name]
Date: [insert day, month, year]
Joint Venture Member’s or Sub-consultant’s Name: [insert full name]
RFP No. and title: [insert RFP number and title]
Page [insert page number] of [insert total number] pages

SEA and/or SH Declaration

We: (a) have not been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations (b) are subject to disqualification by the Bank for non-compliance with SEA/ SH obligations (c) had been subject to disqualification by the Bank for non-compliance with SEA/ SH obligations. An arbitral award on the disqualification case has been made in our favor.

[If (c) above is applicable, attach evidence of an arbitral award reversing the findings on the issues underlying the disqualification.]

PART III

Section 9. Notification of Intention to Award and Beneficial Ownership Forms

# Notification of Intention to Award

[This Notification of Intention to Award shall be sent to each Consultant whose Financial Proposal was opened. Send this Notification to the authorized representative of the Consultant].

For the attention of Consultant’s authorized representative

Name: [insert authorized representative’s name]

Address: [insert authorized representative’s address]

Telephone/Fax numbers: [insert authorized representative’s telephone/fax numbers]

Email Address: [insert authorized representative’s email address]

[IMPORTANT: insert the date that this Notification is transmitted to all Consultants. The Notification must be sent to all Consultants simultaneously. This means on the same date and as close to the same time as possible.]

DATE OF TRANSMISSION: This Notification is sent by: [email/fax] on [date] (local time)

Notification of Intention to Award

Client: [insert the name of the Client]

Contract title: [insert the name of the contract]

Country: [insert country where RFP is issued]

Loan No. /Credit No. /Grant No.: [insert reference number for loan/credit/grant]

RFP No: [insert RFP reference number from Procurement Plan]

This Notification of Intention to Award (Notification) notifies you of our decision to award the above contract. The transmission of this Notification begins the Standstill Period. During the Standstill Period you may:

- request a debriefing in relation to the evaluation of your Proposal, and/or

- submit a Procurement-related Complaint in relation to the decision to award the contract.

- The successful Consultant

| Name: | [insert name of successful Consultant] |
| --- | --- |
| Address: | [insert address of the successful Consultant] |
| Contract price: | [insert contract price of the successful Consultant] |

- Short listed Consultants [INSTRUCTIONS: insert names of all short listed Consultants and indicate which Consultants submitted Proposals. Where the selection method requires it, state the price offered by each Consultant as read out, and as evaluated. Include overall technical scores and scores assigned for each criterion and sub-criterion. Select Full Technical Proposal (FTP) or Simplified Technical Proposal (STP) in the last column below.]

| Name of Consultant | Submitted Proposal | [use for FTP] Overall technical scores | [use for STP] Overall technical scores | Financial Proposal price (if applicable) | Evaluated Financial Proposal price (if applicable) | Combined score and ranking (if applicable) |
| --- | --- | --- | --- | --- | --- | --- |
| [insert name] | [yes/no] | Criterion (i): [insert score] Criterion (ii): [insert score] Criterion (iii): [insert score] Sub-criterion a: 1: [insert score] 2: [insert score] 3: [insert score] Sub-criterion b: 1: [insert score] 2: [insert score] 3: [insert score] Sub-criterion c: 1: [insert score] 2: [insert score] 3: [insert score] Criterion (iv): [insert score] Criterion (v): [insert score] Total score: [insert score] | Criterion (i): [insert score] Criterion (ii): [insert score] Sub-criterion a: [insert score] Sub-criterion b: [insert score] Sub-criterion c: [insert score] Total score: [insert score] | [Proposal price] | [evaluated price] | Combined Score: [combined score] Ranking: [ranking] |
| [insert name] | [yes/no] | Criterion (i): [insert score] Criterion (ii): [insert score] Criterion (iii): [insert score] Sub-criterion a: 1: [insert score] 2: [insert score] 3: [insert score] Sub-criterion b: 1: [insert score] 2: [insert score] 3: [insert score] Sub-criterion c: 1: [insert score] 2: [insert score] 3: [insert score] Criterion (iv): [insert score] Criterion (v): [insert score] Total score: [insert score] | Criterion (i): [insert score] Criterion (ii): [insert score] Sub-criterion a: [insert score] Sub-criterion b: [insert score] Sub-criterion c: [insert score] Total score: [insert score] | [Proposal price] | [evaluated price] | Combined Score: [combined score] Ranking: [ranking] |
| [insert name] | [yes/no] | Criterion (i): [insert score] Criterion (ii): [insert score] Criterion (iii): [insert score] Sub-criterion a: 1: [insert score] 2: [insert score] 3: [insert score] Sub-criterion b: 1: [insert score] 2: [insert score] 3: [insert score] Sub-criterion c: 1: [insert score] 2: [insert score] 3: [insert score] Criterion (iv): [insert score] Criterion (v): [insert score] Total score: [insert score] | Criterion (i): [insert score] Criterion (ii): [insert score] Sub-criterion a: [insert score] Sub-criterion b: [insert score] Sub-criterion c: [insert score] Total score: [insert score] | [Proposal price] | [evaluated price] | Combined Score: [combined score] Ranking: [ranking] |
| [insert name] | … |  |  |  |  |  |
| … | … |  |  |  |  |  |

- Reason/s why your Proposal was unsuccessful [Delete if the combined score already reveals the reason]

[INSTRUCTIONS; State the reason/s why this Consultant’s Proposal was unsuccessful. Do NOT include: (a) a point by point comparison with another Consultant’s Proposal or (b) information that is marked confidential by the Consultant in its Proposal.]

- How to request a debriefing [This applies only if your proposal was unsuccessful as stated under point (3) above]

DEADLINE: The deadline to request a debriefing expires at midnight on [insert date] (local time). You may request a debriefing in relation to the results of the evaluation of your Proposal. If you decide to request a debriefing your written request must be made within three (3) Business Days of receipt of this Notification of Intention to Award. Provide the contract name, reference number, name of the Consultant, contact details; and address the request for debriefing as follows: Attention: [insert full name of person, if applicable] Title/position: [insert title/position] Agency: [insert name of Client] Email address: [insert email address] Fax number: [insert fax number] delete if not used If your request for a debriefing is received within the 3 Business Days deadline, we will provide the debriefing within five (5) Business Days of receipt of your request. If we are unable to provide the debriefing within this period, the Standstill Period shall be extended by five (5) Business Days after the date that the debriefing is provided. If this happens, we will notify you and confirm the date that the extended Standstill Period will end. The debriefing may be in writing, by phone, video conference call or in person. We shall promptly advise you in writing how the debriefing will take place and confirm the date and time. If the deadline to request a debriefing has expired, you may still request a debriefing. In this case, we will provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of the Contract Award Notice.

- How to make a complaint

DEADLINE: The deadline for submitting a Procurement-related Complaint challenging the decision to award the contract expires on midnight, [insert date] (local time). Provide the contract name, reference number, name of the Consultant, contact details; and address the Procurement-related Complaint as follows: Attention: [insert full name of person, if applicable] Title/position: [insert title/position] Agency: [insert name of Client] Email address: [insert email address] Fax number: [insert fax number] delete if not used [At this point in the procurement process] [ Upon receipt of this notification] you may submit a Procurement-related Complaint challenging the decision to award the contract. You do not need to have requested, or received, a debriefing before making this complaint. Your complaint must be submitted within the Standstill Period and received by us before the Standstill Period ends. Further information: For more information see the “Procurement Regulations for IPF Borrowers (Procurement Regulations) (Annex III).” You should read these provisions before preparing and submitting your complaint. In addition, the World Bank’s Guidance “How to make a Procurement-related Complaint” provides a useful explanation of the process, as well as a sample letter of complaint. In summary, there are four essential requirements: - You must be an ‘interested party’. In this case, that means a Consultant who has submitted a Proposal in this selection process, and is the recipient of a Notification of Intention to Award. - The complaint can only challenge the decision to award the contract. - You must submit the complaint within the deadline stated above. - You must include, in your complaint, all of the information required by the Procurement Regulations (as described in Annex III).

- Standstill Period

DEADLINE: The Standstill Period is due to end at midnight on [insert date] (local time). The Standstill Period lasts ten (10) Business Days after the date of transmission of this Notification of Intention to Award. The Standstill Period may be extended. This may happen where we are unable to provide a debriefing within the five (5) Business Day deadline. If this happens, we will notify you of the extension.

If you have any questions regarding this Notification, please do not hesitate to contact us.

On behalf of [insert the name of the Client]:

Signature: 	______________________________________________

Name:	______________________________________________

Title/position:	______________________________________________

Telephone:	______________________________________________

Email:	______________________________________________

INSTRUCTIONS TO CONSULTANTS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the successful Consultant.  In case of joint venture, the Consultant must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Consultant is any natural person who ultimately owns or controls the Consultant by meeting one or more of the following conditions:

- directly or indirectly holding 25% or more of the shares

- directly or indirectly holding 25% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Consultant

Beneficial Ownership Disclosure Form

Request for Proposal reference No.: [insert identification no]

Name of the Assignment: [insert name of the assignment]

To: [insert complete name of Client]

In response to your notification of award dated [insert date of notification of award] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 25% or more of the shares (Yes / No) | Directly or indirectly holding 25 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Consultant (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 25% or more of the shares

- directly or indirectly holding 25% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Consultant

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Consultant shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 25% or more of the shares

- directly or indirectly holding 25% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Consultant]”

Name of the Consultant: *[insert complete name of the Consultant]_________

Name of the person duly authorized to sign the Proposal on behalf of the Consultant: **[insert complete name of person duly authorized to sign the Proposal]___________

Title of the person signing the Proposal: [insert complete title of the person signing the Proposal]______

Signature of the person named above: [insert signature of person whose name and capacity are shown above]_____

Date signed [insert date of signing] day of [insert month], [insert year]_____

* In the case of the Proposal submitted by a Joint Venture specify the name of the Joint Venture as Consultant. In the event that the Consultant is a joint venture, each reference to “Consultant” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

** Person signing the Proposal shall have the power of attorney given by the Consultant. The power of attorney shall be attached with the Proposal Schedules.

For the avoidance of doubt, a sanctioned party’s ineligibility to be awarded a contract shall include, without limitation, (i) applying for pre-qualification, expressing interest in a consultancy, and bidding, either directly or as a nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider, in respect of such contract, and (ii) entering into an addendum or amendment introducing a material modification to any existing contract.

A nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider (different names are used depending on the particular bidding document) is one which has been: (i) included by the bidder in its pre-qualification application or bid because it brings specific and critical experience and know-how that allow the bidder to meet the qualification requirements for the particular bid; or (ii) appointed by the Borrower.

Inspections in this context usually are investigative (i.e., forensic) in nature.  They involve fact-finding activities undertaken by the Bank or persons appointed by the Bank to address specific matters related to investigations/audits, such as evaluating the veracity of an allegation of possible Fraud and Corruption, through the appropriate mechanisms.  Such activity includes but is not limited to: accessing and examining a firm's or individual's financial records and information, and making copies thereof as relevant; accessing and examining any other documents, data and information (whether in hard copy or electronic format) deemed relevant for the investigation/audit, and making copies thereof as relevant; interviewing staff and other relevant individuals; performing physical inspections and site visits; and obtaining third party verification of information.

For the avoidance of doubt, a sanctioned party’s ineligibility to be awarded a contract shall include, without limitation, (i) applying for pre-qualification, expressing interest in a consultancy, and bidding, either directly or as a nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider, in respect of such contract, and (ii) entering into an addendum or amendment introducing a material modification to any existing contract.

A nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider (different names are used depending on the particular bidding document) is one which has been: (i) included by the bidder in its pre-qualification application or bid because it brings specific and critical experience and know-how that allow the bidder to meet the qualification requirements for the particular bid; or (ii) appointed by the Borrower.

Inspections in this context usually are investigative (i.e., forensic) in nature.  They involve fact-finding activities undertaken by the Bank or persons appointed by the Bank to address specific matters related to investigations/audits, such as evaluating the veracity of an allegation of possible Fraud and Corruption, through the appropriate mechanisms.  Such activity includes but is not limited to: accessing and examining a firm's or individual's financial records and information, and making copies thereof as relevant; accessing and examining any other documents, data and information (whether in hard copy or electronic format) deemed relevant for the investigation/audit, and making copies thereof as relevant; interviewing staff and other relevant individuals; performing physical inspections and site visits; and obtaining third party verification of information.

1	The Guarantor shall insert an amount representing the amount of the advance payment and denominated either in the currency(ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the Client.

2	Insert the expected expiration date. In the event of an extension of the time for completion of the Contract, the Client would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Client might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Client’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”

For the avoidance of doubt, a sanctioned party’s ineligibility to be awarded a contract shall include, without limitation, (i) applying for pre-qualification, expressing interest in a consultancy, and bidding, either directly or as a nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider, in respect of such contract, and (ii) entering into an addendum or amendment introducing a material modification to any existing contract.

A nominated sub-contractor, nominated consultant, nominated manufacturer or supplier, or nominated service provider (different names are used depending on the particular bidding document) is one which has been: (i) included by the bidder in its pre-qualification application or bid because it brings specific and critical experience and know-how that allow the bidder to meet the qualification requirements for the particular bid; or (ii) appointed by the Borrower.

Inspections in this context usually are investigative (i.e., forensic) in nature.  They involve fact-finding activities undertaken by the Bank or persons appointed by the Bank to address specific matters related to investigations/audits, such as evaluating the veracity of an allegation of possible Fraud and Corruption, through the appropriate mechanisms.  Such activity includes but is not limited to: accessing and examining a firm's or individual's financial records and information, and making copies thereof as relevant; accessing and examining any other documents, data and information (whether in hard copy or electronic format) deemed relevant for the investigation/audit, and making copies thereof as relevant; interviewing staff and other relevant individuals; performing physical inspections and site visits; and obtaining third party verification of information.

1	The Guarantor shall insert an amount representing the amount of the advance payment and denominated either in the currency(ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the Client.

2	Insert the expected expiration date. In the event of an extension of the time for completion of the Contract, the Client would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Client might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Client’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”